FC BARCELONA BANC Phase 1 Marketing Plan — CMO Challenge Memo Prepared: May 10, 2026 · 14 days to announcement · CONFIDENTIAL

EXECUTIVE SUMMARY The plan is honest and the plan is behind. FCBarcelonaBanc_Marketing.docx is a composite of five distinct document layers — timeline table, scope mapping, Surgence proposal v6, Phase 1 Marketing Plan v2, and a competitor analysis — assembled into a single file. Where the plan is written, it is good. The problem is what is not written. As of May 10, with 14 days to the May 24 announcement: the Surgence contract is unsigned, brand identity does not exist, the landing page does not exist, paid media budget is 'TBD', and 11 of 24 workstreams have no owner. Identification of gaps is not resolution of gaps. This memo converts the document's own self-awareness into an action-forcing instrument.

01  DOCUMENT STRUCTURE

The file is not a single coherent plan. It is five distinct document layers assembled into one 714-paragraph, 57-table Word file. Understanding the layers is prerequisite to using the plan correctly.

| Layer | Name | Status / Notes |
| --- | --- | --- |
| Layer 1 | Timeline table | High-level launch calendar with May 24 anchor, World Cup window, and TGE date. Directionally correct; not a project plan. |
| Layer 2 | Scope mapping | Surgence deliverables list. 13 workstreams confirmed in scope; 11 have no assigned owner as of this date. |
| Layer 3 | Surgence Proposal v6 | The commercial proposal from Surgence Labs — retainer terms, team structure, deliverable cadence. Contract unsigned as of May 10. |
| Layer 4 | Phase 1 Marketing Plan v2 | The substantive marketing strategy: audience segments, World Cup mechanics, creator program, Loyalty Dividend, engagement architecture. This is the strong layer. |
| Layer 5 | Competitor analysis | Nubank, Chime, Revolut, Mercado Pago benchmarks. Grades Barça Banc's own readiness relative to comps. Candidly negative self-assessment embedded. |

02  WORKSTREAM OWNERSHIP MAP

The Surgence scope lists 24 workstreams. 13 are confirmed. 11 have no named owner. Unowned workstreams at T-14 are not gaps — they are failure modes.

| Workstream | Owner | Status |  |
| --- | --- | --- | --- |
| Brand Identity System | Surgence | CONFIRMED | ● |
| World Cup Campaign Creative | Surgence | CONFIRMED | ● |
| Daily Player Drop (Instagram) | Surgence | CONFIRMED | ● |
| Community Seeding (WhatsApp/Reddit/FB) | Surgence | CONFIRMED | ● |
| Loyalty Dividend Mechanic | Surgence | CONFIRMED | ● |
| Country-Edition Cards Design | Surgence | CONFIRMED | ● |
| Bracket Prediction Game | Surgence | CONFIRMED | ● |
| MOTM Cashback Integration | Surgence | CONFIRMED | ● |
| Win Bonus Mechanic | Surgence | CONFIRMED | ● |
| Country Boost Days | Surgence | CONFIRMED | ● |
| Korea Web2-First Activation | Surgence | CONFIRMED | ● |
| Community Advisory Layer | Surgence | CONFIRMED | ● |
| Content Governance Framework | Surgence | CONFIRMED | ● |
| Landing Page / Waitlist CRO | UNASSIGNED | NO OWNER | ● |
| App Store Optimization (ASO) | UNASSIGNED | NO OWNER | ● |
| Paid Media Planning + Buying | UNASSIGNED | NO OWNER | ● |
| Press Kit + Media Assets | UNASSIGNED | NO OWNER | ● |
| Email Nurture Sequence | UNASSIGNED | NO OWNER | ● |
| Customer Support Capacity | UNASSIGNED | NO OWNER | ● |
| Legal / Compliance Review | UNASSIGNED | NO OWNER | ● |
| OOH Campaign (4 markets) | UNASSIGNED | NO OWNER | ● |
| FIFA Broadcast Integration | UNASSIGNED | DEPENDENCY | ● |
| CRM Data Tier | UNASSIGNED | DEPENDENCY | ● |
| Surgence Entity Decision | UNASSIGNED | DEPENDENCY | ● |

03  CRITICAL DEPENDENCIES (T-14 STATUS)

Eight dependencies must resolve before May 24. Each is a potential stop-the-launch event. Status as of May 10.

|  | Surgence Contract T-0 TODAY | Unsigned as of May 10. WhatsApp seeding alone requires 4 weeks of group admin relationship-building. Today is the mathematical last date to sign and still execute community seeding before June 11. |
| --- | --- | --- |

|  | Brand Identity T-0 TODAY | Does not exist. Blocks: landing page, press kit, app store assets, creator briefs, all 19 digital surfaces, Country-Edition card artwork, OOH creative. Cannot be done in parallel with Surgence contract — Surgence is likely the delivery vehicle. |
| --- | --- | --- |

|  | Landing Page / Waitlist T-12 DAYS | Does not exist. Must be designed, built, mobile-optimized, CRO-tested, and live before May 24. 12 days. No agency appointed. |
| --- | --- | --- |

|  | App Store Submission T-7 DAYS | Apple review: 24–72 hours typical, up to 7 days for new financial apps. Submission deadline: May 17. No confirmation submission has been filed. |
| --- | --- | --- |

|  | OOH Booking T-10 DAYS | Premium OOH inventory in São Paulo, Mexico City, Buenos Aires, Bogotá locks 6–8 weeks in advance. That window has passed. Remaining inventory is remnant. No agency appointed. Budget not allocated. |
| --- | --- | --- |

|  | Press Kit / Media Embargo T-10 DAYS | Press kit due May 20 per internal timeline. Does not exist. No embargo placed with Bloomberg, FT, The Athletic, or any LatAm football media. First media contact should have happened this week. |
| --- | --- | --- |

|  | FIFA Broadcast Deal UNCONFIRMED | Listed as a dependency in the plan. No confirmation. Without it, Win Bonus and MOTM Cashback mechanics cannot trigger in real-time — they become manual post-game activations which kills the product moment. |
| --- | --- | --- |

|  | CRM Data Tier UNCONFIRMED | Loyalty Dividend requires FCB's historical spend data mapped to fan identities. Data access, privacy compliance (LGPD, LFPDPPP), and API integration not confirmed. |
| --- | --- | --- |

04  BUDGET & FINANCIAL GAPS

Only one budget line is committed. Everything else is unallocated or missing.

| Line Item | Estimated Cost | Notes |  |
| --- | --- | --- | --- |
| Surgence Phase 1 Retainer | $60,000 | 3 months × $20K |  |
| OOH — 4 LatAm markets | $1,500,000–$3,000,000 | Estimated; not allocated |  |
| Paid Media (Meta/Google/TikTok) | TBD | Per plan — literally 'TBD' |  |
| Creator Program (180 creators) | $180,000–$540,000 | @$1K–$3K per creator |  |
| Press / PR Agency | Unknown | No agency appointed |  |
| App Development (if needed) | Unknown | Depends on product readiness |  |
| Customer Support Staffing | Unknown | No owner; 300K day-1 projection |  |
| Surgence Phase 2 (TGE) | $100,000 + 0.15% $FCB | 4 months × $25K + token |  |

Waitlist math check: Plan targets 750K waitlist → 250–320K downloads → 90–115K activated cards. Organic-only (owned FCB channels, no paid media) yields approximately 25,000 signups based on comparable neobank launches. The 750K target requires significant paid media investment that has not been modeled, budgeted, or assigned. CAC by market (Brazil vs. Mexico vs. Argentina vs. Colombia) is not in the document.

05  INTERNAL CONTRADICTIONS

Six places where the document contradicts itself. These are not editorial inconsistencies — each one is a decision that has been made twice with different outcomes.

| 1 | Brand Voice: Grievance vs. Celebration The Loyalty Dividend is introduced with 'the club has taken from fans their whole lives; now it gives back.' Andrew's correction explicitly bans grievance framing and requires celebration framing: 'Your culer life, rewarded.' Both framings appear in the same document. The brand line for the single highest-impact mechanic is unresolved. |
| --- | --- |

| 2 | Waitlist Math Doesn't Close Plan targets 90–115K activated cards. The document's own funnel math (engagement rate × conversion rate × activation rate applied to FCB's owned audience base) yields approximately 63K — a 30–45% shortfall. The gap is paid media, which is 'TBD'. |
| --- | --- |

| 3 | Surgence Scope: Confirmed vs. Pending The scope mapping table marks Surgence deliverables as 'confirmed.' The contract section states the agreement is 'pending signature.' These cannot both be true. Deliverables are not confirmed until the contract is signed. |
| --- | --- |

| 4 | Phase 1 Web2-Only vs. Surgence Web3 Entity Phase 1 is explicitly 100% Web2 — no token language, no CT seeding, no Web3 channels. The Surgence entity decision (which legal structure Surgence uses to receive payment) is listed as a critical dependency. If Surgence's entity structure is crypto-native, there is a Phase 1 compliance exposure. |
| --- | --- |

| 5 | Creator Program: 180 Creators vs. No Legal Framework The plan specifies 180 creators across 4 markets. Financial advertising requires FTC/ASA/CONAR disclosures in all 4 markets. No compliance framework, no creator brief template, no disclosure language exists in the document. The 180-creator program cannot launch without it. |
| --- | --- |

| 6 | Country-Edition Cards: 5K Units vs. Pre-Order May 24 Pre-order opens May 24. 5,000 units per country = 20,000 total. No manufacturing lead time, fulfillment partner, or shipping logistics are addressed. For physical cards, 20K units requires 8–12 weeks minimum from artwork approval to delivery. Artwork does not yet exist. |
| --- | --- |

06  UNVALIDATED ASSUMPTIONS

Eight assumptions embedded in the plan that have not been confirmed and carry material launch risk.

A1  FCB will grant data access for Loyalty Dividend

The Loyalty Dividend requires historical spend data mapped to fan identities. FCB's data licensing, LGPD compliance (Brazil), LFPDPPP compliance (Mexico), and API integration are all unconfirmed. If this data doesn't transfer cleanly, the single highest-shareability mechanic fails.

A2  800M global fans = high conversion pool

FCB has 800M fans globally. The plan's LatAm-first focus addresses approximately 15–20% of that base. The assumption that LatAm fans convert at the same rate as European fans is not modeled. LatAm has significantly higher unbanked rates AND higher neobank saturation (Nubank has 105M customers in Brazil alone).

A3  FIFA broadcast deal closes before June 11

MOTM Cashback and Win Bonus require real-time match data integration. Without the broadcast deal, these become manual post-game activations — which turns a product moment into a customer service event.

A4  30 Facebook group admins will cooperate

The plan assumes 30 Facebook group admins across LatAm and MENA will seed content organically. No relationship-building timeline, no compensation structure, and no admin vetting framework exists in the document.

A5  App will be approved in 4 target markets by June 11

Brazil, Mexico, Argentina, and Colombia each have separate App Store and Google Play review queues. Financial apps face enhanced scrutiny. No confirmation that regulatory licensing is in place in all 4 markets.

A6  750K waitlist is achievable without paid media

Nubank's first 100K customers required 18 months and a purple credit card mailed directly. Chime's 1M user milestone took 4 years. The plan's 750K waitlist target in 6 weeks is aspirational without a paid media model.

A7  Surgence WhatsApp seeding works in 4 weeks

Authentic WhatsApp group seeding — not spam, but narrative-led community organic integration — takes 6–8 weeks minimum to avoid detection and group removal. 4 weeks from contract signature to June 11 is below the safety threshold.

A8  World Cup window is uncontested attention

Nubank, Mercado Pago, and Revolut are all active in LatAm during the World Cup window. Nubank spent $40M+ on the 2022 World Cup campaign. The window is peak attention AND peak competition.

07  FIVE MOST DANGEROUS GAPS  —  RANKED BY SEVERITY

These are not strategic weaknesses. These are execution blockers that, if unresolved, stop the launch.

| 01 CRITICAL | Surgence Unsigned + Brand Identity Unlocked = Cascading Failure Every downstream deliverable — landing page, press kit, creator briefs, app store assets, OOH creative, card artwork — requires brand identity to exist first. Brand identity is delivered by Surgence. Surgence is unsigned. This is not one gap. It is 19 gaps behind one gate. Action required today: sign the contract or identify an alternative brand identity delivery path with a 72-hour turnaround. |
| --- | --- |

| 02 CRITICAL | No Landing Page, 12 Days to Announcement The waitlist page is the single most important conversion surface for May 24. It does not exist. It requires brand identity (blocked), copywriting, design, development, mobile optimization, CRO testing, and analytics integration. 12 days is achievable only if: (a) brand identity delivers in 48 hours, (b) a dedicated dev team starts May 12, (c) zero revision cycles. There is no named owner, no agency brief, and no confirmed budget. |
| --- | --- |

| 03 HIGH | Paid Media: No Budget, No Model, No Owner The plan's waitlist math requires paid media. Paid media is listed as 'TBD.' LatAm CAC for neobank acquisition: Brazil $8–15, Mexico $12–20, Argentina $6–10, Colombia $10–18 (estimated). To reach 750K waitlist signups: rough paid media requirement = $4–8M across the window. No agency has been briefed. No media plan exists. No creative assets exist for paid. Without a paid media model, the target numbers are fictional. |
| --- | --- |

| 04 HIGH | 180-Creator Program With No Legal Framework 180 creators across Brazil, Mexico, Argentina, and Colombia. Financial advertising is regulated in all 4 markets. Brazil: BACEN and CONAR disclosure requirements. Mexico: CNBV rules. Argentina: BCRA and Defensa del Consumidor. Colombia: SFC. No creator brief template, no disclosure language, no compliance review process, no legal sign-off workflow exists in the document. A single non-compliant creator post can trigger regulatory review and launch suspension. |
| --- | --- |

| 05 HIGH | No Crisis Response Plan for Day 1 The plan projects 300,000 Day 1 signups. That volume will surface: app crashes, onboarding failures, card delays, and customer service queues. Customer support has no named owner. No language coverage plan (PT-BR, ES-MX, ES-AR, ES-CO). No crisis communication playbook for: app outage, security incident, regulatory inquiry, competitor attack, negative media coverage. The first PR crisis at a financial product launch is not a risk — it is a certainty. The variable is response time. There is no response framework. |
| --- | --- |

08  14-DAY CRITICAL PATH  —  MAY 10 TO MAY 24

Actions ordered by dependency. Nothing in Week 2 is possible without Week 1 completion. Items marked RED must complete today (May 10) or the announcement date is at risk.

| Date | Action | Owner |  |
| --- | --- | --- | --- |
| May 10 TODAY | Sign Surgence contract | Walter / FCB Legal |  |
| May 10 TODAY | Brief Surgence on brand identity 72h sprint | Walter + Surgence |  |
| May 10 TODAY | Appoint paid media agency or confirm in-house | Walter / FCB Marketing |  |
| May 10 TODAY | Identify legal counsel for all 4 markets (financial advertising) | FCB Legal |  |
| May 11–12 | Begin Facebook group admin outreach (30 admins) | Surgence |  |
| May 11–12 | Begin WhatsApp community seeding preparation | Surgence |  |
| May 12 | Brand identity v1 delivery from Surgence | Surgence → Walter review |  |
| May 12 | Submit app to App Store and Google Play | Product team |  |
| May 13 | Begin landing page design + build | Web team / Agency |  |
| May 13 | Begin press kit assembly | PR team / Surgence |  |
| May 14 | Paid media plan + budget submitted for approval | Media agency |  |
| May 14 | Creator brief template + legal disclosure language drafted | Legal + Surgence |  |
| May 15 | Creator outreach begins (Tier 1: 20 creators, Wave 1) | Surgence |  |
| May 16 | Country-Edition card artwork to printer | Surgence + Fulfillment partner |  |
| May 17 | Landing page QA + mobile optimization complete | Web team |  |
| May 17 | App Store submission deadline (7-day review buffer) | Product team |  |
| May 18 | Press embargo placed with Bloomberg, FT, The Athletic, ESPN Brasil | PR team |  |
| May 19 | Loyalty Dividend mechanic tested with real CRM data sample | Product + FCB Data |  |
| May 20 | Press kit finalized and distributed to embargoing journalists | PR team |  |
| May 20 | Paid media campaigns loaded, reviewed, and approved | Media agency |  |
| May 21 | OOH remnant inventory booked in São Paulo + Mexico City (minimum) | Media agency |  |
| May 22 | Full launch readiness review with FCB + Surgence | Walter |  |
| May 23 | Go / No-Go decision for May 24 announcement | FCB leadership |  |
| May 24 | ANNOUNCEMENT — Final La Liga match day | All |  |

09  WHAT THE PLAN GETS RIGHT

This memo has focused on gaps. For completeness: the plan's strategic layer is strong. These elements should not be changed.

✓  World Cup timing

Anchoring to June 11–July 19 is the correct commercial decision. This is the single best window for a football-branded financial product in LatAm in a generation.

✓  100% Web2 for Phase 1

The decision to exclude all token/crypto language from Phase 1 is correct. It widens the addressable audience by an order of magnitude and removes regulatory exposure during the most critical window.

✓  Loyalty Dividend mechanic

The concept — a personalised card showing lifetime FCB spend vs. cashback earned — is genuinely differentiated. The ETHGas report (590K shares) and ORBT DeFi Score (70K shares) precedents validate the shareability thesis. This is the right hero mechanic.

✓  Surgence community architecture

Reddit sleeper agents, Facebook group admins, WhatsApp seeding — the playbook is sophisticated and appropriate for the fan-first audience. No other neobank is doing this.

✓  Daily Player Drop cadence

One player per day starting May 25 is the right format for Instagram Stories. It creates a reason to return daily and gives each market a moment without diluting the whole.

✓  Phase 1 / Phase 2 sequencing

Hard-separating the neobank launch from the TGE is strategically correct. Building 300K+ activated users before the token drop creates a real product beneath the token, not the reverse.

BOTTOM LINE

The plan is not the problem. The gap between the plan and the current state of readiness is the problem. As of May 10, the Surgence contract being unsigned is the only blocker that matters. Everything else is downstream of that signature. The question for today's leadership meeting is not strategic — it is operational: who signs, and when.

Prepared by Surgence Labs for FC Barcelona Banc leadership review.  Document status: INTERNAL DRAFT.  Not for external distribution.