# Index

PRIORITY ORDER

# Phase 1 marketing items in execution order

Barça Banc · May 10 – Jul 19, 2026  ·  Surgence rows tinted in garnet

| # | Topic | Description | Responsible |
| --- | --- | --- | --- |
| FOUNDATIONS · THIS WEEK |  |  |  |
| 0A | Surgence contract signing | MSA + Schedule A must be countersigned before any work begins. Gates items 1–4, 8 simultaneously. | Walter + FCB Legal |
| 0B | FCB board / WS2 approval | FCB board must formally authorize public announcement. No approval = May 24 announcement cannot proceed. | FCB Leadership |
| 0C | $BAR delistment | FCB Action Item #4 — $BAR token must be delisted from active exchanges before May 24 announcement. | FCB Legal / Laporta |
| 0D | FCB POC designation | Named point-of-contact for content approval per CCLA. 5 working-day SLA. No POC = content pipeline blocked. | FCB Marketing lead |
| 1 | Brand identity & tone | Locks visuals, voice, co-branding rules. Everything else waits on this. | Surgence |
| 2 | Strategy & GTM document | Master plan, sequencing, phase gates, messaging framework. | Surgence |
| 3 | Messaging hierarchy | PT/ES variants, approved language, prohibited terms by segment. | Surgence + localization |
| 4 | Web2 organic seeding | Reddit, Facebook groups, WhatsApp, Korea. 4-week lead time — cannot defer. | Surgence |
| 5 | Legal counsel per market | BACEN, CNBV, BCRA, SFC. Highest launch-blocker risk. | Per-market legal counsel |
| BUILD · MAY 14–22 |  |  |  |
| 6 | Landing page | banc.fcbarcelona.com, mobile-first, A/B tested. Live before May 24. | UX/UI agency + LFG |
| 7 | App UX/UI design | Onboarding, KYC, dashboard, WC mechanics hub, push notifications. | Leo + Lav's team (Agan) |
| 8 | Loyalty Dividend | Personalised viral share-card. CRM tier confirmed. Launch hook. | Surgence + LFG + FCB |
| 9 | Country-Edition Card | 5K per country, national colors. Design + pre-order flow. | FCB / LFG / design |
| 10A | App Store submission (HARD DEADLINE) | Apple review = 7 days. Must submit by May 17 to go live June 11. Distinct from ASO optimisation (item 10). Miss this = card cannot launch. | FCB Product / LFG |
| 10 | ASO | App Store + Google Play indexing in PT/ES. 2–4 week delay. | ASO specialist |
| 11 | Press kit & embargo | FT/Bloomberg (48h), Athletic (24h), Marca regional. Assets by May 20. | Carlos / PR agency |
| 12 | Localization workflow | PT-BR, MX-ES, AR-ES, CO-ES. Translation review and legal disclaimer adaptation. | Localization specialist |
| ACTIVATE · MAY 24 ANNOUNCEMENT |  |  |  |
| 13 | FCB owned channels | IG Stories priority, X, TikTok, FB, LinkedIn, WhatsApp 50M broadcast. | FCB social + Leo |
| 14 | Hero video | CCLA commercial shoot Jul 1–Dec 31 only; amendment unsigned. Pre-announce only on May 24 — no player footage until shoot window opens. | Creative agency |
| 15 | Daily Player Drop | One player per day from May 25, 15–30s clip on IG Stories. | FCB social + Leo |
| 16 | Tier-1 press placements | Coordinated wave when embargoes lift. Financial + sports + regional. | Carlos / PR agency |
| 17 | Email welcome + nurture | Welcome + 17-day nurture + activation triggers. 750K warm contacts. | CRM/email agency |
| 18 | Paid social | Meta, TikTok, YouTube, Google. CAC targets: BR $8 / MX $6 / AR $4 / CO $5. Three-tier influencer model (30 seed / 150 ambassador / 500 micro). | Performance agency |
| 19 | Creator program | 30 seed + 150 ambassador. Compliance briefs per market (FTC/CONAR/PROFECO). | Influencer agency |
| AMPLIFY · JUNE 11 CARD LIVE |  |  |  |
| 20 | OOH campaign | ⚠ Premium 6–8 week lead window has passed. Remnant OOH only; switch budget to digital OOH / DOOH screens in stadium districts. | OOH/media agency |
| 21 | FIFA broadcast partnership | Mexico opener at Estadio Azteca — half-time or sponsor slot. Commercial broadcast deal, NOT a Web3 or token touchpoint. | Maurits / FCB Commercial |
| 22 | Six WC mechanics | Country Boost, Win Bonus, MOTM, Card Variants, Bracket, Final Ticket Draw. | LFG dev |
| 23 | WC host-city IRL | VIP hangouts, signed jerseys, on-site Loyalty Dividend reveals. | Events agency |
| 24 | Customer support | PT/ES agents, KYC handling, SLA. 10–20× normal volume on Day 1. | Ops lead (TBD) |
| 25 | Analytics & attribution | UTM strategy, funnel dashboard, cohort analysis, weekly reporting. | Analytics agency |
| 26 | Crisis & FUD playbook | 5 named scenarios with response owners and holding statements. | Surgence + FCB comms |
| 22A | CRM data tier confirmation | FCB must confirm which data tier is available: Tier 1 (real spend history), Tier 2 (estimated from supporter tier), or Tier 3 (generic). Gates Loyalty Dividend impact. | FCB Data / Walter |
| SUSTAIN · POST-JULY 19 |  |  |  |
| 27 | Post-WC retention engine | Replaces 6 mechanics going dark. Aug–Dec calendar + churn triggers. | Surgence scope+ or new brief |
| 28 | Phase 1 → 2 transition | Fiat-to-token vocabulary bridge. Single biggest brand challenge. | CMO (Walter) |
| 29 | Pre-TGE handoff | User segmentation, highest-LTV ID, TGE narrative framework. | Surgence |
| 29A | BCB Resolution 561 (Brazil architecture) | BACEN bans crypto/stablecoin in cross-border eFX settlement from Oct 1, 2026. Q3 architecture decision required before Phase 2 / TGE Brazil activation. | FCB Legal / LFG |
| ARCHITECTURE · CAMPAIGN DESIGN GAPS | ARCHITECTURE · CAMPAIGN DESIGN GAPS | ARCHITECTURE · CAMPAIGN DESIGN GAPS | ARCHITECTURE · CAMPAIGN DESIGN GAPS |
| 30 | Funnel ownership & journey map | Named owner across all funnel stages: Awareness → Waitlist → Download → Activation → First Spend → Referral. Drop-off intervention trigger at each step. Closes gap between 750K waitlist target and 90–115K card target. → See RACI tab for stage ownership assignments. | Walter (CMO) → RACI tab |
| 31 | Day 1 success criteria | Three numbers signed off by Walter, Andrew, Maurits before May 24: (1) waitlist sign-ups in first 24h, (2) tier-1 press placements live, (3) Loyalty Dividend share-card downloads. No definition = no aligned team. → See Phase 1 Mkt v2, Section 05 Targets. | Walter + Andrew + Maurits |
| 32 | Total Phase 1 budget & CAC model | Consolidated spend: Surgence $60K + agencies ~$63K + paid media $558K–$747K + OOH + events. CAC by market: BR $8 / MX $6 / AR $4 / CO $5. Payback 12 months base. → See Budget tab, sections A–D for full model. | Walter (CMO) → Budget tab |
| 33 | Live participant counter | Public counter on banc.fcbarcelona.com landing page. Compounding social proof: each signup visible → next signup more likely. Cited in 4 of 6 Surgence case studies (ORBT DeFi Score, ETHGas, etc.). Costs ~2 hours to implement. | Web/Design Agency + Surgence |
| 34 | Competitive response contingency | Scenario plan for Nubank / Mercado Pago counter-promotion during WC window. Rapid-response messaging pre-approved. Real-time social monitoring setup. → See Phase 1 Mkt v2, Section 12 Crisis Playbook. | Surgence + FCB Comms → Phase 1 Mkt v2 |

Surgence owns 8 of 29 items. Critical path: items 1–4 must move this week or May 24 slips.

Barça Banc Phase 1 Priority Order  ·  Confidential  ·  May 2026

THE HONEST ASSESSMENT

The plan covers the blocking and tackling of a fintech launch competently. It misses three things that separate good launch plans from successful ones: a funnel spine (so drop-offs have owners), a success definition (so the team knows what it's chasing), and a budget envelope (so spend is governed, not improvised).

Against competitors: it captures Nubank's growth mechanics and Chime's cultural-tentpole logic well. It is weaker on Nubank's per-country positioning depth and Chime's original content production model.

The biggest single weakness: the plan reads as a list of tasks, not a campaign architecture. Surgence's own case studies prove the architecture works — multi-stage commitment funnel, identity artifact, referral-as-distribution, content-as-acquisition. Renaming the phases as ORBT did (Stage 1 Trailer / Stage 2 Module / Stage 3 Score / Stage 4 Yield) compresses the plan from 34 items to 4 stages with sub-items, and forces every workstream to ladder to a funnel position.

| What the plan gets right | What is missing |
| --- | --- |
| ✓ World Cup window correctly identified as peak conversion moment | ✗ No funnel owner map — drop-offs between 750K waitlist and 115K card target are unowned |
| ✓ Loyalty Dividend mechanic is genuinely differentiated (590K shares precedent) | ✗ No Day 1 success definition signed off before May 24 |
| ✓ Web2-only Phase 1 framing is the correct commercial decision | ✗ No consolidated budget / CAC model per market (fixed in Budget tab) |
| ✓ Surgence engagement mechanics are tested (Reddit, WhatsApp, Facebook groups) | ✗ No live counter / social proof mechanic on landing page |
| ✓ Competitor intelligence: Nubank growth loops, Chime cultural tentpoles | ✗ No competitive response plan if Nubank counter-promotes during WC |
| ✓ 6 WC mechanics cover the full fan journey (match → card → share) | ✗ Hero video gated by CCLA amendment (shoot window Jul 1) — pre-announce risk |
| ✓ Sponsor plays (Spotify, Streamer Camp Nou) are Phase 1-compatible | ✗ OOH premium window has passed — digital OOH fallback not yet briefed |

4-STAGE CAMPAIGN ARCHITECTURE — HOW THE 34 ITEMS CONNECT

Every item in the priority list ladders to one of four funnel stages. Use this view to assign owners by stage, not by task type. Cross-references point to the relevant tab for detail.

| Item(s) | Workstream | Owner | → Detail |
| --- | --- | --- | --- |
| STAGE 1 — IGNITE ¦ Awareness → Waitlist |  |  |  |
| 14 days to May 24. Goal: 750K waitlist before card live June 11. Identity artifact: Loyalty Dividend share-card (zero-cost viral unit). Distribution: FCB owned channels (147M IG) + organic seeding + earned media. |  |  |  |
| 0A–0D + 1–5 | Foundations & contracts | Walter / FCB Legal | RACI Phase 0 |
| 6 | Landing page with live counter (item 33) | Web Agency + Surgence | RACI Phase 1A |
| 8 | Loyalty Dividend viral share-card | Surgence + FCB Data | Budget tab — organic % |
| 11 | Press kit & tier-1 embargo (FT, Bloomberg) | Carlos / PR | PR competitors tab |
| 13 + 15 | FCB owned channel posts + Daily Player Drop | FCB Social + Leo | CCLA Schedule 1 |
| 16 | Tier-1 press wave (embargo lift May 24) | PR Team | Phase 1 Mkt v2 §03 |
| 4 | Reddit/WhatsApp/Facebook seeding | Surgence | Surgence Labs tab |
| 30 | Funnel ownership map — this stage | Walter (CMO) | RACI tab |
| ▸ Funnel target: 750K waitlist by June 10. Conversion benchmark: ETHGas 590K shares in 72h. Loyalty Dividend is the Stage 1 identity artifact. |  |  |  |
| STAGE 2 — COMMIT ¦ Download → Activation → First Spend |  |  |  |
| June 11–19. Card goes live. Goal: 90–115K activated cards. Friction reduction: ASO (item 10), 17-day email nurture (item 17), onboarding UX (item 7). World Cup mechanics replace paid incentives. |  |  |  |
| 7 + 10 + 10A | App UX + ASO + App Store submission (May 17 hard) | Leo + LFG | RACI Phase 1A |
| 12 | Localization (PT-BR, MX/AR/CO-ES) | Localization specialist | Budget tab §A |
| 17 | 17-day email nurture sequence (waitlist → card) | CRM agency | Phase 1 Mkt v2 §07 |
| 18 | Paid social — install campaigns (CAC: BR $8 / MX $6) | Performance agency | Budget tab §B–C |
| 19 | Creator program — 30 seed / 150 ambassador | Influencer agency | Phase 1 Mkt v2 §05 |
| 22 | Six WC mechanics fire (Boost Days, Win Bonus, MOTM) | LFG dev | Phase 1 Mkt v1 §3 |
| 24 | Customer support PT/ES ready (10–20× baseline volume) | Ops lead | RACI Phase 1C |
| 31 | Day 1 KPIs locked before May 24 | Walter + Andrew + Maurits | Index tab — item 31 |
| 33 | Live counter on landing page — compounding social proof | Web Agency | banc.fcbarcelona.com |
| ▸ Funnel target: 90–115K cards activated by July 19. CAC blended $6.80. Payback 12 months base case. → Budget tab §B. |  |  |  |
| STAGE 3 — SCORE ¦ First Spend → Referral → Viral Loop |  |  |  |
| June 11 – July 19. World Cup window. Goal: $1B Y1 transaction volume. Referral = distribution. Identity artifact: Country-Edition Card (5K per market). Viral mechanic: Win Bonus cashback, MOTM cashback, Bracket Prediction Game. |  |  |  |
| 9 | Country-Edition Card (5K × 4 markets, pre-order May 24) | FCB Design / Leo | Phase 1 Mkt v1 §3 |
| 20 | OOH / DOOH (remnant — digital fallback briefed) | Media agency | Budget tab §C |
| 21 | FIFA broadcast slot (Mexico opener, Estadio Azteca) | Maurits / FCB Commercial | Phase 1 Mkt v2 §04 |
| 22 | Country Boost Days / Win Bonus / MOTM Cashback / Bracket / Final Draw | LFG dev | Phase 1 Mkt v1 §3 |
| 23 | WC host-city IRL events (VIP, signed jerseys) | Events agency | Budget tab §E |
| 25 | Attribution & funnel dashboard (real-time daily) | Analytics agency | RACI ongoing |
| 34 | Competitive response plan — Nubank/Mercado Pago counter | Surgence + FCB Comms | Phase 1 Mkt v2 §12 |
| ▸ Funnel target: $95M+ transaction volume during WC window (40-day sprint). Referral rate target: 1 activated user → 0.4 new installs. → Surgence Labs tab for referral mechanic architecture. |  |  |  |
| STAGE 4 — HOLD ¦ Post-WC Retention → Phase 2 Bridge |  |  |  |
| July 20 – Aug 31. Six WC mechanics go dark. Goal: retain activated cohort, bridge to TGE vocabulary. Loyalty program replaces WC mechanics. TGE hard deadline Aug 31 (TLA v5). Walter's operational target: Aug 19. |  |  |  |
| 26 | Crisis & FUD playbook — 5 scenarios active | Surgence + FCB Comms | Phase 1 Mkt v2 §12 |
| 27 | Post-WC retention campaign (Aug loyalty program) | Surgence / new brief | Phase 1 Mkt v2 §10 |
| 28 | Fiat → token vocabulary bridge (Phase 1→2 comms) | Walter (CMO) | Phase 1 Mkt v2 §10 |
| 29 | User segmentation — high-LTV cohort for TGE pre-sale | Surgence + FCB Data | Surgence Labs tab |
| 29A | BCB Resolution 561 — Brazil architecture decision (Oct 1 deadline) | FCB Legal / LFG | Budget tab §E |
| 32 | Final budget reconciliation + CAC audit | Walter (CMO) | Budget tab §A–D |
| ▸ Retention target: ≥60% of activated cards still active 90 days post-WC. TGE handoff: top-LTV segment identified and segmented in CRM. → Phase 1 Mkt v2 §10 for full retention plan. |  |  |  |

Tab cross-reference: Index (this tab) → Phase 1 Mkt v1 (original plan) → Phase 1 Mkt v2 (updated 13-section plan + FCB Deliverables) → Competitors: Nubank / Chime / Tuyo → PR competitors → Budget → RACI → Surgence Labs

# Phase 1 Mkt v1

# Phase 1 Marketing Plan v1

This is the consolidated Phase 1 marketing plan for the Barça Banc launch, designed to be sharable directly with Surgence as the comprehensive view of the campaign. v1 was an internal synthesis with two agencies in scope; v2 narrows the agency stack to Surgence only and lays out where Surgence is already involved, where Surgence proposes to lead, and the surfaces still open for Surgence to take on. The intent is to enable a single, coordinated owner across the full campaign rather than splitting workstreams.

The plan covers May 24, 2026 (announcement) through end of August 2026 (TGE handoff). Phase 2 (token-native, international markets) sits in a separate document; cross-referenced where relevant.

## Executive Summary

Phase 1 launches Barça Banc, a fiat-only Visa credit card with FCB Rewards Points, in 4 LatAm markets (Brazil, Mexico, Argentina, Colombia) plus Chile deferred to Phase 1c. The launch is anchored to the 2026 FIFA World Cup, which doubles as the M1 catalyst. Marketing posture is fiat-only and consumer-facing, with no crypto, web3, stablecoin, or token language anywhere in user-visible material. Surgence is engaged as the always-on Web2 base layer for Phase 1. Walter leads with Maurits and Leo as support. FCB owned channels (especially Instagram) carry the announcement; CCLA Schedule 1 specifies the cadence and is in active redline.

Y1 base case (post-WC end): 250K to 320K downloads, 90K to 115K activated cards, anchored to ~$1.0B Y1 transaction volume on the LatAm cohort alone.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Brand Voice & Messaging Architecture for Barca Banc

Barca Banc has no defined brand identity separate from FCB. "Revolut-competitive with FCB brand trust" describes positioning, not brand personality. Missing: (1) Tone of voice distinct from @FCBarcelona -- is Barca Banc premium, accessible, community-first? (2) Value proposition in one sentence. (3) Visual identity rules for co-branded vs. standalone Barca Banc content. (4) Messaging hierarchy by segment and channel. Without this, content from Surgence, FCB social team, creators, and spokespeople will drift in tone across 56 days of campaign.

────────────────────────────────────────────────────────────────────────

## 1. Phase 1 Constraints

Per projects/fcb/concepts/phase-1-bp-scope-argument and the BP contractual posture:

- Fiat-only consumer UX. No wallet, no token balance, no on-chain user surface. Users top up via local rails (PIX, SPEI, CBU/CVU, Bre-B), spend in local currency on a Visa card, earn FCB Rewards Points, redeem for experiences and merchandise.

- Marketing must not mention crypto, web3, stablecoin, USDC, $FCB, or wallet of any kind in any user-visible surface. Background settlement (Rain USDC orchestration through Bridge to Visa) is invisible plumbing, analogous to how a conventional bank uses SWIFT internally.

- LatAm only in Phase 1. APAC (Indonesia, Singapore, Hong Kong), MENA (UAE), Africa (Nigeria, Kenya), EU, and US all move to Phase 2(target around June 2026) and the crypto-native UX can launch.

- Brand: Barça Banc (with diacritic), domain banc.fcbarcelona.com. Per projects/fcb/concepts/walter-cmo-evaluation.

## 2. Phase Plan and Markets

| Sub-wave | Window | Markets | Anchor moment |
| --- | --- | --- | --- |
| Pre-launch | May 24 to Jun 10 | Global waitlist (LatAm prioritized) | May 24 announcement on the final La Liga match day |
| Phase 1a | Jun 11-13 | Mexico, Brazil, Argentina | Mexico opens the WC at Estadio Azteca Jun 11 (in-broadcast announcement); Brazil opener Jun 12-13; Argentina opener Jun 12-13 |
| Phase 1b | Jun 18-22 | Colombia | Group MD2 / Spain MD2 window |
| Phase 1c (deferred) | Knockout window, opportunistic | Chile (gated on Bridge rail confirmation) | Most-watched knockout in CL |

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Phase Gate Conditions (Go/No-Go Criteria Between Phases)

The plan sequences Phase 1a (Jun 11) -> Phase 1b (Jun 18) -> Phase 1c (knockout) with no defined performance gates. If Phase 1a delivers 40K downloads instead of 100K by Day 7, does Colombia still launch June 18? If a critical KYC bug hits Brazil at launch, does Mexico pause? Missing: minimum downloads by D+7, minimum activation rate threshold, maximum critical bug count, and a named decision owner for go/no-go calls between each sub-wave.

────────────────────────────────────────────────────────────────────────

## 3. World Cup Campaign (the M1 catalyst)

Four phases, anchored to the WC calendar (June 11 to July 19, 2026). Surgence's GTM document is the master operational reference; this section is the campaign-level summary.

### Phase 0: Announcement and Waitlist (May 24 to Jun 14)

Goal: 750K LatAm waitlist signups before card go-live. May 24 to June 14 is FCB's off-season window, naturally lower volume on socials but higher per-post engagement (1M+ likes possible). This is friendly to a launch announcement; tie the framing to the "fresh season" narrative FCB already runs in late June. The May 24 announcement coincides with the final La Liga match day: Surgence has flagged this as a high-emotion moment that the announcement benefits from directly.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Landing Page & Waitlist CRO Strategy

The 750K waitlist target depends entirely on banc.fcbarcelona.com -- which has zero detail in this plan. Missing: (1) Headline and value prop copy. (2) Conversion rate target: 1% vs. 3% from the same traffic = 3x difference in signups from identical spend. (3) Mobile-first optimization -- Brazil and Mexico are 80%+ mobile traffic. (4) A/B test plan for headline, CTA button, and form fields. (5) Page load speed target -- each 1-second delay on mobile reduces conversion by ~7%. This page is the single highest-leverage conversion surface in the entire campaign.

────────────────────────────────────────────────────────────────────────

- May 24 announcement via Barça owned channels (167M+ social reach across IG, TikTok, X, YT). Website opens for waitlist with country selection. Reveal: card design, FCB Rewards tier preview, points earning mechanics, redemption catalog. Materials are pure fiat-product framing.

- Loyalty Dividend pre-registration opens before May 24 (Surgence-built; see Section 4). Personalized card showing how much the FCB card would have paid each fan back across their support history. Queue mechanic active.

- Daily Player Drop beginning May 25. One Barça player per day records a 15-30s clip. Format priority: Instagram Stories first (matches FCB's ~10-stories-per-day baseline; highest-engagement platform per projects/fcb/concepts/fcb-social-baseline), with TikTok player-interview format as the higher-effort weekly anchor (Olivia Rodrigo / Lamine clip got 1M+ likes; proven template). X is secondary.

- Country Waitlist Tiers with referral mechanics. Brazil at 100K, Mexico at 75K, Argentina at 50K, Colombia at 50K. Top tier gets card priority and Final-ticket draw entries.

- Country-Edition Card Pre-Order. 5,000 limited cards per country, designed in national colors, only available to verified residents.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Localization Strategy (Portuguese / Spanish Variants)

Four markets, two languages, multiple regional variants -- treated as one block throughout. Missing: (1) Portuguese localization workflow for all Brazilian content: player drops, WhatsApp messages, emails, push notifications, and the Loyalty Dividend share card. (2) Mexican Spanish vs. Rioplatense Spanish adaptation -- tonally different audiences. (3) Translation review and approval process -- who signs off on Brazilian Portuguese copy? (4) Legal disclaimer localization per market: BACEN (Brazil), CNBV (Mexico), BCRA (Argentina), SFC (Colombia). One English pre-written WhatsApp caption fails all four markets.

────────────────────────────────────────────────────────────────────────

### Phase 1: Card Live and Group Stage (Jun 11 to Jun 27)

Three LatAm anchor markets all go live at their opening matches. Bracket Prediction Game opens. Country Group-Stage Goal Bonuses fire. Match-Day Player Drops on every Barça-affiliated player's match day. Country Boost Days go live for activated users (3 to 5 times FCB Rewards Points during your country's match window).

### Phase 2: Knockouts (Jun 28 to Jul 19)

Phase 1b Colombia activates. All six matchday mechanics live across the LatAm footprint. Final Ticket VIP Draw runs throughout, livestreamed at ~Jul 17. Winners attend the Final. Chile activates if Phase 1c lights up.

### Phase 3: Post-Final Hand-off (Jul 19+)

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Retention Plan After World Cup Ends (August Onward)

The World Cup ends July 19. All six engagement mechanics go dark simultaneously. The plan has no retention layer underneath them. Missing: (1) Ongoing rewards calendar not dependent on WC results. (2) Monthly engagement mechanic for August-December 2026. (3) Churn trigger identification and response sequence -- what happens when a cardholder has not transacted in 30 days? (4) Post-WC loyalty tier progression. (5) Bad Bunny Artist Card Drop has one line in the plan -- it needs its own campaign brief. A user base acquired at peak WC emotion will churn rapidly without a structured post-WC plan.

────────────────────────────────────────────────────────────────────────

Champion Country Card variant ships in 7 days to the winner's market. Player-of-the-Tournament dividend if a Barça player wins Golden Ball or Boot. Hand-off into the projects/fcb/concepts/sponsor-collab-playbook starting with the Bad Bunny Artist Card Drop pre-TGE. Surgence's Phase 1-to-Phase 2 hand-off infrastructure (user segmentation, highest-LTV identification, TGE narrative framework) lands in this window.

### The Six Mechanics

- Country Boost Days (3 to 5 times FCB Rewards Points during your country's matches)

- Win Bonus (+5% retroactive 24h on country wins)

- Player-of-the-Match Cashback (+10% if your selected Barça player is MOTM)

- Country-Edition Card Variants (5K per country; pre-order opens May 24)

- Bracket Prediction Game (in-app, free entry, drives daily DAU through 39 days)

- Final Ticket VIP Draw (50 seats; entries = card spend × wins + bracket + waitlist tier)

All six mechanics are framed in pure FCB Rewards Points language; no crypto. Compounding cascade (Win MD1 → Win MD2 → qualify groups → reach QF → reach SF → win WC) escalates rewards as country results come in.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Full Funnel Customer Journey Map

The plan is 95% acquisition. No documented journey from awareness to spending cardholder. Industry fintech benchmarks: waitlist-to-download 20%, download-to-KYC-complete 50%, KYC-to-card-activated 60%, activated-to-first-spend-in-30-days 70%. Applied to 750K waitlist: approximately 63K spending cards -- not 90-115K. The funnel math does not close. Missing: (1) End-to-end journey map with drop-off rate assumptions at each step. (2) Named owner for each funnel stage. (3) Intervention trigger at each drop-off point (push notification, email, in-app prompt). Without this map, no one owns the steps between a waitlist signup and a spending card.

────────────────────────────────────────────────────────────────────────

## 4. The Loyalty Dividend

The single highest-leverage piece of Phase 1 viral mechanic, owned by Surgence. Full detail at projects/fcb/concepts/loyalty-dividend.

The number that makes the campaign: per-fan personalized card stating "you have spent EUR X supporting FC Barcelona over Y years; if you had been using the FCB card, you would have earned EUR Z back." Brand line: "FC Barcelona is finally paying its fans back."

Format: landscape card showing years as a fan, estimated lifetime FCB spend, Loyalty Dividend figure in large type, supporter tier badge, single brand line at the bottom. One-tap share to X and WhatsApp with a pre-written caption that embeds the personal number.

CRM data execution tiers:

| Tier | Data Available | Dividend Figure | Strength |
| --- | --- | --- | --- |
| Tier 1 | Full CRM transaction history per account | Real figure from actual spend history | Maximum personalization and impact |
| Tier 2 | Account age + supporter tier only | Estimated from average spend per tier; short disclaimer | Still personalized; slightly less precise |
| Tier 3 | Email only, no CRM linkage | Self-reported fan quiz; converts mechanic to quiz format | Usable; does not delay May 24 window |

Surgence confirms CRM access scope within the first 30 days of engagement and ships at the appropriate tier. If full Tier 1 access is not available before May 24, the mechanic launches on Tier 3 and upgrades on confirmation. The launch date does not move for data availability.

Token signal: zero in Phase 1. No forward reference to the token in the card, the email, the landing page, or any Phase 1 collateral. Phase 2 owns all token-related communication.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Email Marketing & Nurture Sequence

750K people give Barca Banc their email at waitlist signup. The plan has no email strategy. Missing: (1) Welcome email sent immediately after signup -- what does it say? (2) Nurture sequence for May 24-June 10 (17 days between signup and card go-live). (3) Activation sequence post-download: Day 1, Day 3, Day 7 nudges for users who downloaded but have not completed KYC. (4) Match-day emails triggered by WC results. (5) Referral trigger emails. (6) Win-back sequence for users who signed up but never downloaded. This is 750K warm contacts left completely unaddressed after the moment of signup.

────────────────────────────────────────────────────────────────────────

## 5. Marketing Targets

| Metric | Y1 Conservative | Y1 Base | Y1 Aggressive |
| --- | --- | --- | --- |
| M1 downloads | 200K | 300K | 450K |
| Y1 active cards (EOY 2026) | ~270K | ~406K | ~570K |
| Y1 tx volume | ~$0.6B | ~$1.0B | ~$1.5B |
| Pre-launch waitlist | 500K | 750K | 1M+ |

By end of WC (~July 19): 250K to 320K cumulative downloads, 90K to 115K activated cards (Base case).

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Analytics & Attribution Framework

The plan has targets but no measurement infrastructure. Missing: (1) UTM strategy -- which channel (Reddit, WhatsApp, Instagram, Facebook, paid) drives each waitlist signup? (2) Attribution model (last-touch vs. multi-touch). (3) Funnel dashboard -- where do users drop off between waitlist and activated card? (4) Cohort analysis -- do June 11 activations spend more than June 28 activations? (5) Match-day mechanic performance tracking -- which of the six mechanics drives the most incremental spend? (6) Weekly reporting cadence, template, and named owner. Without attribution, the campaign cannot be optimized mid-flight and the post-WC debrief will be anecdote-based.

────────────────────────────────────────────────────────────────────────

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Paid Media Budget & CAC Model by Market

Paid media budget is "TBD, confirmed jointly with Andrew." For a 750K waitlist target in 35 days, this is the largest undefined cost line in the plan. Missing: (1) CAC target per waitlist signup and per activated card by market. (2) Budget allocation across Brazil, Mexico, Argentina, Colombia. (3) Channel mix by market -- Meta vs. TikTok vs. YouTube vs. Google (TikTok penetration differs significantly between Brazil and Argentina). (4) ROAS or payback period target. (5) Spend scaling trigger -- at what conversion rate do you increase budget vs. pause? Without a CAC model, spend will be improvised in real time during the most critical window.

────────────────────────────────────────────────────────────────────────

## 6. Surgence Engagement

### Phase 1 Surgence-owned workstreams

#### A. Web2 Infiltration (100%)

The core engine. Phase 1 is 100% Web2; no token signal of any kind across any channel.

- Reddit sleeper agents in r/Barca (high IQ) and r/FCBarcelona (volume). Accounts pre-positioned weeks before May 24 to avoid appearing astroturfed.

- Facebook group admin activation across 30 named regional supporter groups. Admins post in their own voice; Surgence provides talking points and timing. Not branded.

- WhatsApp network seeding: SEA, Middle East, Africa, LATAM. Lead time is four weeks minimum, so seeding starts immediately (not deferrable past May 24 if the announcement is to land warm).

- Football forums and podcast outreach, planted threads. Non-crypto sports media. The pitch is a Revolut-competitive narrative with FCB brand trust, not a Web3 story.

- Korea Web2-first activation via Surgence Korea KOL network plus Web2 partner agency. Local partner confirmed within 30 days of kick-off. Korea has an outsized FCB following relative to market size and high ARPU; Surgence specifically calls it out as a high-leverage market.

- Optional collaborative infiltration with Gun's football-focused team where relevant.

#### B. Viral Product Mechanic: The Loyalty Dividend

Already covered in Section 4. Owned end-to-end by Surgence: pre-registration product, queue mechanic, three CRM-tier execution, share infrastructure. Same mechanic architecture as the ORBT DeFi Score (70K shares) and ETH Gas Report (590K users), adapted for football fans.

#### C. Community Advisory

- Communication guidelines and moderation frameworks for FCB's internal team.

- Telegram channel build and management for new @FCBarcelona Web3 Telegram channel; sits dormant until Phase 2 activation.

- Group-chat alignment with FCB's existing community managers.

- FUD mitigation briefings and real-time response guidance.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Crisis & FUD Response Playbook

"FUD mitigation briefings" are mentioned but no actual playbook exists. Missing documented responses for: (1) App crash on launch day -- 300K concurrent signups on June 11 is a realistic crash scenario. Who communicates? In what languages? Within what timeframe? (2) Crypto exposure incident -- a journalist discovers the Rain/USDC backend and publishes "FCB secret crypto bank." Response window is 2 hours. (3) KYC rejection surge -- rejected users take to Twitter and Reddit. (4) Player scandal during the Daily Player Drop. (5) Data breach of 750K email addresses. Each scenario needs: named response owner, draft holding statement, escalation path, and platform-by-platform communication sequence.

────────────────────────────────────────────────────────────────────────

- FCB's existing WhatsApp broadcast (50M members) is operated by FCB; Surgence aligns talking points and timing.

#### D. Content Governance

- Refine FCB's existing content calendar.

- Official X review before every post goes live in Phase 1.

- Instagram and Facebook briefs for FCB's social team.

- Talking points and approved language for all spokespeople.

- Zero token language from any FCB account in Phase 1. All token messaging activates exclusively at Phase 2.

#### E. Strategy

- Master GTM document: single source of truth for the neobank launch campaign, updated weekly. Delivered within 5 days of kick-off.

- Campaign sequencing and phase-gate conditions through World Cup window.

- Messaging framework: Revolut-competitive positioning, FCB brand trust, unbanked fan audience.

- Weekly alignment sessions with Andrew and Maurits begin week one. Walter joins on activation as CMO.

### Player Access (Schedule B): footballer-roster brokerage

LFG.cat has closed player endorsement relationships covering Messi, Lamine Yamal, Neymar, Ronaldinho, Alexia Putellas, Marcel Ruiz, and others (projects/fcb/concepts/player-access-programme). During the World Cup, every brand on earth seeks footballer association. This programme enables Surgence to broker deals from its Web3 client network against that roster.

| Provision | Detail |
| --- | --- |
| Structure | 60/40 revenue share on commissions. LFG closes the players. Surgence closes the sponsors. |
| Deal Conditions | Each sponsor deal conditional on (1) active co-marketing of the FCB neobank launch, and (2) public commitment to support the $FCB token sale when it goes live. Every brokered deal becomes an organic distribution channel for both phases. |
| Player SLA | LFG confirms player availability within 5 business days of Surgence presenting a qualified sponsor opportunity. |
| Category Exclusivity | Right of first refusal by category. LFG confirms no competing deal is active before Surgence opens any sponsor conversation. |
| Minimum Deal Size | USD 50,000 gross minimum per deal. |
| Independence | Player Access commissions are additive to the monthly retainer. Not offset. |
| Activity period | First qualified opportunity within two weeks of kick-off. |

### What Surgence has explicitly placed out of scope for Phase 1

Per the v6 "Deferred to Phase 2" carve-out:

- All token-related messaging, rumor seeding, and forward references. Zero token signal of any kind in Phase 1 across any channel.

- KOL Tier 2 amplification and Tier 1 TGE-day wave.

- CT FOMO positioning and locked-out narrative for secondary-market intent building.

- Presale support, holder communications, sentiment monitoring.

- Regional crypto-native channels (CIS, China, LATAM crypto channels). Activated in Phase 2.

- On-chain analytics dashboard and Dune deployment.

## 7. Surfaces Where Surgence Could Comprehensively Lead

The intent of this v2 plan is to give Surgence a single comprehensive view of the campaign so they can pick the workstreams where they add the most leverage. The following are surfaces currently under-owned (or owned by FCB / LFG with Surgence in an advisory role) where Surgence could expand scope. Each is presented as an option, not a commitment, and would be confirmed through the weekly alignment session.

### A. Hero Video and Creative Direction

Current state: no hero video produced. CCLA Schedule 1 grants 1 commercial shoot per season with 5 First Team players (15 minutes each), edits subject to FCB approval. CCLA Schedule 2 (Token) adds another commercial shoot for Phase 2.

Possible Surgence scope expansion: creative-direct the hero video and the WC-window player content series. Surgence already has the Web2 brief framework in Content Governance (D); creative direction is a 30-day add-on and aligns the hero asset with the messaging hierarchy.

Why it matters: the hero video is the single most-reused asset across the announcement, the country launches, and the post-final hand-off. A single creative authorship reduces narrative drift across 39 days of WC content.

### B. Creator Program (30 Seed + 150 Ambassador)

Current state: referenced in earlier marketing scaffolding; not currently owned by Surgence in the v6 scope.

Possible Surgence scope expansion: assemble and operate a 30 seed creator + 150 ambassador program with physical pack differentiation (signed jerseys, numbered FCB cards). Surgence's Korea network and Web2 infiltration overlap is high; Surgence is the natural operator if FCB is willing to fund a physical-pack program.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Creator & Influencer Brief and Compliance Framework

A 30-seed + 150-ambassador creator program is proposed with no brief. Missing: (1) Approved messaging and prohibited language list -- creators must not mention crypto, Web3, or $FCB token under any circumstances in Phase 1. (2) Disclosure requirements: FTC (US-based creators), CONAR (Brazil), PROFECO/IFT (Mexico) -- paid creator relationships require jurisdiction-specific disclosure language. (3) Content approval process and turnaround time. (4) Usage rights -- can Barca Banc repost creator content on FCB official channels? (5) Exclusivity terms -- can a Barca Banc ambassador simultaneously promote Nubank or Mercado Pago? A 180-person creator program without a brief across 4 regulated fintech markets is a legal and brand risk.

────────────────────────────────────────────────────────────────────────

Why it matters: Phase 1's primary distribution gap is creator-mediated reach into football-fan audiences who do not follow FCB official channels. Surgence's Reddit and Facebook seeding reaches the engaged-fan layer; a creator program reaches the latent-fan layer.

### C. Press and Mainstream Media

Current state: Carlos owns PR and player access per the v6 scope; not actively brokering mainstream tier-1 press for the neobank narrative.

Possible Surgence scope expansion: mainstream and sports press placement (Bloomberg, WSJ, FT, ESPN, The Athletic, Marca, Sport, Mundo Deportivo). The pitch is the Revolut-competitive narrative with FCB brand trust, which Surgence is already shaping in the Master GTM document.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Press Kit & Media Asset Package + Embargo Strategy

Pitching Bloomberg, WSJ, FT, ESPN, The Athletic, Marca, and Mundo Deportivo simultaneously on May 24 without an asset package or embargo strategy produces zero exclusives -- editors will not compete for a story offered to five competitors simultaneously. Missing: (1) Press kit: high-res card renders, localized app screenshots, executive bios, approved quotes, key stats sheet, background brief on Rain/USDC settlement layer (financial press will ask). (2) Embargo strategy: one financial exclusive (FT or Bloomberg, 48-hour embargo), one sports exclusive (The Athletic, 24-hour embargo), regional exclusives (Marca, Mundo Deportivo). Assets must be ready by May 20.

────────────────────────────────────────────────────────────────────────

Why it matters: the May 24 announcement loses asymmetric impact if it lands only in football and Web2 channels. Tier-1 financial press validates the "better bank" framing for affluent and unbanked-by-choice fan segments.

### D. Paid Media (X / IG / TikTok / YouTube)

Current state: Surgence runs KOL and paid media at-cost with zero margin (per v6 commercial terms). Phase 1 paid-media budget envelope is TBD; allocated to Web2 football creators, podcast placements, and regional amplification when joint-confirmed with Andrew.

Possible Surgence scope expansion: consolidate paid-media planning across all platforms (not only Web2 creators) so spend allocation is governed by the same Master GTM document. The CCLA Schedule 1 already grants 2 branded content campaigns per season; the v4 Schedule 1 Launch Announcement clauses commit FCB to amplify on X / IG / Facebook / LinkedIn at Product Launch and each Country Launch.

Why it matters: if Surgence is operating the organic Web2 layer and the master messaging, splitting paid media to a third party fragments the narrative. A consolidated Surgence-managed paid-media line (still at cost, still client-controlled) keeps the campaign coherent.

### E. IRL Activation (WC Host City and Camp Nou)

Current state: no IRL activation owned by Surgence in v6.

Possible Surgence scope expansion: WC host-city VIP hangout (Mexico City, Guadalajara, Monterrey, Boston, NYC, LA, Toronto, Vancouver, Mexico City for the final). 10 to 30 invited fans per host city, signed jerseys, on-site Loyalty Dividend reveals, on-site card sign-ups. Anchored to opening matches.

Why it matters: IRL becomes the highest-converting moment of WC because the audience is already at peak emotion. Surgence's KOL and ambassador network is the natural vector for invite distribution.

### F. World Cup Final Ticket VIP Draw Operations

Current state: mechanic exists in the campaign design (projects/fcb/concepts/world-cup-campaign); operations and livestream production not yet owned.

Possible Surgence scope expansion: operate the Final Ticket VIP Draw end-to-end: entries calculation (card spend × wins + bracket + waitlist tier), livestream production, winner outreach and travel coordination, on-site at MetLife Stadium (NJ) for the final.

Why it matters: the Final Ticket draw is the campaign's single highest-emotion conclusion. A dedicated operations owner avoids it landing as a back-office afterthought.

### G. Cross-Schedule Coordination with the Token Launch Campaign

Current state: v6 explicitly defers all token activity to Phase 2; coordination is asymmetric (Phase 1 does not signal Phase 2; Phase 2 inherits Phase 1's audience).

Possible Surgence scope expansion: even within the no-token-signal Phase 1 frame, the Surgence-built audience segmentation, highest-LTV identification, and TGE narrative framework for Phase 2 is the single most valuable hand-off asset of the campaign. Surgence already names this as the "Pre-TGE Hand-off" sub-phase. Comprehensive ownership means Surgence treats Phase 1 as a Phase 2 audience-build mission from day one, not as a standalone deliverable.

Why it matters: by the time Phase 2 activates in August, the most valuable TGE audience available to any project launching in Q3 2026 is the pre-warmed FCB neobank user base. Surgence has named this; the v2 plan codifies it as a Phase 1 success metric, not a Phase 2 starting point.

## 8. FCB Owned Channels

We have the following marketing rights:

- Exclusion Territories (UAE, Singapore, Malaysia, Indonesia + sanctioned jurisdictions).

- FCB to publish coordinated organic posts on X, Instagram, Facebook, and LinkedIn at (a) Product Launch (Barça Banc go-live) and (b) each Country Launch within the Territory. Country Launches timed to coincide with FIFA World Cup 2026 match windows.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: App Store Optimization (ASO)

No mention of App Store or Google Play optimization anywhere in the plan. When a Brazilian fan searches "cartao Barcelona," "banco do Barca," or "FCB card" on the App Store, what happens? ASO is typically the #2 acquisition channel for fintech apps after referrals. Missing: (1) App name, subtitle, and keyword field optimization in Portuguese and Spanish. (2) Screenshot strategy localized per country showcasing the six WC mechanics. (3) App preview video (30 seconds, localized). (4) Review velocity plan -- 500+ reviews in week 1 significantly boosts ranking. (5) Localized app store descriptions per market. ASO takes 2-4 weeks to index after submission. The app is live June 11. Start now.

────────────────────────────────────────────────────────────────────────

- Instagram, X, Facebook, LinkedIn, Web .

### Reweighted post-count cadence (per projects/fcb/concepts/fcb-social-baseline)

Instagram is FCB's highest-engagement platform (147M followers, ~10 stories/day baseline, 1M+ likes possible per post during off-season). The cadence the CCLA should bind:

| Channel | Format | Cadence (post-Announcement) |
| --- | --- | --- |
| Instagram | Stories (priority) | 3 per day for 7 days |
| Instagram | Feed post | 1 anchor + 2 follow-up posts in week 1 |
| X / Twitter | Posts | 2 per week for 2 weeks |
| TikTok | Player-interview clip (Olivia Rodrigo template) | 1 in week 1 |
| Facebook | Post | 1 |
| LinkedIn | Post | 1 |
| WhatsApp | Channel post (CTA / waitlist link) | 1 + 1 follow-up |

All commitments bind every FCB-operated language account (English, Spanish, Catalan, Portuguese, Indonesian, Japanese, Arabic, etc.), not only the primary @FCBarcelona handle.

### Outstanding ask in the next CCLA pass

- Open Ask #7: "FCB shall pause all non-Banc-related organic content on the primary @FCBarcelona main accounts (Instagram, X, TikTok) for at least 8 hours surrounding the Announcement post on the Announcement Date, excluding live-match coverage and breaking-news exceptions agreed in advance with NewCo." Operational ask supported by the social-baseline data.

### Other CCLA marketing rights worth flagging

- 1 commercial shoot per season with 5 Men's First Team players, 15 minutes each

- Right to use existing FCB footage for advertising 2 branded content campaigns per season

- Project Microsite at banc.fcbarcelona.com

## 9. Sponsor Collaboration Plays (Phase 1 compatible)

Six campaign archetypes apply the Spotify-Barça mechanic to the neobank surface. Phase 1 ships only the four that don't require an NFT or token surface:

| Play | Notes |
| --- | --- |
| #1 Spotify Collab Jersey Raffle | Fiat raffle for 10 signed jerseys whenever Spotify activates a Barça-artist collab. Easy, huge impact. Olivia Rodrigo / Lamine TikTok format is proven template. Ship next. |
| #2 Streamer Camp Nou Takeover | Kai Cenat / IShowSpeed / ElXokas single-stream playbook. ~10K cards in 4 hours at 0.5% conversion on a 2M-concurrent stream. |
| #3 National Holiday Drops | Brazil Independence Sep 7, Mexican Independence Sep 16, etc. Recurring annual calendar; minimal incremental design cost after Year 1. |

## 10. Critical-Path Open Items

The five highest-priority items that gate Phase 1 launch quality:

- FIFA broadcast partnership for the Mexico opening-match in-broadcast announcement. This is the highest-leverage cinematic moment of the entire launch. Owner: Maurits to engage FIFA / Telemundo / Televisa within 7 days.

- CRM data tier confirmation for the Loyalty Dividend. Surgence confirms within 30 days of kick-off; Tier 1 (full transaction history) requires LFG-B + FCB cooperation. Launch date does not move for data availability: if Tier 1 is unavailable, mechanic ships at Tier 3 and upgrades on confirmation.

- Client entity decision on the Surgence services agreement.

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Customer Support Capacity for Launch Day

300K people attempting to sign up across 4 LatAm markets on June 11 with no customer support plan. Missing: (1) Support channel strategy -- in-app chat, WhatsApp support line, email helpdesk, or all three? (2) Language coverage -- Portuguese-speaking agents for Brazil, the largest market. (3) Expected ticket volume model -- fintech launches generate 10-20x normal support volume on Day 1. (4) KYC rejection handling -- the most common support issue at launch; rejected users need a clear communication and resubmission path. (5) Response time SLA by issue category. For a product where "cannot activate my card" means "cannot participate in the WC mechanics I was promised," support failure becomes viral social media content instantly.

────────────────────────────────────────────────────────────────────────

────────────────────────────────────────────────────────────────────────

⚠ MISSING: Competitive Response Contingency

The plan assumes the competitive landscape is static through July 19. It is not. Nubank (100M+ customers in Brazil), Mercado Pago (dominant across LatAm), and Revolut all operate in these markets and will react to a major FCB neobank announcement. Missing: (1) Scenario plan for a Nubank "FCB fan" counter-promotion on May 25. (2) Response if a competitor copies the Loyalty Dividend mechanic within 72 hours -- it is not patented. (3) Competitive differentiation messaging ready for rapid deployment. (4) Real-time monitoring setup to detect competitive responses. A launch this visible guarantees competitive reaction. No contingency plan means the first response will be improvised.

────────────────────────────────────────────────────────────────────────

Missing also out of home campaign? World cup activation

# Phase 1 Mkt v2

FC BARCELONA BANC Updated Phase 1 Marketing Plan — LatAm Fiat Card Launch Incorporating benchmarks: Nubank · Chime · Tuyo · May 10, 2026 · T-14 days to announcement · CONFIDENTIAL

| ✅ CONFIRMED | ⚠️ IN PROGRESS | ❌ MISSING | 🔗 DEPENDENCY |
| --- | --- | --- | --- |

### Phase 1 / Wave 1 — LatAm Fiat Card Launch

Announced May 24 → Card live June 11

| Sub-wave | Window | Markets | Anchor |
| --- | --- | --- | --- |
| 1a | Jun 11–13 | Mexico, Brazil, Argentina | Mexico opens World Cup at Estadio Azteca |
| 1b | Jun 18–22 | Colombia | Highest-rated Spain or Brazil match (MD2) |
| 1c | Opportunistic (knockout window) | Chile — deferred | Bridge cannot confirm Chilean rails yet |

Product: Barça Banc — fiat-only Visa card, FCB Rewards Points. Zero crypto/wallet/token surfaces in consumer UX. Background settlement via Rain USDC. Domain: banc.fcbarcelona.com.

Target funnel: 1.5M waitlist before June 11 → 500K M1 downloads (now tracking ~60–80% of that due to 4-market scope) → 35.75% effective conversion (KYC 55% × card activation 65%).

Win/Advance/Survive cascade: Match results escalate rewards as countries progress — peaks with a Champion Card metal variant shipped within 7 days if a country wins the World Cup.

# 01  STRATEGIC FOUNDATION

POSITIONING

| Tagline | Your culer life, rewarded. | ✅ CONFIRMED |
| --- | --- | --- |
| Positioning | The only card that pays you back for being a Barça fan. Every swipe converts loyalty into cashback. No crypto required. | ✅ CONFIRMED |
| Frame | Celebration — not grievance. FCB gives back what the fan has always deserved. Grievance framing (e.g., 'the club has taken from you') is explicitly banned. | ✅ CONFIRMED |
| Phase 1 Rule | 100% Web2. No token language, no CT seeding, no Web3 channels. Token discourse (TGE) begins August 2026 and is a separate campaign. | ✅ CONFIRMED |

BRAND IDENTITY — STATUS: MISSING

| Brand Identity |  | ❌ MISSING |  |  |
| --- | --- | --- | --- | --- |
|  | Does not exist as of May 10. Required: Brand identity, landing page / microsite, press kit, creator briefs, app store assets, Country-Edition card artwork, all 19 digital surfaces. Nubank benchmark: purple card as identity artifact — one color, zero ambiguity. | - Brand identity = Andrew / Walter - Surgence? |  |  |
|  |  | - Press Kit = Walter + Agency / Carlos |  |  |
|  |  | - Landing Page = Lav’s team |  |  |
|  |  | - App store assets = Lav’s team |  |  |
|  |  | - App design = Lav’s team |  |  |
|  |  | - Creators brief = ??? |  |  |

AUDIENCE SEGMENTS

| Segment | Who They Are | Activation Angle | Benchmark Learning |  |
| --- | --- | --- | --- | --- |
| Core Culers | FCB social followers, merch buyers, match viewers. 18–45. LatAm primary. | Brand loyalty. The club they supported their whole lives now offers something back. | Nubank: NPS-led referral from existing advocates. Chime: member identity ('I bank with Chime'). | ✅ CONFIRMED |
| Unbanked / Underbanked | Young LatAm fans with predatory local banks or no banking. High mobile. | Modern clean digital banking with a brand they already trust. Zero crypto required. | Nubank: launched with waitlist + purple mailer to underbanked Brazil. Primary growth vector. | ✅ CONFIRMED |
| Korean Fan Market | Outsized FCB following relative to market size. High ARPU. Premium buyers. | Web2-first activation. Football channels, not crypto. Localised card variant. | Tuyo: X-only distribution for niche-but-passionate audience. Adapt for Korean football forums. | ✅ CONFIRMED |
| LatAm Football Adjacent | Non-Barça fans who watch La Liga + World Cup. New to FCB brand. | World Cup is the entry point. Country Boost Days turn national pride into Barça Banc trial. | Chime: Ball on a Budget NBA activation — 25M views from sports-adjacent audience. Apply same logic. | ⚠️ IN PROGRESS |
| Web3 / Crypto-Adjacent Fans | CT users who follow football and crypto. | OUT OF SCOPE — Phase 2 only. Zero Phase 1 touchpoints. | Tuyo Phase 1 → Phase 2 sequencing: build product users first, then layer token narrative. | ✅ CONFIRMED |

02  PRE-LAUNCH SPRINT  —  MAY 10–24

14 days. Every item below must complete before May 24. Items are ordered by dependency.

| Item | What It Is | What Good Looks Like | Benchmark | Status |
| --- | --- | --- | --- | --- |
| Clarify scope with Surgence | Understand what is included on Phase 1 scope ($60K retainer, 3 months). | Clear dependencies (CRM) and understand all open questions. | — | ❌ MISSING May 11-13 |
| Sign Surgence contract | Legal agreement for Phase 1 scope ($60K retainer, 3 months). | Signed, countersigned, entity confirmed. WhatsApp seeding starts same day. | — | ❌ MISSING May 13 |
| Brand identity sprint UX/UI | Logo, color system, type, card artwork brief, tone-of-voice guide. | Lav’s team to complete | Nubank: single purple card = entire brand. Zero ambiguity. | ❌ MISSING XXXX |
| Landing page + waitlist | banc.fcbarcelona.com — hero visual, tagline, waitlist CTA, referral queue-jump mechanic. | Mobile-first. Under 3s load. A/B test CTA copy. Queue-jump counter visible in real time. | Chime: landing page was their primary CAC surface. Nubank: waitlist exclusivity created FOMO. | ❌ MISSING May 10–17 |
| App Store submission | iOS + Android submissions in Brazil, Mexico, Argentina, Colombia. | All 4 market submissions filed by May 17. Apple review buffer = 7 days. | Financial apps face enhanced review. Nubank: separate submissions per market took 3 weeks. | ❌ MISSING May 17 HARD DEADLINE |
| Press kit assembly | Brand assets, embargo pitch, founder bio, product screenshots, key stats, B-roll. | PDF + Dropbox folder. Embargo pitch written. 10 journalists briefed by May 18. | Chime: Halftime Wedding generated 20 media pickups from one tight press kit. | ❌ MISSING May 10–20 |
| Paid media setup | Agency brief, account setup (Meta Ads, Google Ads, TikTok Ads), creative specs, budget approved. | Media plan submitted May 14. Campaigns loaded May 20. Live June 1 (pre-World Cup warm-up). | Chime: $1M Bet AKQA — 375M impressions from one bold paid activation. Model the single big bet. | ❌ MISSING May 14 |
| Legal framework — creator disclosures | FTC/CONAR/CNBV/SFC disclosure language per market. Creator brief template. NDA template. | One-page creator brief. Disclosure language appended. Legal sign-off before any creator contract. | Chime three-tier model: each tier had a different disclosure + exclusivity structure. | ❌ MISSING May 14 |
| Facebook group admin outreach | 30 admins across LatAm football Facebook groups. Relationship-building, not spam. | Personal outreach from Surgence team. No pitch in first contact. Build trust over 2 weeks. | Nubank: seeded early adoption through organic Facebook groups in Brazil in 2014–2015. | ⚠️ IN PROGRESS Starts May 11 |
| WhatsApp community seeding | Football fan WhatsApp groups in Brazil, Mexico, Argentina, Colombia, SEA, MENA. | Surgence team joins as members, provides value for 2 weeks before any product mention. | Needs 4 weeks minimum. May 10 is last possible start date to reach June 11 organically. | ❌ MISSING Starts TODAY |
| Country-Edition card artwork | 4 cards × 5,000 units: Brazil, Mexico, Argentina, Colombia. Design + to printer. | Artwork brief May 12. Design approved May 16. Printer file submitted May 16. | Physical artifact = earned media. Nubank's purple card got photographed by 200K users. | ❌ MISSING May 16 TO PRINTER |
| Loyalty Dividend CRM integration | FCB historical spend data → fan identity mapping → personalised card generation. | Sample data set tested with 1,000 fan profiles. Shareability tested. LGPD compliance confirmed. | Tuyo: BNPM slot machine was viral because it was personalised + surprising. Same logic here. | 🔗 DEPENDENCY FCB Data team |
| Korea activation brief | Localised strategy for Korean football channels, forums, and fan communities. | Brief written. One local partner identified. Korean-language content calendar mapped. | Tuyo: X-only for niche audience. Korea = niche-but-high-ARPU. Don't dilute with mass channels. | ❌ MISSING May 20 |

03  LAUNCH MOMENT — MAY 24

The final La Liga match day. Every activation fires simultaneously across owned, rented, and borrowed channels. This is not a social media post. It is a coordinated detonation across 8 surfaces in a 6-hour window.

| Time (CET) | Activation | What Happens | Benchmark |  |
| --- | --- | --- | --- | --- |
| 06:00 CET | Press embargo lifts | Bloomberg, FT, The Athletic, ESPN Brasil, Marca, GOAL publish simultaneously. | Chime: Halftime Wedding — 20 media pickups in 4 hours from one coordinated embargo. | ❌ MISSING |
| 10:00 CET | FCB official social post | Instagram + TikTok + X + YouTube Shorts. Product hero visual. Tagline. Waitlist link. | Nubank: launch post went to 5M followers at once. Engagement > reach. | ✅ CONFIRMED |
| 10:01 CET | Loyalty Dividend goes live | banc.fcbarcelona.com/your-rewards — fans enter FCB fan ID, get personalised card. | Tuyo: BNPM slot machine was live on launch day and drove immediate shares. Same mechanic. | 🔗 DEPENDENCY |
| 10:00 CET | WhatsApp broadcast (50M) | FCB WhatsApp broadcast list. One message. Link. No overexplaining. | 50M reach. Nubank used WhatsApp as primary Brazil activation channel 2014–2016. | ✅ CONFIRMED |
| 10:00 CET | Country-Edition card pre-order opens | 5K units per country. Countdown timer visible. Queue-jump for waitlist members. | Nubank: original purple mailer created physical FOMO. Scarcity drives urgency. | 🔗 DEPENDENCY |
| 12:00 CET | Daily Player Drop #1 | First player card live on Instagram Stories. Interactive poll: 'Which country edition?' | Cadence-first. Nubank's Carnaval drops were daily. Chime's NBA content was episodic. | ✅ CONFIRMED |
| Match Kickoff | In-match social activation | Live commentary + cashback mechanic preview. Story countdown: 'First win = first bonus.' | Chime: Ball on a Budget worked because it was live sports commentary. Time the content. | ⚠️ IN PROGRESS |
| Full Time | Founder post / CEO thread | FCB CEO or Barça Banc MD posts personal thread on X: why we built this, for who. | Nubank: Cristina Junqueira's personal posts outperformed all brand posts. Make it human. | ❌ MISSING |
| All Day | Reddit sleeper agents activate | Organic mentions across r/fcbarcelona, r/soccer, country-specific subs. | Tuyo: no paid Reddit. Surgence organic seeding model is correct. Execute as planned. | ⚠️ IN PROGRESS |
| All Day | Paid media day-1 campaigns live | Meta + Google + TikTok waitlist campaigns running in all 4 markets. | Chime: paid media was running before launch day. Don't cold-start on announcement day. | ❌ MISSING |

04  WORLD CUP WINDOW — JUNE 11 TO JULY 19

The six core mechanics. Each runs across the full window with market-specific peak moments. Nubank spent $40M+ on the 2022 World Cup. The advantage here is owned audience — FCB's 147M Instagram alone reaches more people than Nubank's entire customer base at that time.

| 01 | Country Boost Days When the national team of Brazil, Mexico, Argentina, or Colombia plays, cashback multiplier activates for all cardholders from that country. 3× cashback on match day. | EXECUTION REQUIREMENTS Design a match-day notification sequence: pre-match hype, kick-off cashback alert, final whistle summary. In-app banner + push + WhatsApp. | BENCHMARK Chime: Financial Progress Month — themed windows that activate the full member base. Apply same calendar architecture to football match schedule. ✅ CONFIRMED |
| --- | --- | --- | --- |

| 02 | Win Bonus When Barça wins, all cardholders get a win bonus deposited to their account. Automatic, instant, announced via push notification. | EXECUTION REQUIREMENTS Real-time trigger requires FIFA broadcast data integration. Backup: manual post-match activation with 15-minute delay. Design both flows. | BENCHMARK Nubank: real-time transaction notifications trained users to check the app after events. Win Bonus = same behavioral loop. 🔗 DEPENDENCY |
| --- | --- | --- | --- |

| 03 | MOTM Cashback The Man of the Match from each World Cup game triggers a cashback category boost. Messi MOTM = double cashback on food. Vinicius MOTM = double on transport. | EXECUTION REQUIREMENTS Category mapping needs product team sign-off. 32 MOTM categories to pre-map. Requires real-time match data. | BENCHMARK Nubank: partnered with streaming services (Netflix Wednesday) for co-branded moments. MOTM = the most co-brandable moment in football. 🔗 DEPENDENCY |
| --- | --- | --- | --- |

| 04 | Country-Edition Cards 5,000 physical cards per country (Brazil, Mexico, Argentina, Colombia). Pre-order opened May 24. Ship during World Cup window. | EXECUTION REQUIREMENTS Physical fulfillment partner needed. Shipping logistics to 4 countries. Unboxing video brief for creator program Wave 2. | BENCHMARK Nubank: original purple card was photographed by 200,000+ users. Physical artifact = free earned media at scale. Design the unboxing to be photographable. 🔗 DEPENDENCY |
| --- | --- | --- | --- |

| 05 | Bracket Prediction Game In-app game. Predict the bracket, earn points redeemable for cashback boosts. Daily engagement mechanic for the full 38-day window. | EXECUTION REQUIREMENTS Product feature must be built and QA'd before June 11. Leaderboard visible to all users. Social sharing of bracket = organic viral loop. | BENCHMARK Tuyo: BNPM slot machine drove shares because it was game-mechanic native. Bracket prediction = same logic, football context. ⚠️ IN PROGRESS |
| --- | --- | --- | --- |

| 06 | Final Ticket VIP Draw One cardholder per country wins tickets + hospitality to the World Cup Final (July 19). Entry = one transaction per week of the tournament. | EXECUTION REQUIREMENTS Legal sweepstakes compliance in all 4 markets. Prize logistics. Weekly winner announcement for sub-prizes (jerseys, signed merch) to maintain engagement. | BENCHMARK Chime: Final Ticket VIP Draw equivalent = their $1M Bet — one big prize creates disproportionate earned media relative to cost. ⚠️ IN PROGRESS |
| --- | --- | --- | --- |

05  CREATOR & INFLUENCER PROGRAM

180 creators across 4 markets over 3 waves. Chime's three-tier model is the template. Every creator brief requires legal sign-off before it goes out. Legal framework is the gate.

THREE-TIER CREATOR ARCHITECTURE (ADAPTED FROM CHIME)

| Tier | Profile | Count | Audience | Fee Range | Status |
| --- | --- | --- | --- | --- | --- |
| Tier 1 Macro | Football + finance macro influencers. Known faces in each market. | 10 | 1M–10M followers | $5K–$15K / post | ❌ MISSING Legal framework needed first |
| Tier 2 Mid | Football commentators, fan page operators, lifestyle creators with 100K–1M. | 50 | 100K–1M followers | $1K–$5K / post | ❌ MISSING Legal framework needed first |
| Tier 3 Micro | Super-fans, match-day vloggers, stadium regulars. Authentic voice. | 120 | 10K–100K followers | $200–$1K / post | ❌ MISSING Legal framework needed first |

CREATOR WAVE CALENDAR

| Wave | Dates | Creators | Brief Focus | Status |
| --- | --- | --- | --- | --- |
| Wave 1 | May 15–24 | 10 Tier 1 | Launch announcement. Loyalty Dividend reveal. 'Here's what my Barça years would have paid me back.' | ❌ MISSING Blocked: legal framework missing |
| Wave 2 | May 25–Jun 10 | 60 Tier 2 | Daily Player Drop amplification. Country-Edition card unboxing. Waitlist urgency. | ❌ MISSING Blocked: legal framework missing |
| Wave 3 | Jun 11–Jul 19 | 110 Tier 3 | World Cup mechanics live. Match-day content. Win Bonus reactions. Country Boost Days. | ❌ MISSING Blocked: legal framework missing |

MISSING: LEGAL COMPLIANCE FRAMEWORK

| ❌ MISSING Legal Framework | Required before first creator contract is signed. Includes: (1) FTC/CONAR/CNBV/SFC disclosure language per market, (2) Creator brief template with embedded disclosure, (3) NDA/exclusivity terms, (4) Content approval workflow — all posts require compliance sign-off before publishing. A single non-compliant post in a regulated financial market can trigger enforcement action and halt the campaign. Owner needed: FCB Legal + external financial advertising counsel in each market. |
| --- | --- |

06  PAID MEDIA

The waitlist math does not close without paid media. Organic alone from FCB's owned channels yields ~25K signups. The 750K target requires a paid media investment that has not been modeled. Chime's '$1 Million Bet' (375M impressions, AKQA) and Nubank's $40M+ World Cup spend are the benchmarks.

BUDGET MODEL — MISSING

| Market | Est. CAC | Budget Needed | Channel Mix | Status / Action |
| --- | --- | --- | --- | --- |
| Brazil 🇧🇷 | $8–15 | $600K–1.5M | Meta 50% · Google 25% · TikTok 25% | ❌ MISSING — Nubank dominates Brazil paid. Must outbid on FCB brand terms + football keywords. |
| Mexico 🇲🇽 | $12–20 | $400K–800K | Meta 40% · Google 30% · TikTok 30% | ❌ MISSING — Mercado Pago is the dominant incumbent. Differentiate on FCB loyalty angle. |
| Argentina 🇦🇷 | $6–10 | $200K–400K | Meta 60% · Google 20% · TikTok 20% | ❌ MISSING — Lower CAC due to economic conditions. High engagement market. Messi fandom is acute. |
| Colombia 🇨🇴 | $10–18 | $200K–400K | Meta 45% · Google 30% · TikTok 25% | ❌ MISSING — Fastest-growing neobank market in LatAm. Revolut and Nubank both entering. |
| Korea 🇰🇷 | $15–25 | $150K–300K | Instagram 50% · YouTube 30% · Naver 20% | ❌ MISSING — Web2-first, premium audience. Different channel mix. Requires localised creative. |

THE SINGLE BIG BET — CHIME BENCHMARK

| BARÇA BANC BIG BET CONCEPT | The Loyalty Dividend Reveal is the $1M Bet equivalent. Design one hero paid/earned campaign for May 24 built entirely around the Loyalty Dividend mechanic: 'We calculated what every BarçaFan would have earned if the card existed since 2000. Here's yours.' Full-page newspaper ad in Marca + Sport + Folha de S.Paulo. One OOH placement in Camp Nou. Paid social amplification of the personalised card generator. Chime's $1M Bet (AKQA) generated 375M impressions at a fraction of normal CPM because the concept was inherently newsworthy. Loyalty Dividend is equally newsworthy. Status: ❌ MISSING — concept validated, execution not started, budget not allocated. |
| --- | --- |

OOH — MISSING (DEADLINE PASSED FOR PREMIUM INVENTORY)

| ❌ MISSING OOH — 4 MARKETS | Premium OOH inventory in São Paulo, Mexico City, Buenos Aires, Bogotá locks 6–8 weeks in advance. That window has passed. Remaining strategy: (1) book remnant inventory NOW for June 11 (World Cup opener), (2) focus OOH spend on stadium adjacency — fan zones, transit routes to watch parties, (3) Nubank benchmark: Sphere Las Vegas ($10M+, 700 press mentions) — find the LatAm equivalent single-statement placement that earns media. Budget estimated $500K–1.5M for remnant + experiential OOH. Owner needed: media agency with LatAm OOH network. Brief required immediately. |
| --- | --- |

07  OWNED CHANNEL ACTIVATION

| Channel | Content Focus | Execution Standard | Status |
| --- | --- | --- | --- |
| Instagram (147M) | Daily Player Drop (Stories). Reel per match day. Country Boost Day countdown. Country-Edition card launch. | One story per day minimum. Player card = thumb-stop format. Poll mechanic on every post. | ✅ CONFIRMED |
| TikTok | Match-day reactions. Behind-the-scenes of card design. Loyalty Dividend demo. Duet with fans. | Post within 15 minutes of full time. Use trending audio. Fan-generated content repost strategy. | ⚠️ IN PROGRESS |
| X / Twitter | Announcement thread May 24. Real-time match commentary. Win Bonus announcements. CEO thread. | Founder/CMO account posts alongside brand account. Nubank CEO model: personal post > brand post. | ⚠️ IN PROGRESS |
| YouTube | Loyalty Dividend explainer. Country-Edition card unboxing. FCB Banc product tour. | 3–5 minute product story. Subtitle in PT-BR + ES. SEO-optimised title. Embed on landing page. | ❌ MISSING |
| WhatsApp Broadcast (50M) | Launch announcement May 24. World Cup match previews. Win Bonus notifications. | Max 2 messages per week. No marketing language — news only. Link to landing page always. | ✅ CONFIRMED |
| Email / CRM | Waitlist confirmation → onboarding sequence → activation nudge → first spend → referral ask. | 6-email sequence. Day 0, 1, 3, 7, 14, 30. Personalised with fan data where possible. | ❌ MISSING |
| banc.fcbarcelona.com | Waitlist page, Loyalty Dividend generator, product explainer, country card pre-order. | Mobile-first. Under 3s load. Waitlist CTA above fold. Queue-jump referral counter visible. | ❌ MISSING |

EMAIL ONBOARDING SEQUENCE — MISSING

| Send | Trigger | Content | Status |
| --- | --- | --- | --- |
| Day 0 | Waitlist signup | Welcome. Queue position. How to move up (referral). Your Loyalty Dividend preview: 'We're calculating yours now.' | ❌ MISSING Copywriter needed |
| Day 1 | +24 hours | Loyalty Dividend revealed: 'Here's what your Barça years were worth.' Shareable card image. CTA: Share to move up queue. | ❌ MISSING Copywriter needed |
| Day 3 | +3 days | How Barça Banc works. Product explainer. Country-Edition card preview. CTA: Pre-order your card. | ❌ MISSING Copywriter needed |
| Day 7 | App goes live | You're in. Download link. First 7 days: double cashback. Bracket Prediction Game is live. | ❌ MISSING Copywriter needed |
| Day 14 | +7 days post-download | First spend nudge. 'You have $X cashback waiting. Spend $1 to unlock it.' CTA: Make your first transaction. | ❌ MISSING Copywriter needed |
| Day 30 | +30 days | Monthly Culer Report — personalised spend summary, cashback earned, how you compare to other fans in your country. | ❌ MISSING Copywriter needed |

08  PR & EARNED MEDIA

Design one engineered earned moment per phase. Chime generated 20 media pickups from the Halftime Wedding and 375M impressions from the $1M Bet — both designed to be inherently newsworthy. Nubank's Sphere Las Vegas activation generated 700+ press mentions. The Loyalty Dividend is Barça Banc's equivalent.

| Phase / Date | Moment Name | Execution | Benchmark |  |
| --- | --- | --- | --- | --- |
| Phase 1 Earned Moment May 24 | Loyalty Dividend Launch | The story: 'We calculated what 50 million culers would have earned if this card existed since 2000.' Publish top-10 fan lifetime values (anonymised). FCB legend on record. Send to 10 journalists under embargo. | Chime: Manifest Money Candle (Apotheke collab) — designed to be photographed and shared. Loyalty Dividend card image = same photogenic hook. | ❌ MISSING |
| Phase 2 Earned Moment Jun 11 World Cup Opener | First Country Boost Day | Real-time coverage of first cashback multiplier activation. '50,000 Barça fans in Brazil earned 3× cashback at kick-off.' Press release with live transaction data (anonymised). | Nubank: released transaction data during World Cup 2022 in real time. Press loved the data story. | ❌ MISSING |
| Phase 3 Earned Moment Jul 19 Final | VIP Draw Winner Announcement | Announce the 4 Final ticket winners publicly. Video their reaction. Fly press to the Final. One human story = 10× the coverage of a product feature. | Chime: Halftime Wedding (Mavs game) — one human moment, 20 media pickups. Same model. | ❌ MISSING |
| Crisis Earned Moment On-demand | CEO Response Protocol | If app crashes, security incident, or regulatory inquiry: FCB Banc CEO posts personal statement within 60 minutes. No corporate communications language. Direct, human, specific. | Nubank: Cristina Junqueira's Instagram post during Brasil Paralelo crisis reversed sentiment in 48 hours. The CEO being visible IS the crisis response. | ❌ MISSING |

PRESS EMBARGO LIST — MISSING

Target 10 journalists briefed by May 18, embargo lifting simultaneously May 24 at 10:00 CET.

| Publication | Market | Journalist Target | Status |
| --- | --- | --- | --- |
| Bloomberg | Global | LatAm fintech / sports finance beat | ❌ MISSING |
| Financial Times | Global | European football / neobank correspondent | ❌ MISSING |
| The Athletic | Global | FCB beat writer — direct brand story angle | ❌ MISSING |
| ESPN Brasil | Brazil | Football + commerce intersection | ❌ MISSING |
| Folha de S.Paulo | Brazil | Business section — fintech coverage | ❌ MISSING |
| Marca | Spain/LatAm | FCB official media — will cover | ⚠️ IN PROGRESS |
| El País | Spain/LatAm | Business + football crossover | ❌ MISSING |
| El Financiero | Mexico | Fintech beat, neobank coverage | ❌ MISSING |
| Infobae | Argentina | Digital native, high LatAm reach | ❌ MISSING |
| Forbes Colombia | Colombia | Business + fintech coverage | ❌ MISSING |

09  COMMUNITY DISTRIBUTION ARCHITECTURE

| Channel | Who / Where | Execution | Benchmark |  |
| --- | --- | --- | --- | --- |
| Reddit Sleeper Agents | r/fcbarcelona, r/soccer, r/brasil, r/futbol, r/argentina + country subs. | Surgence team. Pre-existing accounts with history. Organic mentions, not promotion. | Tuyo: zero paid Reddit. Pure organic seeding through authentic community members. | ⚠️ IN PROGRESS |
| Facebook Group Admins (30) | 30 admins across LatAm and MENA football groups. | Surgence outreach. Two-week relationship build before any product mention. | Nubank: seeded adoption through Brazilian Facebook groups 2014–15. Primary early growth channel. | ⚠️ IN PROGRESS |
| WhatsApp Seeding | Football fan WhatsApp groups: Brazil, Mexico, Argentina, Colombia, SEA, MENA. | Surgence team joins as members. Minimum 2 weeks before product mention. Must start TODAY. | Requires 4 weeks from start to June 11. Last possible start date = May 10. | ❌ MISSING |
| Korea Web2-First | Korean football fan forums, Naver Cafe communities, Instagram football accounts. | Local partner brief. Korean-language content. No crypto language. Card + cashback only. | Tuyo: niche-but-high-ARPU audience. Concentrate rather than dilute. | ❌ MISSING |
| Loyalty Dividend Community | Community Advisory Board: 10–20 super-fans as early testers and advocates. | Recruited before May 24. Given early access. Brief to share Loyalty Dividend card. | Chime: early super-users (Wayne Brady, Tiffany Aliche) were community-native before they were paid. | ⚠️ IN PROGRESS |
| Discord / Fan Forum | NOT in Phase 1 plan. Recommendation: one owned community space. | Create a Barça Banc Discord or Telegram. Culer Lane concept (Chime Lane equivalent). Members-only perks, early access, exclusive content. | Chime Lane: member-exclusive lanes at events = owned community loyalty layer. Apply same logic. | ❌ MISSING |

10  POST-WORLD CUP RETENTION — AUGUST ONWARD

The World Cup ends July 19. The 2026-27 La Liga season opens early August. This gap is the biggest unaddressed risk in the plan. Chime's Financial Progress Month and monthly Culer Report concept solve this. Tuyo's seasonal points mechanic (4× → 3× → 2× → 1×) provides the reward architecture.

| Mechanic | What It Is | Execution + Benchmark |  |
| --- | --- | --- | --- |
| Monthly Culer Report | Personalised monthly spend summary, cashback earned, ranking vs. other fans in your country. | Data-as-content. Month 1 report publishes August 1. Shareable PDF card format. Chime: Financial Progress Report was their highest-earned-media piece of the year. | ❌ MISSING |
| La Liga Season Activation | Season opener in August = relaunch moment. New Daily Player Drop cadence for 2026-27 squad. | New country boost calendar for La Liga matches. Loyalty Dividend updated with World Cup cashback data. | ❌ MISSING |
| Culer Lane — Members Only | Exclusive community layer for activated cardholders. Early access. VIP perks. | Chime Lane (NBA member benefit). Barça Banc equivalent: early access to Phase 2 features, Camp Nou virtual events, signed squad card drops. | ❌ MISSING |
| Referral Engine — Ongoing | Post-activation referral program. Invite a fan, earn 500-position queue jump or cashback bonus. | Nubank NPS-as-acquisition-infrastructure: every happy customer was a growth channel. Referral must be a permanent product feature, not a launch tactic. | ⚠️ IN PROGRESS |
| TGE Bridge Narrative | August: Phase 2 narrative begins. 'You've earned cashback. Imagine if it were also equity.' | Zero token language in Phase 1. August narrative shifts: '300K+ fans are already earning. Phase 2 gives them ownership.' Tuyo model: build users first, then layer token. | ❌ MISSING |
| Win-Back Campaign | 30-day inactive users receive re-engagement sequence. World Cup winner celebration mechanic. | Email + push: 'You earned $X during the World Cup. Here's your summary. Your friends earned $Y.' Chime: win-back email sequence was their highest-ROI retention channel. | ❌ MISSING |

11  ANALYTICS & MEASUREMENT FRAMEWORK

The plan has targets (750K waitlist, 250-320K downloads, 90-115K activated cards, $1.0B Y1 tx volume) but no measurement framework. Without attribution, the CAC model can't be built and paid media can't be optimized.

| Metric | Cadence | How to Measure | Target | Status |
| --- | --- | --- | --- | --- |
| Waitlist Signups | Daily | Source-tagged link per channel. UTM parameters on all paid + organic links. | 750K by Jun 11 | ❌ MISSING Owner needed |
| Referral Rate | Daily | % of signups from referral link. Queue-jump conversion rate. | >30% referral-driven | ❌ MISSING Owner needed |
| Loyalty Dividend Shares | Daily | Share events from personalised card generator. Viral coefficient. | >100K shares week 1 | ❌ MISSING Owner needed |
| App Downloads | Daily | App Store Connect + Play Console. By country, by source. | 250–320K total | ❌ MISSING Owner needed |
| Card Activation Rate | Weekly | Downloads → KYC complete → card activated. Funnel drop-off by step. | 35–45% of downloads | ❌ MISSING Owner needed |
| First Transaction Rate | Weekly | Activated cards → first spend within 7 days. | >60% within 7 days | ❌ MISSING Owner needed |
| Cashback Engagement | Per mechanic | Win Bonus claim rate. Country Boost Day uplift in tx volume. MOTM cashback redemption. | Per mechanic baseline TBD | ❌ MISSING Owner needed |
| CAC by Market | Weekly | Paid media spend ÷ new activated cards per market. | $15–30 blended target | ❌ MISSING Owner needed |
| NPS / Referral Score | Monthly | In-app NPS survey at Day 30. Referral send rate by NPS score bucket. | NPS > 50 | ❌ MISSING Owner needed |
| Creator Attribution | Per wave | UTM-tagged creator links. CPA per creator. ROAS by tier. | Tier 3 highest ROAS (Chime benchmark) | ❌ MISSING Owner needed |

12  CRISIS & COMPETITIVE RESPONSE PLAYBOOK

A financial product launch at scale will have a crisis moment. The variable is response time, not occurrence. Nubank's Cristina Junqueira reversed negative sentiment in 48 hours with a personal Instagram post. The playbook needs to be written before May 24, not during the incident.

| Scenario | Trigger | Response Protocol | Benchmark |
| --- | --- | --- | --- |
| App Crash / Outage | App unavailable >15 min on launch day or World Cup. | T+15min: CEO posts to X + Instagram. 'We know. We're fixing it.' T+30min: In-app ETA. T+2hr: Resolution post. T+24hr: Affected users get cashback credit as goodwill. | Nubank CEO model. Personal, specific. No corporate language. |
| Security / Data Incident | User data breach or fraudulent transaction spike. | Immediate: legal engaged. T+1hr: CEO statement. T+24hr: audit announced. T+7 days: remediation report. Affected users individually notified. | Early transparency only path to trust recovery in fintech. |
| Competitor Response | Nubank/Mercado Pago counter-campaign or cashback price-match. | 'They can copy the cashback. They cannot copy the crest.' Lean FCB brand. Escalate Loyalty Dividend content. Announce next mechanic early. | Nubank: leaned into NPS community vs. price war when attacked. |
| Regulatory Inquiry | BACEN/CNBV/BCRA/SFC inquires about advertising or licensing. | Pause all paid ads in that market immediately. Legal responds within 24hr. No public statement until legal reviewed. No team social posts about inquiry. | One non-compliant creator post can trigger this. Pre-empt with legal framework. |
| Negative Viral Moment | Creator post wrong. Loyalty Dividend error. FUD on X or Reddit. | Identify within 1hr (social listening required). Correct factual errors fast. Don't engage bad-faith FUD. Community advocates respond first. CEO only if it escalates. | Tuyo: slot-machine criticism. Founder explainer thread resolved it. |

13  MASTER ACTION TABLE — EVERYTHING MISSING

Every MISSING item from this plan in one place. Ordered by deadline. Assign an owner to each line before the end of this week.

| Deadline | Action | Why It Matters / What It Blocks | Owner Needed |
| --- | --- | --- | --- |
| TODAY May 10 | Sign Surgence contract | Unlocks brand identity, WhatsApp seeding, 19 downstream deliverables | Walter / FCB Legal |
| TODAY May 10 | Start WhatsApp community seeding | Needs 4 weeks minimum. Today = last possible start for June 11 | Surgence (post-signature) |
| TODAY May 10 | Appoint paid media agency | No budget model, no CAC by market, waitlist math doesn't close | Walter / FCB Marketing |
| TODAY May 10 | Identify legal counsel — all 4 markets | Creator program blocked. Any creator post is a compliance risk | FCB Legal |
| May 12 | Brand identity v1 delivery | Blocks landing page, press kit, card artwork, creator briefs | Surgence |
| May 12 | Submit app to App Store + Google Play | 7-day review minimum. Miss this = no app on launch day | Product team |
| May 13 | Begin landing page build | No waitlist capture surface = zero signups before May 24 | Web team / Agency |
| May 13 | Begin press kit assembly | Media embargo cannot be placed without assets | PR team / Surgence |
| May 14 | Paid media plan + budget submitted | Campaigns cannot be built without plan and budget approval | Media agency |
| May 14 | Creator brief + legal disclosure drafted | Wave 1 creator outreach starts May 15 | Legal + Surgence |
| May 15 | Wave 1 creator outreach (10 Tier 1) | Must post on May 24 launch day | Surgence |
| May 16 | Country-Edition card artwork to printer | Physical cards for pre-order. 8–12 week production. Already late. | Surgence + Fulfillment |
| May 17 | App Store submission deadline (hard) | 7-day Apple review buffer. No submission = no app on launch. | Product team |
| May 17 | Landing page QA complete | Must be live and tested before May 24 | Web team |
| May 18 | Press embargo placed with 10 journalists | Journalists need 6 days to write. Embargo lifts May 24. | PR team |
| May 18 | Email nurture sequence written | Day 0 email sends automatically at waitlist signup | Copywriter / CRM team |
| May 19 | Loyalty Dividend CRM data test | Must work with real FCB fan data before May 24 | Product + FCB Data |
| May 20 | Press kit finalized + distributed | Journalists need assets to write the story | PR team |
| May 20 | Paid media campaigns loaded + approved | Must be ready to launch simultaneously with May 24 announcement | Media agency |
| May 20 | Korea activation brief written | Local partner needs brief to start outreach | Surgence |
| May 20 | Analytics + attribution setup | No measurement = no optimization = no CAC model | Analytics / Growth team |
| May 20 | Crisis response playbook written | Must exist before launch. Cannot write during a crisis. | CMO + Legal |
| May 21 | OOH remnant inventory booked (minimum) | São Paulo + Mexico City minimum. June 11 World Cup opener target. | Media agency |
| May 21 | Discord / Culer Lane community setup | Owned community space for activated users post-World Cup | Community team |
| May 22 | Full launch readiness review | Go/No-Go gate. All items above must be green. | Walter + FCB + Surgence |
| May 23 | Go / No-Go decision | If 3+ critical items are red, push announcement to June 11. | FCB Leadership |
| Jun 11 | World Cup mechanics all live + tested | Country Boost, Win Bonus, MOTM, Bracket Game all must work on day 1 | Product + Surgence |
| Jul 19 | Post-World Cup retention plan built | August plan must be ready before World Cup ends | CMO / Surgence |
| Aug 1 | Monthly Culer Report — Edition 1 live | First retention content post-World Cup | Content team |
| Aug 2026 | TGE bridge narrative drafted | Phase 2 narrative begins. 'You earned cashback. Now earn ownership.' | Surgence Phase 2 team |

BOTTOM LINE FOR EXECUTION

The strategy is sound. The World Cup window is right. The Loyalty Dividend is genuinely differentiated. The community architecture is more sophisticated than anything Nubank, Chime, or Tuyo deployed at Phase 1. None of that matters if the Surgence contract isn't signed today. Sign the contract. Brief the brand identity sprint. Everything else follows.

FC Barcelona Banc · Phase 1 Updated Marketing Plan · May 10, 2026 · Prepared by Surgence Labs · CONFIDENTIAL — Not for external distribution

14  FCB DELIVERABLES & CONTRACT STATUS

What FCB must deliver for Phase 1 to launch. Updated May 2026.

Contract Status Tracker

| Contract | Counterparties | Status | Effective Date | Key Gates |
| --- | --- | --- | --- | --- |
| Surgence Services Agreement (MSA) | Surgence Labs ↔ Barça Banc | ⚠️ IN PROGRESS — countersignature pending | May 4, 2026 | Phase 1 all workstreams; $20K/mo ×3 |
| CCLA (Content & Commercial Licence) | FCB ↔ Barça Banc | ⚠️ IN PROGRESS — Schedule 1 redline Apr 29 | TBD (target pre-May 24) | Instagram Stories, X bio, Telegram, all language accounts |
| TLA v5 (Token Launch Agreement) | FCB ↔ Surgence ↔ Barça Banc | ✅ SIGNED | Signed 2026 | TGE hard deadline Aug 31, 2026 |
| Rain FinTech (card issuer) | Rain ↔ Barça Banc | ⚠️ IN PROGRESS | TBD | Visa card issuance; KYC; 4 LatAm markets |
| Bridge (fiat rails / USDC) | Bridge ↔ Barça Banc | ⚠️ IN PROGRESS | TBD | Cross-border FX; Brazil BCB 561 exposure |
| FCB Player Access (Schedule B) | FCB ↔ Surgence | ❌ MISSING — amendment not circulated | Target Jul 1, 2026 | Hero video; player social posts; shoot window Jul–Dec |
| Per-market legal counsel | 4 firms: BR/MX/AR/CO | ❌ MISSING — firms not appointed | Required before launch | BACEN, CNBV, BCRA, SFC advertising compliance |

FCB Channel & Marketing Deliverables

What FCB must grant or configure before May 24. Source: CCLA Schedule 1 + FCB 29 Action Items.

| Deliverable | Channel / Asset | Status | Owner @ FCB |
| --- | --- | --- | --- |
| Instagram Stories access | FCB Instagram (147M) | ⚠️ IN PROGRESS | FCB Social |
| Instagram feed post (pinned) | FCB Instagram (147M) | ⚠️ IN PROGRESS | FCB Social |
| X (Twitter) bio link | FCB X account | ❌ MISSING | FCB Social |
| X pinned post slot | FCB X account | ❌ MISSING | FCB Social |
| Telegram broadcast | FCB Telegram | ❌ MISSING | FCB Digital |
| WhatsApp broadcast (50M) | FCB WhatsApp | ⚠️ IN PROGRESS | FCB Digital |
| TikTok integration | FCB TikTok | ❌ MISSING | FCB Social |
| YouTube channel collab | FCB YouTube | ❌ MISSING | FCB Content |
| All-language account access | ES/PT/AR/CO language accounts | ❌ MISSING | FCB International |
| banc.fcbarcelona.com domain | Web — subdomain setup | ⚠️ IN PROGRESS | FCB Tech |
| Daily Player Drop assets | IG Stories May 25 onward | ❌ MISSING — brief not sent | FCB Media |
| Country-Edition Card imagery | 5K per country (4 markets) | ⚠️ IN PROGRESS | FCB Design / Leo |
| Loyalty Dividend CRM data | Tier 1 / 2 / 3 confirmation | ❌ MISSING | FCB Data |
| Player image rights (Phase 1) | Fiat-only marketing; no TGE | ⚠️ IN PROGRESS | FCB Legal |
| Stadium shoot access | Camp Nou for content creation | ❌ MISSING — Action Item #17 | FCB Operations |
| $BAR delistment confirmation | Exchange delistment | ❌ MISSING — Action Item #4 | FCB Legal |
| FCB POC designation | Content approval SLA | ❌ MISSING | FCB Marketing lead |
| CRM history for Loyalty Dividend | 7+ years supporter transaction data | ❌ MISSING | FCB Data |
| FCB board / WS2 go decision | Internal — gates all public comms | ⚠️ IN PROGRESS | FCB Leadership |
| App Store listing (FCB brand assets) | Apple App Store + Google Play | ❌ MISSING | FCB Brand / Leo |

FCB Must-Do Before May 24 — Critical Path

| # | Action | Hard Deadline | Risk if Missed |
| --- | --- | --- | --- |
| 1 | Countersign Surgence MSA + Schedule A | May 11 (TODAY) | All Phase 1 workstreams blocked. No agency work can begin. |
| 2 | FCB board / WS2 go-ahead | May 14 | Announcement cannot happen May 24. Full campaign slips minimum 2 weeks. |
| 3 | Delist $BAR from active exchanges | May 20 | Regulatory exposure. May 24 announcement creates market confusion. |
| 4 | Designate FCB POC (content approver) | May 12 | Content pipeline blocked. 5-day CCLA SLA cannot start. |
| 5 | Submit app to Apple App Store | May 17 (hard) | 7-day review window. Miss = app not live June 11. |
| 6 | Confirm CRM data tier (1/2/3) for Loyalty Dividend | May 15 | Loyalty Dividend quality degrades. Tier 3 = generic card = 70% less viral. |
| 7 | CCLA Schedule 1 countersigned | May 20 | No right to use FCB channels, player images, or branding on May 24. |
| 8 | Brief daily player drop asset pipeline | May 18 | 15-day content streak starts May 25. Miss brief = dead air at peak moment. |
| 9 | Appoint per-market legal counsel (BR/MX/AR/CO) | May 16 | Financial advertising compliance not cleared. Paid media cannot run. |

# Branding

Figma

https://www.figma.com/design/zKekn1GVRrynrsN38hJDHi/FCB-App?node-id=1253-3&t=xkdryFZ3JNwE8Ro6-1

# Competitors

Chime vs Nubank vs Tuyo vs Barça Banc — Marketing Activation Comparison

Reference for Barça Banc Phase 1–2 strategy  ·  Synthesis: May 2026

Strategic takeaway

Three playbooks, three philosophies. Chime spends to manufacture cultural presence Barça Banc already owns through the player roster, 167M+ owned reach, and 428M-fan base. Nubank engineered scarcity and word-of-mouth that Barça Banc can replicate exactly via the Peña network and Country-Edition Card mechanics. Tuyo shows what Phase 2 looks like when the product is fully crypto-native — and where Barça Banc's $FCB token must land once the fiat trust layer is established. The column added here surfaces how far Phase 1 planning has progressed against each dimension and where the critical gaps remain.

| Dimension | Chime | Nubank | Tuyo | Barça Banc |
| --- | --- | --- | --- | --- |
| Scale | ~38M customers (US only); $519.8M marketing spend in 2024 | 118.6M customers across Brazil, Mexico, Colombia; CAC ~$7 (as low as $0.80 at peak) | 50,000+ users (May 2026); founded 2024; 4.9/5.0 App Store rating | Phase 1 targets: 750K waitlist (18 days), 250–320K downloads, 90–115K activated cards, ~$1.0B Y1 transaction volume. Addressable: 428M global fans; 800M total FCB fanbase. Markets: Brazil, Mexico, Argentina, Colombia. Pre-revenue as of May 2026. |
| Core positioning | Anti-traditional bank: no hidden fees, get paid early, "financial progress, not perfection" | Anti-incumbent freedom: "Libertad" — purple card vs. grey legacy banks | Full financial sovereignty: "The era of asking permission to use your own money is over. Ditch your bank." | The financial product only FC Barcelona could build: a Visa card that turns fan loyalty into compounding rewards. 'Barça Banc gives back to culers what years of supporting the club always deserved.' Additive, not corrective — never 'FCB finally paying you back.' Positioned vs. Revolut on identity, not features. |
| Emotional anchor | "You're making it" — validation of the paycheck-to-paycheck struggle | "Your choices take you forward" — possibility, rebellion, independence | Freedom and control — not community, not loyalty, not rewards | 'Your culer life, rewarded' — celebrates culer identity; orients forward (every match earns) not backward. 'Celebratory, not corrective.' Pride travels; grievance does not (Andrew, May 7 2026). Concrete over abstract: specific numbers (€336, 12 years) do the emotional work. |
| Target audience | Gen Z / millennials; Black & Hispanic communities over-indexed; underbanked | LatAm mass market; varies by country (Brazil rebellion, Mexico inclusion, Colombia aspiration) | Crypto-native users seeking self-custody + everyday spending; assumes user knows USDC, Base, airdrops | Primary: FCB fans 18–45, LatAm (BR/MX/AR/CO); web2-native, not crypto-native; bank account or mobile payments; not investors. Secondary: unbanked/underbanked young fans — high mobile penetration, existing FCB brand trust. Phase 1 explicitly excludes crypto-adjacent segment (Phase 2 only). |
| Acquisition engine | Paid media + cultural sponsorships + experiential stunts | Word-of-mouth (80–90% of acquisition); invite-only scarcity; gamified referral | Pure organic — viral X posts of free purchases; airdrop hunters; founder-led PR | Peña network seeding (community anchors) + Loyalty Dividend viral mechanic + waitlist scarcity + FCB owned channels (167M+ reach). Daily Player Drop from May 25. Surgence groundwork: 30 FB group admins, Reddit sleeper agents, WhatsApp seeding. CAC could approach $0 via owned channels — unproven. |
| Marketing-to-revenue ratio | Very high — $519.8M on a fintech still scaling | Very low — NPS 90 + referrals do the work paid media usually does | Effectively zero paid — BNPM "spends" on absorbing transactions instead of ads | Pre-revenue. Surgence retainer: $20K/month Phase 1. No paid media budget documented — the plan assumes FCB owned channels absorb distribution cost. Biggest risk: if organic reach underdelivers, no paid media fallback is planned. |
| OOH strategy | Moment-based stunts (MyPay vault, Times Square DOOH); 600+ placements per launch | Moment-based stunts (Sphere Las Vegas — 100M particle faces); no always-on billboards | None — no OOH, no billboards, no transit | Not in Phase 1 plan — identified gap. No OOH budget, format, or timeline documented. The Country-Edition Card and Loyalty Dividend card are designed to be photographed and shared, but no physical OOH activation planned. |
| OOH philosophy | "The billboard IS the content" — designed to be filmed for TikTok | "The billboard IS the PR moment" — designed to be picked up by NYT, Bloomberg, CNN | N/A — the transaction itself is the content; X screenshots replace billboards | Gap — undefined. If added: the launch-day Camp Nou event or country activation moments could function as OOH stunts designed for social photography. No current plan for this format. |
| Influencer model | 3-tier: FinTok always-on / A-list cultural anchors (Kai Cenat, Deion Sanders, Becky Lynch, Cooper Flagg) / affiliate program | 2-track: mid-tier always-on creators (Gusta, Manu Gavassi) + one celebrity anchor (Anitta, 2022–25) | No ambassadors, no influencers, no celebrities — peer-to-peer referral only | Two tracks: (1) Community anchors — Peña presidents, 30 Facebook group admins, Reddit power-users (Surgence-seeded); (2) Player broadcast layer — Lamine Yamal, Raphinha, Pedri via FCB owned channels. Gap: no always-on mid-tier creator brief between campaign moments. |
| Celebrity stance | Embraces A-list talent across sports, music, streaming, comedy | Publicly anti-celebrity — but used Anitta heavily for cultural moments | Founder IS the celebrity — Jorge Izquierdo (Aragon, EIP-1271) carries Ethereum-native credibility | Players ARE the celebrities (Lamine, Raphinha, Pedri) — but accessed through FCB's owned channels, not individual Barça Banc ambassador deals. Zero separate talent fee. No individual player deal structure documented for Barça Banc specifically. |
| Cross-cultural mix | NFL coach + WWE champion + Twitch streamer + #1 NBA pick in same campaign | Single cultural anchor (Anitta) + niche mid-tier roster | Single archetype — crypto-native sovereignty, no cultural variation | Country-specific player associations planned (Brazil→Raphinha). Market-specific messaging NOT defined — identified as a gap. Current plan treats LatAm as one block. Nubank ran distinct positioning per country; Barça Banc has not. |
| Sponsorship strategy | Member-benefit layer on every deal: Chime Lane (Mavs), WrestleMania access, Cooper Flagg ambassador | Selective and PR-driven: FIFA World Cup 2022, Netflix × Wednesday creative co-production | None — no sports, music, or cultural sponsorships | Inverse model: Barça Banc IS a sub-brand of FCB, not a sponsor of anything. FCB provides identity anchor, players, Camp Nou, social reach. Barça Banc provides the financial product. Country-Edition Cards (5K, national colors) function as the 'sponsored product' equivalent. |
| Flagship sponsorship | Dallas Mavericks jersey patch — $33M / 3 years, framed internally as "serialized social content platform" | Netflix × Wednesday — co-created character "Littlefoot," not a media buy | N/A | None — relationship is inverted. Camp Nou seat draw (62 seats per match, points-based) is the closest equivalent to Chime's Chime Lane mechanic: sponsorship value converted into a tangible member benefit. |
| Experiential signature | MyPay Vault Tour — 7-city semi-truck vault, Kai Cenat livestream; 155M+ views | Sphere Las Vegas — 100M customer faces in purple particles; 700+ editorial mentions, 3M+ YouTube views | "Buy Now, Pay Maybe" — every transaction is potentially the experience; viral on X May 7, 2026 | Country-Edition Card (5K per country, national colors, pre-order opens May 24). Camp Nou VIP seat draw (62 seats per match, points-based entry). Country Boost Days during World Cup (3× points when country scores). Win Bonus (FCB win = bonus points). No physical event activation planned. |
| Owned cultural tentpole | Financial Progress Month (April) — invented and owns it; everything ladders to it | Carnaval (Anitta-led Ensaios & Blocos) + FIFA World Cup; co-opted, not invented | Seasonal multiplier drops (4× → 3× → 2× → 1×) function as repeatable launch moments | World Cup window (Jun 11–Jul 19) is the Phase 1 tentpole — a natural one, not invented. La Liga Final Day (May 24) is the launch anchor. Key difference from Chime: Barça Banc does not own these moments — they borrow from football's calendar. Risk if World Cup underperforms commercially. |
| Original content | "Mama I Made It" YouTube series; "Ball on a Budget" WNBA series | "Nu-Libertade" cinematic shorts; Netflix character integration | Permissionless Podcast appearance; founder X threads as content | Daily Player Drop (Instagram Stories priority, from May 25 — one player per day). Loyalty Dividend shareable card (landscape format, one-tap share to X and WhatsApp). Gap: no YouTube series, no documentary, no podcast content planned for Phase 1. |
| Hero campaign | "$1 Million Bet" / Pay Progress Forward (Wayne Brady) — 375M impressions, 115M views, Ad Age Breakout Brand 2024 | "With Nu, your choices take you forward" — 500M+ impressions; "Nu-Libertade" drove 35% AUM rise in Q1 2025 | "Buy Now, Pay Maybe" — most talked-about fintech launch of the week (May 2026); zero paid media | Loyalty Dividend — personalized card showing lifetime FCB spend vs. cashback earned. 'Your culer life, rewarded.' Sample: '12 years a culer. €4,200 of love. Earn it back, every match.' Three data tiers: Tier 1 (real CRM data), Tier 2 (estimated), Tier 3 (self-reported quiz fallback). Launches May 24. |
| Hero campaign mechanic | Product mechanic IS the campaign — social experiment proves the brand mission | Cinematic emotion — banking chains dissolving into purple mist | Variable reinforcement — slot-machine logic on everyday purchases; uncertainty IS the feature | Personal financial data made shareable — same mechanic as ETHGas (590K shares) and ORBT DeFi Score (70K shares). The culer's years + spend figure makes their devotion legible; the Dividend orients forward. Pride in fandom is the share driver. WhatsApp group chats and pre-game threads are the primary distribution surface. |
| Streaming/TV mix | Heavy — Hulu, Peacock, Tubi, Fubo, broadcast TV, YouTube, TikTok | Lighter — TV used selectively; emphasis on social and earned | None — X-only distribution | Not planned. FIFA broadcast deal is in the critical path for brand visibility in match broadcasts — not paid ad slots. No streaming advertising budget documented. Gap vs. Chime's Hulu/Peacock model for reaching LatAm diaspora audiences in the US. |
| Web3 / crypto | Explicitly anti-crypto. CEO publicly opposes pushing crypto on vulnerable customers. No roadmap. | Stealth crypto. Nucoin loyalty token on Polygon — 13.2M users in 8 months; never marketed as crypto | Aggressively crypto-native. USDC on Base, self-custodial, full Web3 vocabulary, TUYO TGE in 2026 | Phase 1: 100% fiat, zero crypto. Prohibited vocabulary in all consumer-facing material: crypto, token, stablecoin, wallet, web3, on-chain, DeFi, blockchain — even in player scripts and influencer briefs. Phase 2: $FCB token via same infrastructure (stealth flip — same Nucoin model, no UX disruption). |
| Token / loyalty mechanic | No token; cashback via Visa interchange model | Nucoin (Polygon) — free distribution to 70M users; 13.2M activated in 8 months as "rewards," not crypto | TUYO seasonal points (4× → 3× → 2× → 1×) — 20% of supply to community at TGE | Phase 1: FCB Rewards Points (fiat) — earned via card spending, Matchday Bonus, Win Bonus, Country Boost. Phase 2: $FCB token (stealth upgrade from points — Nucoin model; users earn token without knowing). Gap: no seasonal multiplier design documented for Phase 2 pre-TGE period. |
| Referral program | Affiliate: up to $75 per successful referral, 30-day cookie | Gamified queue — priority access for referrers; quality scored, not just volume | 20% of referral's ongoing TUYOs forever (not one-time) + 4× boost for new joiners' first 72 hrs | Queue jump: 500 positions per referral; queue position visible; country-first waves create urgency; hard-side seeding before May 24. Gap: referral mechanic ends at activation — no ongoing earn share for referrers after card activation. Tuyo's 20% ongoing model is stronger post-activation. |
| Trust-building tactic | Community education partnerships (For Oak Cliff, First Tech Fund); Workday B2B distribution | NPS 90 as acquisition infrastructure; customer support resolutions made public on social | Founder pedigree — Ethereum since 2016, EIP-1271 author, Aragon track record | Pre-existing 428M-fan emotional trust — no other neobank starts here; FCB brand does the trust work before Barça Banc exists. Loyalty Dividend demonstrates value before the card is live. Peña network as community anchors ('trusted friend invited you' at group scale). Gap: no educational content layer; no NPS-to-referral infrastructure. |
| Distribution innovation | Workday Wellness integration — B2B acquisition channel reducing CAC | Pix education — taught Brazil how to use the rails, became #1 originator | Airdrop aggregator SEO — airdrops.io, AirdropBee, third-party guides drive organic signups | Peña network — structured physical/social fan communities unique to football culture; no fintech competitor has equivalent. WhatsApp-first distribution (primary LatAm channel, underused by fintech competitors). FCB owned channels: 147M Instagram, 50M WhatsApp broadcast, banc.fcbarcelona.com. |
| What they don't do | Always-on national billboards; transit/airport signage; competitor attacks | Stadium naming, festival sponsorships, podcast originals, branch banking, direct competitor attacks | OOH, TV, celebrity deals, sports sponsorships, Meta ads, traditional PR | OOH. Podcast advertising. Traditional financial advertising. Crypto/token language. Grievance framing ('FCB finally paying you back'). 'Finally' (implies club was wrong). Hype language ('revolutionary', 'groundbreaking'). Corporate finance vocabulary (APR, FX spread, basis points). Celebrity deals separate from FCB relationship. |
| Greatest strength | Cultural omnipresence — every Gen Z touchpoint (sports, wrestling, streaming, finance education) covered | Capital efficiency — NPS 90 means the product markets itself; sub-$1 CAC at peak | CAC reframed as product feature — BNPM converts every transaction into potential earned media | Pre-existing emotional trust from 428M fans + players as influencer tier no competitor can replicate + World Cup as a free cultural tentpole + FCB owned channels (167M+ reach) = structural CAC advantage no competitor has. 'What Nubank had to build from scratch, Barça Banc inherits.' |
| Greatest weakness | High burn — $519.8M annual marketing spend is unsustainable without IPO economics | Concentration risk — Anitta's defection to Mercado Pago (April 2025) showed the cost of a single celebrity anchor | Audience ceiling — vocabulary and self-custody assume crypto literacy; won't convert Web2 users | Dependency stack with fixed launch date: CRM data tier, FIFA broadcast deal, Surgence entity decision all unresolved as of May 10. No market-specific messaging per country. No CS capacity plan. No paid media fallback if organic reach underdelivers. Phase 2 vocabulary shift (fiat→crypto) is the biggest brand challenge. |
| Most replicable for Barça Banc | Owned cultural tentpole (Financial Progress Month → World Cup window Jun 11–Jul 19) | Invite-only scarcity + gamified referral (waitlist + queue jump + Country-Edition Cards) | Phase 2: TUYO-style seasonal multiplier season design pre-TGE; Phase 1: BNPM-style "transaction-is-the-content" logic for Loyalty Dividend | Already designed from comparators: Nubank invite-only scarcity + gamified referral (waitlist + queue jump); Nubank Nucoin stealth model ($FCB Phase 2); Chime's event-as-content logic (Loyalty Dividend card). Still missing: Chime's market-specific messaging per country; Nubank's NPS-to-referral infrastructure; Tuyo's ongoing referral earn share post-activation. |

Chime · Nubank · Tuyo · Barça Banc  ·  Marketing Activation Comparison  ·  May 2026

# Competitors: Nubank

NUBANK

Marketing Activation Playbook

Research reference for Barça Banc Phase 1 Launch
 Synthesis: May 2026  ·  Sources: 12 publications

Scale Reference

| Metric | Figure |
| --- | --- |
| Total customers (Q1 2025) | 118.6M |
| Brazil | 104.6M |
| Mexico | 11M |
| Colombia | 3M |
| Net new customers in 2024 | 20.4M |
| Customer acquisition cost | ~$7 (2023–25); as low as $0.8 at peak efficiency |
| NPS (Brazil) | 90 (industry gold standard: 50–70) |
| Word-of-mouth share of all acquisition | 80–90% |

1 · The Invite-Only Growth Engine (2014–2017)

Nubank's earliest and most powerful acquisition mechanic was artificial scarcity:

·       Credit card was invite-only from day one

·       New members entered via referral from existing users

·       The waitlist was gamified: users who referred friends got priority access

·       The referrer got social status; the referee got access to something exclusive

Result: 350,000 credit card customers in ~1 year, almost entirely from referrals. CAC under $5.

Why It Worked

·       Scarcity created desire in a market where most people expected to be rejected by banks

·       Being invited meant you were 'selected' — a powerful inversion of banking's exclusion dynamic

·       Social proof: your friend trusted Nubank enough to invite you, so you trusted it too

·       Referral quality was tracked and rewarded — one high-quality referral > five weak ones

For Barça Banc: The fan community inverts this further. FCB fans already trust the club. The scarcity mechanic (waitlist + queue jump + country-first waves) creates FOMO inside fan communities. Peña-anchored seeding replicates the 'trusted friend invited you' dynamic at group scale.

2 · The Purple Card as Cultural Artifact

The purple card's virality was both organic and engineered.

What Was Organic

·       Users photographed their purple cards at checkout because it looked unlike any other card

·       Social media amplification happened with zero Nubank instigation

·       "I have a Nubank card" became shorthand for "I'm not getting ripped off by legacy banks"

What Was Engineered

·       The "roxinho" (vibrant purple) was a deliberate contrast to corporate blues and reds of incumbents

·       Invite scarcity made the card rare enough to photograph and share

·       Nubank Ultravioleta (metallic purple) took the status symbol upmarket as the base scaled

Cultural Dynamic

In Brazil, carrying a purple card signalled financial independence and membership in a new generation. The card became a badge before it became a utility object.

For Barça Banc: A blue-and-garnet Visa card with the club crest is already a cultural artifact — it signals 'I'm a culer.' Country-Edition Cards (national colors, 5K per country) add the same scarcity dynamic Nubank used with Ultravioleta. Key question: what does it mean to carry this card in front of someone who doesn't have one?

3 · Nucoin Launch (2023) — 13M Users in 8 Months

Nubank launched Nucoin as a loyalty/rewards token on Polygon. The marketing approach is the most directly relevant precedent for the $FCB token (Phase 2).

| Metric | Figure |
| --- | --- |
| Target base | 70M existing Nubank customers |
| Announced | October 2022 |
| Launched | March 1, 2023 |
| Registered users (November 2023) | 13.2M (18.8% of base) |

How They Did It

·       Positioning: rewards program, not crypto speculation — blockchain language was never the lead message

·       Co-design: 2,000 customers in a discussion group before launch became the first advocates

·       Zero cost barrier: Nucoin distributed free to all 70M customers; earned via engagement, not purchase

·       Utility first: discounts, exclusive content, community access; Coinbase listing was not the pitch

Key insight: Nubank users earned Nucoin without knowing or caring it was a blockchain token. The stealth crypto approach is exactly what Phase 1 of Barça Banc replicates — FCB Rewards Points are fiat, but the infrastructure exists to flip to $FCB in Phase 2 with no UX disruption.

4 · Campaign Examples

"With Nu, your choices take you forward" (2024–25)

·       Omnichannel: social, television, OOH

·       Authentic mid-tier influencers (500K–5M followers): Gusta, Manu Gavassi, Pedro Otoni, Jacira, Aline Diniz

·       500M+ impressions

·       Messaging: forward-looking, possibilities-focused — no feature lists

"Nu-Libertade" — Freedom Campaign (early 2025)

·       Cinematic short films: traditional banking chains dissolving into purple mist

·       Triggered a 35% rise in AUM in Q1 2025

·       Emotional anchor: "Libertad" (freedom) for the LatAm consumer

Netflix × Wednesday Collaboration (July 2025)

·       Co-created character "Littlefoot" inspired by Wednesday Addams

·       Entertainment storytelling merged with product promotion

·       Extended reach beyond Nubank's existing audience via Netflix distribution

Pix Adoption Campaign (2020–2022)

·       Invested in educational content to teach Brazilians how to use Pix (Brazil's instant payment system)

·       Became the top Pix originator by 2022

·       Turned a product feature into a public education initiative — built trust, positioned as expert

What They Did NOT Do

·       No direct attacks on competitor banks

·       No celebrity-only campaigns

·       No feature-first advertising

·       No crypto/blockchain language in the Nucoin launch

5 · NPS as Acquisition Infrastructure

Nubank treats NPS as a growth metric, not a satisfaction metric.

Product experience → NPS 90 → 85% loyalty rate → passive sharing → active referral → community advocacy

Active NPS Mechanics

·       In-app surveys after key moments (first transaction, first support interaction)

·       Detractor conversion: fast-response resolution → detractors turned into promoters

·       Promoter activation: in-app invite prompts at peak satisfaction moments

·       Visible referral tracking: users saw how many friends they'd invited, creating friendly competition

Customer Support as Marketing

·       Known for responsive, empathetic support

·       Public resolution of complaints on social media = visible brand virtue

·       Nubank support interactions became shareworthy moments — a resolved problem got retweeted

6 · Market-Specific LatAm Tactics

| Market | Pain Point | Messaging Angle | Key Tactics |
| --- | --- | --- | --- |
| Brazil | $100+/year in fees + 300%+ APR credit cards | Freedom, anti-establishment, 'we're on your side' | CDI auto-investment; Pix #1 adopter; cultural rebellion framing |
| Mexico | Cash-heavy, large unbanked population, low digital trust | Pragmatic inclusion (NOT rebellion) | Cuenta Nu 13% yield; mobile recharge integration; customizable virtual cards |
| Colombia | Emerging middle class, limited product options | Premium positioning, financial education | Nu CDT savings certificates; Nu Plus gamified savings; education content platform |

Cross-market universal truth: Anti-bank sentiment resonates everywhere, but the expression must be locally adapted. Brazil = rebellion. Mexico = inclusion. Colombia = aspiration.

7 · What Nubank Did Not Have (That Barça Banc Has)

| Nubank Started With… | Barça Banc Starts With… |
| --- | --- |
| Had to build trust from scratch | Inherits 428M fans' pre-existing emotional trust |
| Had to create desire for a new product category | Fans already desire the club; card is the access mechanism |
| Had to find influencers to advocate | Has the actual players (Lamine, Raphinha, Pedri) |
| Had to manufacture cultural identity (purple card) | Cultural identity already exists (Barça crest, blue-garnet) |
| CAC $5–7 per customer | CAC could approach $0 through owned channels (FCB social 167M+ reach) |
| Took 5+ years to reach 100M | 750K waitlist in 18 days is the stated Phase 1 target |

8 · Directly Replicable Mechanics for Phase 1

| Nubank Mechanic | Barça Banc Equivalent | Status |
| --- | --- | --- |
| Invite-only scarcity | Waitlist + queue jump + country-first waves | Designed |
| Gamified referral | Queue position visible + 500 positions per referral | Designed |
| Purple card as cultural artifact | Country-Edition Cards (5K per country, national colors) | Designed |
| NPS-driven word of mouth | Target NPS >80 via product excellence + culer identity | Not yet measured |
| Influencer-community mix (authentic, mid-tier) | Peña presidents, Reddit power-users, FB group admins | Designed — Surgence scope |
| Market-specific messaging | Brazil (pride), Mexico (community), Argentina (identity), Colombia (aspiration) | GAP — not in any current doc |
| Anti-bank positioning without direct attack | Revolut-competitive messaging anchored in FCB brand trust | Underdeveloped |
| Loyalty token stealth launch (Nucoin) | $FCB token via Phase 2 (FCB Rewards Points in Phase 1) | Phase 2 only |
| 2,000 co-design community members | Hard-side seeding before May 24 | Designed |
| Educational content as trust-builder | Not in current plan | GAP |

9 · Key Gaps Relative to the Nubank Playbook

Gap 1: Market-specific positioning per country

Current plan treats LatAm as one block. Nubank adapted messaging per market. Brazil ≠ Mexico ≠ Argentina ≠ Colombia.

Gap 2: Anti-incumbent contrast

Nubank made "purple card vs. grey bank card" a cultural statement. Barça Banc hasn't defined what it means to carry this card in front of someone who has a Bradesco card.

Gap 3: Educational content layer

Nubank won in Mexico by teaching digital banking before selling. Barça Banc's onboarding content strategy is not defined.

Gap 4: NPS infrastructure

Nubank built explicit systems to convert NPS into referrals. No equivalent in the current Phase 1 plan.

Gap 5: Support-as-marketing

Nubank's CS was a marketing channel. No customer support capacity plan exists for Barça Banc launch day.

10 · Channel Activation Deep Dive

How Nubank actually executed across paid, earned, and experiential channels — based on campaign-level research beyond the brand strategy layer.

Out-of-Home (OOH)

·       No evidence of a sustained, permanent billboard program — Nubank uses high-impact moment-based OOH, not always-on outdoor

·       Sphere Las Vegas / Exosphere (May 2024) — their biggest OOH moment. World's largest LED screen (112m high, 157m wide). 100 million purple particles formed the faces of their first customers to mark the 100M milestone. Ran May 7–14. Followed by local OOH activations in Brazil, Mexico, and Colombia.

·       Selective OOH around major product launches and the FIFA World Cup

The Sphere activation was engineered as a PR stunt first, OOH second — the visual was inherently press-worthy. Result: 700+ editorial mentions (NYT, Forbes, Bloomberg, CNN) and 3M+ YouTube views. The OOH spend generated multiples in earned media value.

Influencer Program

Two tracks running simultaneously — mid-tier creators for always-on content, one celebrity anchor for milestone moments.

| Track | Tier / Role | Detail |
| --- | --- | --- |
| Always-on creators | Mid-tier (500K–5M followers) | Finance, lifestyle, entertainment niches. Names: Gusta, Manu Gavassi, Pedro Otoni, Jacira, Aline Diniz. No celebrity brief — purely aspirational, no feature lists. |
| Anitta (celebrity anchor) | Board member → Global Brand Ambassador | Board 2021–2022. Ambassador from Aug 2022. Campaigns: FIFA World Cup 2022; Carnaval 2023 (Modo Rua + phone insurance — activated her own Ensaios and Blocos across Brazil). Left to Mercado Pago April 2025. |
| CMO hire (2025) | Kim Farrell — ex-TikTok Global Head of Creators | Signals the creator program is scaling into a structured, platform-native operation. Responsible for global brand architecture and creator partnerships going forward. |

Key tension: Nubank publicly positioned against celebrity marketing, yet Anitta was their most visible face for 3 years. The resolution: Anitta was used for milestone moments and carnival/World Cup culture events, not product feature ads. Mid-tier creators carried the always-on load.

Experiential & Events

| Activation | Market | Mechanic | Result |
| --- | --- | --- | --- |
| Sphere / Exosphere, Las Vegas | Global (press hook) | 100M particle faces of first customers on world's largest LED screen | 700+ press mentions, 3M+ YouTube views, stock surpassed Itaú |
| Anitta Carnaval Ensaios & Blocos | Brazil | Anitta took Nubank messaging into her own carnival street blocks — Modo Rua + phone insurance; live audiences of tens of thousands | Mass reach at peak cultural moment; no media buy required |
| Pop-ups & community kiosks | Mexico, Colombia | Physical financial education and trust-building in markets where digital alone underperforms | Offline conversion tool; specific results not published |
| Large experiential events | Brazil (institutional / older cohorts) | High-production events to reach demographics less responsive to digital | Complement to hyper-personalized digital paid media |

Sponsorships

| Property | Year | Format | Notes |
| --- | --- | --- | --- |
| FIFA World Cup | 2022 | Regional sponsor | Anitta was the face of the World Cup campaign across all markets |
| Netflix × Wednesday | 2025 | Creative co-production | Co-created character 'Littlefoot'; not a media buy — a creative partnership extending reach via Netflix's audience |
| Anitta | 2022–2025 | Celebrity ambassador + equity | Originally joined the board with equity stake; became ambassador after board exit; defected to Mercado Pago April 2025 publicly jabbing Nubank on exit |

No evidence of: stadium naming rights, club shirt sponsorship, music festival activations, podcast original content.

PR as Activation Channel

·       Customer support resolutions shared publicly on social = engineered earned media moments

·       100M milestone campaign generated editorial coverage equivalent to a large paid media buy — without the paid media budget. The Sphere was designed to be photographed and published.

·       Anitta's defection to Mercado Pago (April 2025) generated more press coverage of Nubank than most of their paid campaigns — a reminder that brand relationships are PR assets

Channels They Did Not Use

·       Stadium naming rights

·       Music festival sponsorships

·       Podcast original content (none documented)

·       Traditional bank advertising formats (branch signage, bank statement inserts, financial advisor networks)

·       Direct competitor attack advertising

Nubank Marketing Activation Playbook  ·  Barça Banc Research  ·  May 2026

# Competitors: Chime

CHIME

Marketing Activation Playbook

Research reference for Barça Banc Phase 1 Launch
 Channel-level deep dive: OOH, Influencers, Experiential, Sponsorships  ·  May 2026

Scale Reference

| Metric | Figure |
| --- | --- |
| Total customers (2024) | ~38M+ |
| Marketing spend (2024) | $519.8M (15% YoY increase; revenue grew 30%) |
| Primary markets | United States only |
| Core audience | Gen Z, millennials; Black and Hispanic communities over-indexed |
| Positioning | Anti-traditional bank: no hidden fees, early direct deposit, fee-free overdraft |
| Revenue model | Interchange fees — incentive to drive card spend, not fee revenue |
| IPO status | Filed S-1 2025; valuation ~$25B |

1 · Brand Strategy & Positioning

Chime's entire marketing machine is built on one insight: most Americans are one unexpected expense away from a fee spiral. Traditional banks profit from that vulnerability. Chime does not. Every activation, sponsorship, and influencer brief flows from that single positioning.

| Element | Detail |
| --- | --- |
| Core promise | Banking that works for you — no hidden fees, get paid early, build credit without debt |
| Emotional anchor | Financial progress, not financial perfection. 'You're making it.' |
| Tone | Warm, validating, community-rooted. Never condescending. Never traditional bank. |
| Target | Paycheck-to-paycheck Americans, Gen Z and millennials, underbanked communities |
| Villain | The two-week pay cycle, overdraft fees, minimum balance requirements |
| CMO quote (Vineet Mehra) | "From FinTok to WrestleMania, we're meeting consumers where they are." |

2 · Out-of-Home (OOH)

Chime uses OOH as a launch amplifier tied to product moments — not always-on brand presence.

MyPay Campaign — Labor Day 2024

·       600+ OOH placements nationwide for the MyPay (early wage access) product launch

·       High-impact DOOH in New York City: Times Square, Penn Station, Lincoln Tunnel

·       Digital billboard at National Harbor, MD — geolocated product demo on the screen

·       Messaging: 'Why do we work every day but wait two weeks to get paid?' — question format, no product push

·       Hyperlocal executions: ads showing how local Chime members in specific neighborhoods are reaching goals

OOH strategy: Chime doesn't use billboards as brand wallpaper. They use them as media stunts — the billboard IS the content, then gets photographed and reshared on social. The National Harbor digital billboard activation was designed to generate a TikTok, not just impressions.

What They Don't Do

·       No always-on national billboard program

·       No transit wraps or airport signage documented

·       OOH only appears around major product launches or cultural moment campaigns

3 · Influencer Program

Chime runs a three-tier influencer model: FinTok creators for always-on reach, A-list cultural talent for campaign moments, and an affiliate program for performance.

Tier 1: FinTok / Personal Finance Creators (Always-On)

·       Finance bloggers, YouTube personal finance creators, FinTok accounts

·       Authentic testimonials — product demos, 'how I use Chime' formats

·       Brief: real-world financial progress stories, not feature lists

·       Partnered with FinTok creators for Financial Progress Month (April 2025)

Tier 2: A-List Cultural Talent (Campaign Anchors)

| Talent | Category | Campaign | Why They Fit |
| --- | --- | --- | --- |
| Kai Cenat | Twitch / TikTok creator (#1 most influential creator, Rolling Stone) | MyPay tour (2024); 'You're Making It' TV spot (2025) | Massive Gen Z reach; authentic street-level energy; live-streaming audience |
| Fanum | Streamer / creator | MyPay nationwide vault tour (2024) | Kai Cenat's creative partner; AMP community reach |
| Deion Sanders ('Coach Prime') | NFL HOF / University of Colorado head coach | 'You're Making It' TV spot (2025) — plays 'Coach Chime' | Multi-generational appeal; coaching = validation framing; Black community icon |
| Becky Lynch | 7× WWE Champion | 'You're Making It' TV spot (2025) | WrestleMania sponsorship tie-in; female empowerment angle; cross-sport reach |
| Cooper Flagg | #1 NBA Draft Pick 2025, Dallas Mavericks | 'Mama I Made It' YouTube series; multi-year ambassador | First-ever multi-year Chime athlete ambassador; youth + sports crossover |
| WNBA stars (Arike Ogunbowale, Lexie Brown, Chelsea Gray, Kamilla Cardoso) | Professional basketball | Ball on a Budget series (2024) | Fashion-meets-finance angle; WNBA cultural moment; female audience |

Tier 3: Affiliate Program

·       Open affiliate program: up to $75 per successful referral

·       30-day cookie duration

·       Open to bloggers, influencers, personal finance content creators

·       Performance-based — scales with creator output, no upfront guarantee

Chime's influencer mix is deliberately cross-cultural and cross-format: a Twitch streamer, an NFL coach, a WWE champion, and a #1 NBA draft pick in the same campaign. The through-line is 'making it' — financial progress as a cultural value, not a product feature.

4 · Experiential & Events

Chime's experiential strategy converts product launches and cultural moments into physical, shareable events.

MyPay Vault Tour — September 2024 (Flagship Activation)

·       Concept: a semi-truck-sized vault representing $340B trapped in the two-week pay cycle

·       7-part cross-country series: NYC (Flatiron Plaza launch) → Philadelphia → Houston → Phoenix → San Francisco

·       Talent: Kai Cenat and Fanum hosted each stop; 10-crew production team

·       Finale: Fanum literally blew up the vault — captured in 6K with five cameras, live-streamed by Kai Cenat to 14.7M followers

·       Sweepstakes: $500K in equivalent pay unlocked across the tour; 1M+ sweepstakes entries

·       Results: 155M+ views across all content; campaign drove MyPay product sign-ups nationwide

The vault tour is the clearest example of Chime's experiential model: the event IS the content. The physical activation existed to generate the TikTok. There was no separation between the event and the media — Kai's live-stream was the media buy.

Ball on a Budget — WNBA 2024

·       Concept: WNBA stars create tunnel-worthy fits for under $300 — athletic style + financial savvy

·       Talent: Arike Ogunbowale, Lexie Brown, Chelsea Gray, Kamilla Cardoso

·       Production partner: SLAM Magazine and WSLAM (LeagueFits Instagram — leading NBA/WNBA fashion platform)

·       Event elements: VIP party, pop-up tunnel walk, vintage shopping, on-site t-shirt customization, Money Moves panel

·       Results: 55.2M views (124% increase vs. prior NBA season version); 222K+ social engagements

·       Recognition: Shorty Awards nomination; first consumer brand to spotlight WNBA fashion culture at scale

Chime Lane — American Airlines Center (Ongoing)

·       Dedicated member entrance at Dallas Mavericks games at American Airlines Center

·       Perks: Hangar gift cards, free soft drinks and popcorn, limited-edition giveaway items at select events

·       Extended to WrestleMania 41 (Las Vegas, April 2025) — first WrestleMania sponsorship

·       Model: turns the sponsorship from a logo placement into a product benefit — members feel the value at the door

5 · Sponsorships

| Property | Deal | Value / Term | Activation Layer |
| --- | --- | --- | --- |
| Dallas Mavericks (NBA) | Jersey patch sponsor — renewed May 2025 | $33M / 3 years | Chime Lane at AAC; Cooper Flagg ambassador deal; 'serialized social content' strategy through Mavs games |
| Cooper Flagg (Dallas Mavericks) | Multi-year brand ambassador — first athlete on this basis for Chime | Undisclosed | 'Mama I Made It' YouTube series; social content; product tie-ins; first-ever multi-year athlete partner |
| WNBA | Content partnership via Ball on a Budget series | Undisclosed | SLAM/WSLAM production; 4 WNBA stars; social series + physical event |
| WWE WrestleMania 41 | Official financial services partner | Undisclosed | Chime Lane access at the event; Becky Lynch brand tie-in; TikTok sweepstakes campaign |

Chime's sponsorship model: they don't just buy logo placements. Every sponsorship has a product activation layer (Chime Lane, early access, member perks) that makes the sponsorship feel like a member benefit, not a media buy. The Dallas Mavericks deal was described internally as a 'serialized social content' platform, not a jersey patch.

6 · TV & Paid Media

'You're Making It' — TV Spot (April 2025)

·       Prime-time TV spot for Financial Progress Month (April)

·       Talent: Deion Sanders, Becky Lynch, Kai Cenat, Josue De Paz (Chime Changemaker / First Tech Fund)

·       Deion plays 'Coach Chime' — validation and encouragement framing, not product features

·       FinTok trend integration: 'loud budgeting' and 'girl math' referenced in the spot

·       Distribution: TV + all brand channels + talent social amplification simultaneously

MyPay Campaign — Omnichannel (Sept 2024)

·       600+ OOH placements + DOOH in NYC + prime-time TV + digital display + paid social + influencer + experiential tour — all running the same message simultaneously

·       Single question as the hook across every channel: 'Why do we work every day but wait two weeks to get paid?'

·       Funnel: all channels pointed to one action — sign up for Chime, enable direct deposit, get MyPay

Paid Media Scale

·       $519.8M marketing spend in 2024 — one of the highest marketing-to-revenue ratios in US fintech

·       Revenue grew ~30% in 2024 vs. 15% marketing spend growth — improving efficiency

·       Media mix: digital (Instagram, TikTok, YouTube), TV, OOH, experiential, influencer, affiliate

7 · Original Content

'Mama I Made It' — YouTube Series

·       Original YouTube series built around the emotional 'financial progress' positioning

·       Format: talent shares their journey with a parent figure — milestone moments, financial wins

·       Cooper Flagg debuted in the series alongside his mother Kelly Flagg (first episode after signing)

·       Distribution: YouTube primary; Instagram Reels clips for social

·       Purpose: depth content that builds brand affinity beyond the 30-second ad unit

Ball on a Budget — Social Series

·       Multi-episode social content series with WNBA stars (not a one-off campaign)

·       Each episode: one player, one outfit, under $300 budget — financial savvy + fashion credibility

·       Distribution: SLAM/WSLAM Instagram (LeagueFits) + Chime channels + player channels

·       Framing: finance education through culture, not through financial advice

8 · Financial Progress Month (April) — Owned Tentpole

Chime has built a proprietary annual cultural moment: Financial Progress Month (April). Every major activation, TV spot, sponsorship, and influencer brief in Q2 ladders up to this frame.

·       Annual TV spot launch (April 1 each year) — 'You're Making It' in 2025

·       FinTok creator partnerships activated for the month

·       WrestleMania 41 (April 2025) — Chime Lane + Becky Lynch tie-in — timed to Financial Progress Month

·       In-app financial education content and challenges for existing members

·       Press and earned media hook: financial wellness data, 'making it' cultural moment angle

This is the most directly replicable mechanic for Barça Banc: an owned cultural tentpole that isn't a bank holiday or a brand anniversary — it's a theme the brand created and owns. Barça Banc could own the World Cup window the same way Chime owns April.

9 · Applicability to Barça Banc

| Chime Mechanic | Barça Banc Equivalent | Notes |
| --- | --- | --- |
| Financial Progress Month (owned tentpole) | World Cup window (Jun 11–Jul 19) as the owned cultural moment | Barça Banc has a bigger natural moment — the World Cup already exists. Chime had to invent April. |
| Vault tour — event IS the content | Peña activations + country launch events designed to generate social content | Gap: current plan doesn't specify event-as-content design for country launches |
| Chime Lane — sponsorship as member benefit | Camp Nou Access / Country-Edition Card as member benefit layers inside FCB events | Designed — closest analog is the Camp Nou seat draw mechanic |
| Cross-cultural talent roster (HOF athlete + WWE + streamer in same spot) | Lamine + Raphinha + Pedri — players already are the cross-cultural talent roster | Barça Banc has this built in; doesn't need to assemble it |
| FinTok creator tier (always-on finance content) | Football finance / LatAm personal finance creators (not documented in current plan) | GAP — no creator brief for always-on content between campaign moments |
| Omnichannel message unity (one question, all channels) | Loyalty Dividend number as the single hook across all channels | Designed — Loyalty Dividend is the equivalent of 'Why do we wait two weeks?' |
| 'Mama I Made It' original YouTube series | Player + fan documentary format for YouTube / FCB TV | GAP — no original content series planned for Phase 1 |
| OOH as media stunt (designed to be photographed and reshared) | Country-Edition Card unboxing + launch day activations | Partial — card is shareable by design but no OOH stunt planned |

Chime Marketing Activation Playbook  ·  Barça Banc Research  ·  May 2026

# Competitors: Tuyo

TUYO

Launch & Marketing Activation Research

Research reference for Barça Banc Phase 1–2 strategy
 Competitive intelligence: crypto-native neobank launch playbook  ·  May 2026

Company Snapshot

| Attribute | Detail |
| --- | --- |
| Full name | Tuyo (handle: @itstuyo) |
| Founded | 2024 |
| Cofounders | Jorge Izquierdo (CEO) — co-founder of Aragon, author of EIP-1271, Ethereum contributor since 2016 Alejandro Perezpayá — ex-Allfunds (acquihire), head of digital product |
| Product | Self-custodial crypto neobank: Visa debit card spending USDC on Base network + yield vaults + global transfers |
| Blockchain | Base (Coinbase L2) |
| Stablecoin | USDC |
| Card network | Visa — 140M+ / 175M merchants worldwide |
| Markets | United States, EU, Latin America |
| Users (May 2026) | 50,000+ |
| App Store rating | 4.9 / 5.0 (iOS, as of December 2025) |
| TGE | Confirmed for 2026 — 20% of total token supply earmarked for community |
| Tagline | "Buy Now, Pay Maybe" |

2 · Launch Timeline

| Date | Event |
| --- | --- |
| May 2024 | The Block reveals Tuyo — Aragon co-founder Jorge Izquierdo announces self-custodial wallet project; targets App Store launch post-summer 2024 |
| Late 2024 (December) | Tuyo Card launched globally — Jorge tweets: 'Today we're launching Tuyo Card globally. For close to a decade, I've dreamed about using only crypto in my daily life.' iOS first; Android to follow. |
| Nov 1, 2025 → Dec 11, 2025 | Season 0 closes (Pioneer phase); Season 1 (Early Adopters) begins with 3× TUYO multiplier |
| Dec 11, 2025 → Jan 22, 2026 | Season 2 (FOMO) — 2× multiplier |
| Jan 22, 2026 → TGE | Season 3 (Stacking/Last Call) — 1× baseline multiplier; users urged to accumulate before TGE |
| May 7, 2026 | 'Buy Now, Pay Maybe' announced — went viral on X; 50,000+ users confirmed; most talked-about fintech launch of the week |
| 2026 (TGE pending) | Token Generation Event — TUYO token launch on Base; 20% supply to community based on accumulated points |

3 · Product Overview

| Feature | Detail |
| --- | --- |
| Card type | Prepaid Visa debit card; funds held in USDC on Base |
| Self-custody | Full self-custody — users control keys; Tuyo cannot access funds |
| Spending limit | Up to $200,000 per day |
| Annual fee | Zero |
| Yield | Earn vaults — additional yield on USDC holdings, paid daily |
| Global transfers | Send money globally, instantly, for free |
| Account numbers | USD and EUR account numbers for receiving local payments in each region |
| Apple Pay | Supported |
| Android | Google Play available |
| Onboarding | Described by reviewers as 'best onboarding in crypto' — fast USDC funding, smooth KYC |
| 'Buy Now, Pay Maybe' | Algorithm randomly absorbs purchase cost — no published probability; purchases in $5–$100 range reported free on X |

4 · Web3 / Token Positioning

Tuyo is the opposite of Barça Banc Phase 1 — it is explicitly, loudly, and unapologetically crypto-native. This is not a Phase 2 pivot; it is the product from day one.

| Element | Detail |
| --- | --- |
| Core architecture | USDC on Base — every transaction is on-chain, self-custodial |
| Token | TUYO — launching on Base; 20% of supply to community via airdrop |
| Vocabulary | Full web3 vocabulary in all consumer-facing material: self-custodial, on-chain, USDC, Base, airdrop, TGE, yield vaults |
| Positioning vs. banks | "The era of asking permission to use your own money is over." / "Ditch your bank." |
| Founder framing | "When I started working on Ethereum in 2016, we imagined a world where crypto would feel like trad money." — Jorge Izquierdo |
| Primary audience | Crypto-native users seeking self-custody + everyday spending; not web2 converts |
| Anti-bank tone | Aggressive — unlike Nubank and Chime, Tuyo directly frames banks as the enemy |

For Barça Banc: Tuyo is the Phase 2 competitive reference, not Phase 1. When Barça Banc launches $FCB token, Tuyo's self-custodial + USDC architecture is what the crypto-native audience will compare it to. The key difference: Tuyo targets existing crypto users; Barça Banc Phase 2 targets FCB fans being introduced to crypto for the first time.

5 · Headline Marketing Mechanic — 'Buy Now, Pay Maybe'

BNPM is simultaneously Tuyo's product hook, acquisition mechanic, and viral distribution engine. It launched on May 7, 2026 and generated more earned media than any paid campaign could have achieved.

How It Works

·       Every time a user pays with the Tuyo card, the purchase might be free — no published probability, no merchant tier, no minimum spend

·       An algorithm determines which transactions are absorbed by Tuyo

·       Users in the $5–$100 range have been the most common free-purchase reports on X (coffees, dinners, grocery runs)

·       No guarantee language in legal terms: 'Tuyo makes no promise, representation, warranty, or guarantee that any particular transaction, or any transaction at all, will receive the BNPM benefit'

Why It Went Viral

·       The mechanic self-distributes: users who get a free purchase immediately post about it on X — social proof at zero cost

·       The uncertainty is the feature: like a slot machine, variable reinforcement is more compelling than guaranteed cashback

·       'Buy Now, Pay Maybe' is a one-line pitch that is instantly understood and instantly shareable

·       It reframes CAC as a product feature: instead of $40 in Google Ads per acquisition, Tuyo 'spends' $40 by absorbing a coffee — but gets the post, the trust, and the referral along with it

Critical Reception

·       GamblingHarm.org: 'Buy Now, Pay Maybe Turns Your Coffee Into A Slot Machine' — gambling mechanics applied to everyday spending

·       Cameron Mattis (X): highlighted the legal disclaimer that Tuyo makes no guarantee any transaction will ever be free

·       View from the Wing: 'This New Card Sometimes Earns 100% Cash Back — But Might Never Pay You A Dime'

·       Despite criticism, the controversy itself generated additional coverage and awareness

The BNPM mechanic is the most creative CAC-reduction play in consumer fintech in 2026. Whether it's ethical is a separate question — as a distribution mechanism, it converts every transaction into a potential earned media moment. The Loyalty Dividend works on similar logic: a shareable financial-data moment that users post because it says something about them.

6 · TUYO Rewards Program — Stealth Airdrop Mechanic

Before any token launch, Tuyo ran a points accumulation program across four seasons. This is the closest analog to Nubank's Nucoin launch — points earned through behavior, redeemable for token at TGE. 50,000+ participants enrolled.

How to Earn TUYOs

| Activity | Mechanic |
| --- | --- |
| Card spending | TUYOs earned per dollar spent with the Tuyo Visa card |
| Trading | TUYOs earned per trade executed on the platform |
| Earn vaults | Additional TUYOs on top of yield from Earn strategies; paid daily |
| Referrals | 20% of all TUYOs earned by referred users, ongoing |

Seasonal Multiplier Structure

| Season | Period | Multiplier | Label |
| --- | --- | --- | --- |
| Season 0 | Launch → November 1, 2025 | 4× | Pioneers — retroactive rewards for early users + 48-hour launch boost |
| Season 1 | Nov 1 – Dec 11, 2025 | 3× | Early Adopters |
| Season 2 | Dec 11, 2025 – Jan 22, 2026 | 2× | FOMO |
| Season 3 | Jan 22, 2026 → TGE | 1× (baseline) | Stacking Season / Last Call |

TGE / Airdrop Structure

·       20% of total TUYO token supply earmarked for community distribution

·       Allocation based on accumulated TUYO points — more points = larger airdrop share

·       Token launches on Base network

·       Tuyo has not publicly confirmed exact TGE date as of May 2026

The seasonal multiplier structure is behaviorally sophisticated: early adopters get 4× the points, creating urgency to join early and stay active. Each season drop (4× → 3× → 2× → 1×) triggers another wave of signups from users who see the multiplier window closing. This is the mechanic Barça Banc should study for $FCB Phase 2 — not just the token, but the pre-TGE points accumulation season design.

7 · Distribution & Marketing Channels

Tuyo's marketing is almost entirely organic and community-driven. No documented OOH, TV, or traditional paid media.

X (Twitter / CT) — Primary Channel

·       @itstuyo — active on X; primary announcement channel for all product launches and updates

·       Jorge Izquierdo (@izqui9) — cofounder's personal X account used for founder-led marketing; Ethereum credibility backstory

·       Crypto Twitter (CT) community seeding — the BNPM launch went viral organically on X within hours of the May 7 announcement

·       New referral boost announced via X: '4x the TUYOs for using the app' — social-first mechanic

·       Tuyo's core distribution is X posts by users sharing free purchase screenshots — earned media loop

Podcast — Crypto Media

·       Permissionless Podcast — Jorge Izquierdo appearance: 'building borderless, self-custodial banking for everyone'

·       Permissionless is one of the highest-reach crypto podcasts; appearance = crypto community credibility

·       No mainstream podcast or finance podcast presence documented

Founder-Led PR

·       Jorge Izquierdo's X thread on launch day ('Today we're launching Tuyo Card globally') — personal narrative, not corporate press release

·       Ethereum/Aragon pedigree used as trust signal with the crypto-native audience — 'I've been working on this since 2016'

·       The Block coverage (May 2024 reveal) — credibility in crypto media from day one

Airdrop Aggregators & Crypto Media

·       Airdrops.io, AirdropBee — TUYO listed as potential airdrop; generates organic sign-ups from airdrop-hunting community

·       CoinCodeCap, CoinLive, Meme-Insider, CryptoCardHub — review coverage driving SEO and discovery

·       The TUYO rewards page architecture is designed for airdrop-hunter SEO — 'how to be eligible' pages indexed on third-party sites

Referral Program

·       20% of referral's ongoing TUYOs — not a one-time bonus; incentivizes sustained engagement from referrers

·       New user referral boost: 4× TUYOs for first 72 hours after joining with referral code

·       No documented ambassador or influencer tier — referral is peer-to-peer only

What They Are NOT Doing

·       No OOH / billboard advertising

·       No TV or streaming advertising

·       No celebrity ambassador deals

·       No sports sponsorships

·       No Facebook / Instagram advertising documented

·       No traditional PR / press release distribution (founder X posts replace press releases)

8 · Positioning & Brand Voice

| Axis | Tuyo |
| --- | --- |
| Core promise | Full financial sovereignty — your money, your keys, your rules |
| Anti-bank tone | Aggressive: 'The era of asking permission to use your own money is over.' 'Ditch your bank.' |
| Audience assumption | User already knows what USDC, Base, and self-custody mean |
| Vocabulary | Self-custodial, on-chain, USDC, Base, airdrop, TGE, yield vaults, DeFi |
| Emotional anchor | Freedom and control — not community, not loyalty, not rewards |
| Trust signal | Cofounder's Ethereum history (2016), EIP-1271 authorship, Aragon track record |
| Geography | Borderless by design — US, EU, LatAm from launch |
| Launch tagline | "Crypto shouldn't be so painful, it's time to start over" |

9 · Press Coverage & Reception

Positive / Neutral Coverage

| Outlet | Coverage |
| --- | --- |
| The Block | Reveal (May 2024): 'Aragon co-founder reveals self-custodial crypto wallet designed to keep things simple' |
| Neobanque.ch | BNPM launch: 'most talked-about product launch of the week'; called the one-line pitch 'brilliant' |
| View from the Wing | 'This New Card Sometimes Earns 100% Cash Back' — intrigued but skeptical tone; high-reach travel/finance audience |
| CoinCodeCap | 'Most innovative crypto card of 2026'; praised smooth onboarding, self-custody, DeFi yield |
| CryptoCardHub | Card review: positive on limits, zero fees, global availability |
| Meme-Insider | TUYO token breakdown: utility, airdrop timeline, card explained |
| Airdrops.io / AirdropBee | Tuyo listed as eligible airdrop; community guides on how to accumulate TUYOs |

Critical Coverage

·       GamblingHarm.org: framed BNPM as slot-machine gambling mechanics applied to everyday purchases

·       Cameron Mattis (X): called out the legal disclaimer — Tuyo guarantees nothing about BNPM

·       OnlineThreatAlerts: 'Tuyo Buy Now Pay Maybe App and Debit Card — How Does it Work' — fact-check tone, skeptical

·       The Blaze: 'Debit card company promises to pay your bill ... sometimes' — skeptical framing for mainstream audience

The critical coverage has so far helped Tuyo more than it has hurt. GamblingHarm.org and The Blaze reaching audiences who had never heard of Tuyo is net-positive awareness. The product is controversial enough to generate press; that press drives downloads.

10 · Applicability to Barça Banc

Tuyo is not a Phase 1 competitor — it's a Phase 2 reference and a partial Phase 2 threat.

| Tuyo Mechanic | Barça Banc Equivalent / Gap | Phase |
| --- | --- | --- |
| TUYO seasonal points program (4× → 3× → 2× → 1×) | FCB Rewards Points in Phase 1 are the behavioral infrastructure; the multiplier season design is the Phase 2 layer to add pre-TGE | Phase 2 |
| BNPM — CAC reframed as product feature | Loyalty Dividend — historical spend reframed as forward-earning opportunity. Same logic: financial data moment = shareable content = acquisition | Phase 1 |
| Referral: 20% of referral's ongoing points (not one-time) | Barça Banc referral: 500 queue positions. Gap: no ongoing earn share for referrers after activation | Phase 1 gap |
| Founder-led marketing (Jorge's personal X as primary PR channel) | Walter / Maurits / FCB players as the equivalent — but player content is managed, not founder-authentic | Phase 1 |
| Crypto-native vocabulary, no apology | Phase 1: prohibited. Phase 2: required. The vocabulary flip is the biggest brand challenge in the Phase 1 → Phase 2 transition | Phase 2 |
| Self-custody positioning (your keys, your money) | No equivalent in Phase 1 or Phase 2 current plan — Barça Banc is custodial | Not applicable |
| Airdrop aggregator SEO (airdrops.io, third-party guides) | Phase 2 only — TGE airdrop community will self-organize; Barça Banc should plan for it | Phase 2 |
| No OOH, no TV, no celebrities — pure community distribution | Barça Banc has celebrity assets (players) that Tuyo does not — this is an advantage, not a gap | Phase 1 |

Tuyo Launch & Marketing Research  ·  Barça Banc Competitive Intelligence  ·  May 2026

# PR competitors

PR Campaign Analysis

Nubank  ·  Chime  ·  Tuyo

Comparative earned media, press relations, crisis communications, and PR architecture
 Research reference for Barça Banc  ·  May 2026

Overview — PR Architecture at a Glance

| Dimension | Nubank | Chime | Tuyo |
| --- | --- | --- | --- |
| PR model | Milestone-anchored + CS-as-PR | Culturally engineered earned moments | Founder-led / organic CT seeding |
| Primary press hook | Scale milestones (100M, IPO, ReclameAQUI) | Social experiment campaigns ($1M Bet) | Product virality (BNPM) + controversy |
| Press office | Formal — international.nubank.com.br/newsroom | Formal — chime.com/newsroom | None — @izqui9 X posts replace press releases |
| Key media targets | Bloomberg, Reuters, FT, Exame, Valor | Ad Age, TechCrunch, Forbes, Campaign US | The Block, CoinDesk, crypto review sites |
| Crisis documented | Brasil Paralelo (June 2024); Anitta exit (Apr 2025) | None documented at scale | GamblingHarm controversy (May 2026) |
| Founder as PR asset | David Vélez — TIME 100, Stanford GSB, TED talks | Chris Britt — functional, not media-forward | Jorge Izquierdo — Ethereum pedigree, X-native |
| Awards used for PR | ReclameAQUI (8× consecutive), TIME, Best Brand | Ad Age Breakout Brand, Shorty Awards | None yet |
| CS as PR | Yes — formal strategy, ReclameAQUI evidence | Partial — MyPay campaign implied | No CS documented |

1 · Nubank PR Campaign Analysis

Nubank treats PR as a system, not a campaign. Every customer service interaction, every milestone, and every product launch is designed to generate press — not through a PR agency pitching journalists, but through proof points so strong that journalists come to them.

1.1 · Milestone PR — Engineered News Moments

| Milestone | PR Mechanic | Coverage Generated |
| --- | --- | --- |
| NYSE IPO (December 2021) | $45B valuation on day one; David Vélez letter to employees published as open letter; 'return to mission' narrative post-IPO | Bloomberg, Reuters, WSJ, FT, CNBC; framed as LatAm fintech coming-of-age story |
| 100 Million Customers (May 2024) | Sphere Las Vegas activation (May 7–14) + HQ celebration event (May 15) with press + content creators from Brazil, Colombia, Mexico; David Vélez interview series all week | 700+ press mentions — NYT, Forbes, Bloomberg, CNN; stock surpassed Itaú (largest bank in LatAm by market cap) |
| 10th Anniversary (June 2023) | Opened Nubank HQ to press and influencers; announced Jornal Nacional partnership (Brazil's most-watched news programme) with Wieden+Kennedy; David Vélez keynote on 10-year journey | Major Brazilian financial press; Crowdfund Insider; multiple fintech trade outlets |
| First digital bank outside Asia to reach 100M | Framing device used in all international press — the 'first' label made the milestone globally newsworthy, not just LatAm | International financial media amplified because the 'first' frame gave non-LatAm journalists a reason to cover it |

1.2 · Customer Service as PR Infrastructure

·       ReclameAQUI Award: won 8 consecutive years — the most trusted Brazilian consumer complaint platform; lowest complaint rate among the 15 largest financial institutions in Brazil (Q3 2024)

·       RA1000 Seal (highest tier): >90% customer satisfaction on resolutions; used in all investor and press materials

·       Special awards: 'Super Champion Company' and 'Champion Customer Service Team' (2023)

·       Fast-resolution stories published on X and Instagram: every resolved complaint becomes a proof point, not just a support ticket

·       TechCrunch EC1 feature (2021): 'How Nubank's CX strategy made it one of the most loved digital banks' — organic long-form press from CS excellence

The ReclameAQUI strategy is the most replicable model for Barça Banc: winning a third-party award for customer service generates more trust than any paid campaign. It also gives press a credible, verifiable claim to cite. No equivalent award target exists in the current Phase 1 plan.

1.3 · Founder as Permanent PR Asset

·       David Vélez — TIME magazine 100 Most Influential People; Stanford GSB profiled alumnus; regular TED/conference speaker

·       'Infinite game' narrative: after every milestone, Vélez publicly frames it as the beginning, not the destination — keeps the story alive post-announcement

·       Planned philanthropy: widely covered intention to give away majority of wealth (Gates Pledge equivalent) — generates positive coverage without any campaign cost

·       Cristina Junqueira (co-founder) — Brazilian media circuit presence; also the source of the 2024 crisis (see below)

1.4 · Content PR — 'Fala, Nubank' Blog

·       Nubank operates a financial literacy blog ('Fala, Nubank') generating millions of monthly unique visitors in Brazil

·       Topical authority in personal finance: positions Nubank as a trusted expert, not just a bank — press cite Nubank data in their own articles

·       Financial education content generates organic backlinks and third-party citations = PR without outreach

1.5 · Crisis Management — Brasil Paralelo (June 2024)

The most significant PR crisis in Nubank's history — and how they managed it reveals the limits of their PR model.

·       Trigger: co-founder Cristina Junqueira posted on Instagram thanking Brasil Paralelo (a Brazilian content company demonetized by the Superior Electoral Court for spreading disinformation) for an invitation to a Jordan Peterson lecture

·       Reaction: immediate wave of negative comments on X; customer cancellation threats; Nubank stock fell 1.18% end of day; internal employee social network also showed discontent

·       Response: CEO David Vélez stated the post 'does not violate our Code of Conduct' and 'does not support any content nor point of view' — distancing without disciplining Junqueira

·       Outcome: Nubank cut ties with Brasil Paralelo; Junqueira left the Políticos Ranking website board (which had Brasil Paralelo as a supporter); crisis subsided without lasting brand damage

·       Lesson: the crisis was person-generated, not product-generated — the brand's NPS cushion absorbed the blow; most customers did not cancel

1.6 · Anitta Exit — PR Moment for Competitor (April 2025)

·       Anitta left Nubank for Mercado Pago in April 2025, publicly jabbing Nubank: 'My old relationship wasn't paying off'

·       Generated significant press — Bloomberg covered it; Brazilian media widely covered

·       Nubank did not publicly respond — silence was the correct tactical decision (engaging would amplify)

·       Net effect: more awareness of both brands from a talent story than from any campaign either had run recently

2 · Chime PR Campaign Analysis

Chime's PR approach is more deliberate and agency-driven than Nubank's. They engineer 'earned moments' — campaigns that look organic but are constructed to generate press and social pickup. The '$1 Million Bet' is the clearest example: the experiment WAS the press release.

2.1 · The '$1 Million Bet' — Best-in-Class PR-as-Campaign (September 2024)

·       Agency: AKQA

·       Concept: social experiment — 10 participants facing financial setbacks, each offered double their needed sum on the condition that half would choose to share it with strangers, unlocking a $1M prize if they all paid forward

·       Talent: Wayne Brady — used his own documented financial hardship ('All I needed was $56 and didn't have it') to make the vulnerability real and authentic

·       Distribution: hero film + paid media seeding + Wayne Brady's own channels

| Metric | Result |
| --- | --- |
| Total impressions | 375 million |
| Video views | 115 million |
| Brand sentiment lift | 15% increase in 'cares about its customers' metric vs. prior year |
| Awards | Ad Age 2024 Breakout Brand Work Winner |
| Benchmark | Outperformed ALL previous Chime activations |

The $1 Million Bet worked because the experiment proved the brand's mission — it didn't just claim that Chime cares about people; it created a situation where ordinary people demonstrated generosity on camera. The brand was the facilitator, not the hero. This is the PR model Barça Banc should study: design activations that prove the mission, not just communicate it.

2.2 · Q1 Earned Moments — The Engineered Organic Playbook

Chime's internal team describes a Q1 strategy of building 'earned marketing moments' — culturally timed activations designed to generate press and social pickup without relying on paid distribution.

| Campaign | Period | Mechanic | Coverage |
| --- | --- | --- | --- |
| Manifest Money Candle | January–February | Custom-scented candle + manifestation guide; partnered with Apotheke (bespoke candle brand) and Maria Concha (mindset coach); tapped into existing audience language on social | One of Chime's best-performing campaigns; exact press count not published |
| Halftime Wedding | Valentine's Day (February 13) | Real couple married at Dallas Mavericks game; $7,000 Chime gift; couples' interview series; 'Love Don't Cost A Thing' Spotify playlist; 20+ local Dallas influencers | 20+ media publication pickups; broadcast news coverage |
| Ball on a Budget (NBA version) | March (NBA pre-season) | 4 NBA players styling $300 tunnel outfits; partnered with SLAM Magazine; GQ, Highsnobiety coverage | 9+ headlines; 25M+ views; ranked among Chime's best earned moments |

2.3 · Creator-Led Earned Media — 37 Creators in 2024

Chime's creator strategy is explicitly designed to generate earned media through cultural relevance, not product features.

| Creator | Category | Views | Why They Fit |
| --- | --- | --- | --- |
| Marshawn Lynch | NFL legend / cultural icon | 62.7M | Authentic money story; Black community icon; anti-corporate energy aligned with Chime positioning |
| Reesa Teesa | Viral storyteller ('Who TF Did I Marry?') | 13.7M | Peaked virally during period; audience overlap with Chime's underserved demographic |
| Jools Lebron | TikTok / 'Very demure' creator | 10.7M | Gen Z cultural moment; 'demure' framing applied to financial behavior = shareable content |
| Kai Cenat | Twitch / TikTok (#1 Rolling Stone) | 155M+ (MyPay tour) | Largest creator reach in the portfolio; Gen Z primary; live-streaming audience |

The pattern: Chime activates creators at their cultural peak moment (Reesa Teesa while she was still trending, Jools Lebron while 'demure' was everywhere) rather than signing long-term deals. Speed-to-cultural-moment is the competitive advantage — not the depth of any single relationship.

2.4 · IPO as PR Moment (May–June 2025)

·       S-1 public filing (May 13, 2025): TechCrunch headline revealed the $33M Dallas Mavericks deal publicly for the first time — the S-1 itself was the press moment

·       Banks: Morgan Stanley, Goldman Sachs, JP Morgan — names carry their own PR weight with financial press

·       IPO pricing: $27/share on June 12, 2025 — $11B valuation (down from 2021 peak of $25B but still a successful public offering)

·       Press framing: first major US neobank IPO; profitability ($12.9M net income Q1 2025) made the story more credible than expected

·       Board connection: Cynthia Marshall (ex-Dallas Mavericks CEO) on Chime board — journalists noted the Mavericks sponsorship originated from a board relationship

2.5 · Shorty Awards — Third-Party Validation PR

·       Ball on a Budget submitted and recognized at Shorty Awards — used in press materials and recruitment content

·       MyPay campaign submitted to Shorty Awards

·       Strategy: award submissions generate a second wave of press coverage (the win announcement) beyond the original campaign launch

2.6 · Crisis Comms — No Documented Incident at Scale

·       No major public crisis found in 2023–2025 research

·       Historical note: Chime faced regulatory issues in 2021 (FTC investigation into account closures; settled) — predates this research window

·       IPO S-1 revealed: $25M net loss in 2024, down from $203M in 2023 — managed proactively in press with profitability-trajectory narrative

3 · Tuyo PR Campaign Analysis

Tuyo has no formal PR operation. The founder's X account IS the press office. All announcements, narratives, and responses flow through @izqui9 and @itstuyo. This is not a gap — it is a deliberate model that matches their crypto-native audience's expectation of founder transparency.

3.1 · Launch PR — The Block Reveal (May 2024)

·       First public mention: The Block article — 'Aragon co-founder reveals self-custodial crypto wallet designed to keep things simple'

·       The Block is the highest-credibility crypto journalism outlet; placement there immediately signalled that Tuyo was a serious project, not a memecoin

·       Mechanic: Jorge Izquierdo gave The Block the exclusive reveal — classic embargo strategy, but executed in crypto media instead of mainstream finance media

·       The Aragon/Ethereum background did the PR heavy lifting: 'co-founder of Aragon' is a trust signal inside CT that no press release could manufacture

3.2 · Card Launch — Founder X Thread (December 2024)

·       Jorge Izquierdo posted a personal X thread: 'Today we're launching Tuyo Card globally. For close to a decade, I've dreamed about using only crypto in my daily life.'

·       The thread was personal, not corporate — no product specs, no feature lists; pure narrative of a decade-long vision becoming real

·       This thread = launch event, press release, and brand campaign simultaneously

·       Format: crypto founders are expected to post personally; a corporate press release would have undermined the self-custody credibility

3.3 · Permissionless Podcast — Earned Crypto Media

·       Jorge Izquierdo appeared on Permissionless Podcast: 'building borderless, self-custodial banking for everyone'

·       Permissionless is one of the highest-reach shows in crypto media; appearance = implied endorsement from a respected distribution channel

·       Topic: origins of Tuyo + what's next for consumer crypto — positioned Tuyo within a broader narrative of crypto going mainstream

·       No fee documented — earned placement based on founder credentials and product novelty

3.4 · 'Buy Now, Pay Maybe' Viral PR Moment (May 7, 2026)

The BNPM launch generated more press in 72 hours than the prior 18 months of Tuyo's existence combined.

| Outlet | Tone | Key Angle |
| --- | --- | --- |
| Neobanque.ch | Positive | 'Most talked-about product launch of the week'; called the pitch 'brilliant' |
| View from the Wing | Skeptical / intrigued | 'This New Card Sometimes Earns 100% Cash Back — But Might Never Pay You A Dime' — high-reach travel finance audience |
| GamblingHarm.org | Critical | 'Buy Now, Pay Maybe Turns Your Coffee Into A Slot Machine' — slot machine / variable reinforcement framing |
| OnlineThreatAlerts | Skeptical | Fact-check framing — highlighted the legal disclaimer's lack of guarantees |
| The Blaze | Skeptical | Mainstream conservative audience; 'Debit card company promises to pay your bill ... sometimes' |
| Cameron Mattis (X) | Critical | Viral X post screenshotting the legal terms — no guarantee language highlighted |
| CoinCodeCap | Positive | 'Most innovative crypto card of 2026'; praised onboarding and self-custody |
| Cryptonoshi / CryptoCardHub | Neutral-positive | Card review format; pros and cons; reached airdrop-hunting audience |
| Airdrops.io / AirdropBee | Neutral | Airdrop eligibility guides — structured as SEO content for people searching 'Tuyo airdrop' |

The critical coverage (GamblingHarm, Cameron Mattis) functioned as amplification, not damage control. GamblingHarm.org reaching audiences who had never heard of Tuyo is net-positive awareness for a product with 50K users. The controversy is the distribution mechanism: people who disagree with the mechanic still tell their network about it.

3.5 · Airdrop Aggregators as Earned PR Channel

·       Airdrops.io, AirdropBee, and similar platforms publish 'how to be eligible' guides for TUYO — written by third parties, not Tuyo

·       This content reaches a specific audience (airdrop hunters) who sign up specifically to accumulate points before TGE

·       Tuyo does not pay for this coverage — it is incentivized by the structure of the rewards program itself

·       Equivalent to SEO — the product mechanics generate the press, not the press team

3.6 · No Crisis Documented — But BNPM Is a Latent Risk

·       No reputational crisis documented as of May 2026

·       BNPM legal terms (no guarantee of any free purchase ever occurring) are the latent risk: if no user receives a free purchase over an extended period, the mechanic fails as a trust signal and could trigger regulatory scrutiny

·       GamblingHarm.org coverage is an early indicator — if a regulator picks up the 'slot machine' framing, Tuyo faces a compliance PR challenge

·       No documented crisis response playbook or spokesperson beyond Jorge Izquierdo

4 · Comparative Analysis — PR Mechanics Side by Side

| PR Mechanic | Nubank | Chime | Tuyo |
| --- | --- | --- | --- |
| Milestone moments | Engineered around scale (100M, IPO, 10 yrs) with press events, Sphere activation, CEO interview series | IPO S-1 as press moment; ad awards as second-wave coverage | Card launch (Dec 2024); BNPM (May 2026) — no milestone structure yet |
| Earned media design | CS excellence → ReclameAQUI → press cites → proof loop | Social experiments ($1M Bet) + cultural timing (Halftime Wedding, Manifest Candle) | Product mechanic IS the earned media (BNPM posts = user-generated press) |
| Founder as PR | David Vélez: TIME 100, TED, Stanford — traditional media circuit | Chris Britt: functional CEO; not used as brand-facing PR asset | Jorge Izquierdo: X-native; personal threads replace press releases |
| Media targets | Bloomberg, Reuters, FT (international); Valor, Exame (Brazil) | Ad Age, Campaign US, TechCrunch, Forbes (US) | The Block, CoinDesk, crypto review sites; CT influencers |
| Crisis documented | Brasil Paralelo (Jun 2024): person-generated; managed with silence + distance; Anitta exit (Apr 2025): no response, correct call | None at scale in this window; historical FTC issue (2021) predates window | BNPM gambling framing (May 2026): early stage; no formal response yet |
| Awards / third-party validation | ReclameAQUI (8×), TIME, Best Brand Brazil — used proactively in press | Ad Age Breakout Brand, Shorty Awards — used for second-wave press cycle | None yet — too early |
| Press office structure | Formal; international.nubank.com.br/newsroom; multi-market PR teams | Formal; chime.com/newsroom; agencies (AKQA confirmed) | None — @izqui9 and @itstuyo X accounts are the press office |
| Tone of press relationship | Proof-point led: we show you the data, you write the story | Campaign-led: we create the moment, you cover the moment | Community-led: CT covers Tuyo because CT IS Tuyo's audience |

5 · Implications for Barça Banc PR

Barça Banc has assets none of the three comparators have — but also has gaps none of them faced.

| PR Mechanic | Barça Banc Status | Source Model | Gap / Action |
| --- | --- | --- | --- |
| Milestone announcement (May 24 launch) | Planned — La Liga final match day | Nubank 100M + Chime IPO | Press pack, media embargo, exclusive access for 3–5 tier-1 LatAm financial journalists needed before May 24 |
| Earned media designed into the product | Loyalty Dividend card = shareable moment | Nubank Sphere + Chime $1M Bet | Designed — but no 'experiment' hook; the number does the work. No press hook for journalists beyond the product itself |
| Founder / face of the brand as PR asset | No named founder; Walter as CMO | Nubank (David Vélez) / Tuyo (Jorge Izquierdo) | GAP — players are the media faces but are not CMO-level spokespeople; a named internal voice for press is absent |
| CS excellence as PR proof point | Not planned | Nubank ReclameAQUI | GAP — no customer support capacity plan; no third-party award target; launch-day support failure = first PR crisis |
| Crisis response playbook | Not documented | Nubank (Brasil Paralelo); Chime (FTC) | GAP — Phase 1 regulatory risk across 4 LatAm markets; no crisis comms plan visible in any current document |
| Third-party validation / awards | None targeted | Nubank (ReclameAQUI); Chime (Ad Age, Shorty) | GAP — identify LatAm fintech / banking award targets for Q3 2026 entry; builds press credibility in markets |
| Player content as press moment | Daily Player Drop planned | No direct comparator — unique asset | Advantage — Lamine / Raphinha / Pedri posts will generate sports media pickup that no fintech competitor can replicate |
| Crypto/token PR bridge (Phase 2) | Not planned (Phase 1 scope) | Tuyo (The Block, Permissionless) | Phase 2 gap — when $FCB launches, need a crypto media relationship already established; no equivalent of The Block embed yet |

PR Campaign Analysis: Nubank · Chime · Tuyo  ·  Barça Banc Research  ·  May 2026

# Budget

BUDGET & CAC MODEL — PHASE 1

Barça Banc · Wave 1 LatAm · June–July 2026  ·  Confidential · May 2026

A. Retainer & Agency Spend

| Line | Vendor | Rate | Months | Total |
| --- | --- | --- | --- | --- |
| Surgence Labs — Phase 1 retainer | Surgence Labs | $20,000/mo | 3 | $60,000 |
| Surgence Labs — Phase 2 retainer | Surgence Labs | $25,000/mo | 4 | $100,000 |
| Surgence Labs — Phase 2 token comp | Surgence Labs | 0.15% $FCB supply | — | TBD at TGE |
| Performance media agency | TBD | ~$8,000/mo | 3 | ~$24,000 |
| PR agency (Carlos + agency) | TBD | ~$6,000/mo | 3 | ~$18,000 |
| Influencer / creator agency | TBD | ~$5,000/mo + CPA | 3 | ~$15,000 + CPA |
| Localization (PT-BR, MX-ES, AR-ES, CO-ES) | Specialist | ~$3,000 setup + $1K/mo | 3 | ~$6,000 |
| ASO specialist | TBD | ~$2,500 setup | 1 | ~$2,500 |
| Legal counsel (4 markets × firm) | 4 local firms | ~$5,000 per market | — | ~$20,000 |
| Analytics / attribution setup | TBD | ~$2,000 setup + tooling | 1 | ~$5,000 |
| PHASE 1 AGENCY SUBTOTAL (excl. media spend) |  |  |  | ~$150,500 + token |

B. CAC Model by Market

Targets calibrated to Nubank BR ($8–12 early stage), Chime US ($35–55), Tuyo (crypto-native, ~$15). Barça brand reduces top-of-funnel cost vs. generic neobank.

| Market | Target Downloads | Target Cards | CAC Target | Media Budget | Organic % | Paid % | LTV Est. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Brazil 🇧🇷 | 120,000–150,000 | 40,000–50,000 | $8 | $320K–$400K | 60% | 40% | $85 |
| Mexico 🇲🇽 | 80,000–100,000 | 25,000–32,000 | $6 | $150K–$200K | 65% | 35% | $70 |
| Argentina 🇦🇷 | 30,000–40,000 | 12,000–18,000 | $4 | $48K–$72K | 70% | 30% | $45 |
| Colombia 🇨🇴 | 20,000–30,000 | 8,000–15,000 | $5 | $40K–$75K | 65% | 35% | $55 |
| TOTAL | 250,000–320,000 | 85,000–115,000 | $6.8 blended | $558K–$747K | — | — | $72 blended |

C. Paid Media Allocation (Phase 1 — 3 months)

Benchmark: Nubank spent ~20% of total CAC budget on Meta/Instagram in early LatAm growth. Chime: 3-tier influencer model ($1M Bet AKQA-driven). Tuyo: X-only cold-start.

| Channel | Allocation | Monthly Spend | Primary KPI | Benchmark |
| --- | --- | --- | --- | --- |
| Meta (Instagram + Facebook) | 35% | $65K–$87K/mo | App installs (LatAm) | Nubank primary channel |
| TikTok | 20% | $37K–$50K/mo | Waitlist sign-ups | Chime influencer amplifier |
| Google UAC (App campaigns) | 20% | $37K–$50K/mo | Organic search + installs | High-intent capture |
| YouTube pre-roll | 10% | $19K–$25K/mo | Brand awareness | Hero video distribution |
| Twitter/X | 5% | $9K–$12K/mo | CT community reach | Tuyo model — seed before amplify |
| Creator / Influencer CPA | 10% | $19K–$25K/mo | Referral downloads | Chime 3-tier model |
| TOTAL | 100% | $186K–$249K/mo | — | — |

D. Revenue & Payback Model

| Metric | Conservative | Base Case | Optimistic | Driver |
| --- | --- | --- | --- | --- |
| Activated cards (M1) | 85,000 | 100,000 | 115,000 | Card live June 11 |
| Avg monthly spend / card | $180 | $220 | $280 | World Cup lift |
| Y1 gross transaction volume | $700M | $950M | $1.2B | 90-day WC activation |
| Interchange revenue (1.5%) | $10.5M | $14.3M | $18.0M | Visa card economics |
| Blended CAC (paid + organic) | $12 | $8 | $5 | FCB brand organic pull |
| CAC payback period | 18 months | 12 months | 8 months | LTV $45–85 |
| Phase 1 retainer as % revenue | 21% | 16% | 12% | Surgence $60K + agencies |
| Y1 revenue per activated user | $124 | $143 | $157 | Interchange + fees |

E. Budget Gaps — Items Not Yet Funded

| Gap | Estimated Cost | Risk if Unfunded |
| --- | --- | --- |
| OOH campaign (remnant, digital) | $80K–$120K (3 markets) | Missed street-level brand visibility during WC |
| WC host-city IRL events | $150K–$300K (4 cities) | No physical presence at peak fan moment |
| FIFA broadcast deal | $200K–$1M (market-dependent) | Miss Mexico opener = no broadcast anchor |
| Customer support ramp (PT/ES agents) | $30K–$60K (3 months) | App crash or KYC backlog at launch |
| Crisis PR retainer | $10K–$20K (contingency) | No coordinated response to security incident |
| Post-WC retention campaign (Aug+) | ~$50K/mo | User drop-off after July 19; no stickiness |
| Phase 2 / TGE marketing budget | $150K–$400K | Token launch under-resourced; separate brief |

# RACI

RACI MATRIX — PHASE 1 · BARÇA BANC LAUNCH

R = Responsible (does the work)  ·  A = Accountable (signs off)  ·  C = Consulted (input required)  ·  I = Informed (kept updated)

Roles: Walter (CMO) · FCB Leadership · FCB Legal · FCB Product/Tech · FCB Data · Surgence Labs · Media Agency · PR Team · Web/Design Agency · Legal Counsel (LatAm)

| Task / Workstream | Walter (CMO) | FCB Leadership | FCB Legal | FCB Product/Tech | FCB Data | Surgence Labs | Media Agency | PR Team | Web/Design Agency | Legal Counsel (LatAm) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PHASE 0 — CONTRACTS & GOVERNANCE ¦ NOW – MAY 14 |  |  |  |  |  |  |  |  |  |  |
| Countersign Surgence MSA + Schedule A | A | R | C |  |  | C |  |  |  |  |
| FCB board WS2 go/no-go decision | C | R | C |  |  |  |  |  |  |  |
| Delist $BAR from exchanges | I | A | R |  |  |  |  |  |  | C |
| Appoint FCB POC (content approver) | C | R |  |  |  |  |  |  |  |  |
| Redline + sign CCLA Schedule 1 | A | C | R |  |  | C |  |  |  |  |
| Appoint legal counsel (BR/MX/AR/CO) | A |  | C |  |  |  |  |  |  | R |
| Confirm per-market financial ad rules | C |  | A |  |  |  |  |  |  | R |
| Player Access — Schedule B amendment | A | C | R |  |  | C |  |  |  |  |
| PHASE 1A — PRE-LAUNCH SPRINT ¦ MAY 10 – 24 |  |  |  |  |  |  |  |  |  |  |
| Brand identity & tone of voice | A | C |  |  |  | R |  |  | C |  |
| Messaging hierarchy (PT/ES variants) | A |  |  |  |  | R |  |  |  | C |
| Landing page (banc.fcbarcelona.com) | A |  |  | C |  | R |  |  | R |  |
| App UX/UI design (onboarding + KYC) | A |  |  | C |  | I |  |  | R |  |
| App Store submission (Apple + Google) | C |  |  | R |  | I |  |  |  | C |
| ASO keyword research (4 markets, 4 langs) | A |  |  |  |  | R |  |  |  | C |
| Loyalty Dividend mechanics design | A |  |  |  | C | R |  |  |  | C |
| CRM data tier confirmation | C |  |  |  | R | C |  |  |  |  |
| Country-Edition Card design (4 markets) | A |  |  |  |  | C |  |  | R |  |
| Press kit & asset pack | C |  |  |  |  | R |  | R | C |  |
| Embargo briefs (FT, Bloomberg, Athletic) | A |  |  |  |  | C |  | R |  |  |
| Influencer brief + compliance framework | A |  | C |  |  | R | R |  |  |  |
| Email welcome sequence (17-day nurture) | A |  |  |  |  | R | C |  |  | C |
| Web2 organic seeding setup | C |  |  |  |  | R |  |  |  |  |
| Reddit sleeper agent activation | I |  |  |  |  | R |  |  |  |  |
| WhatsApp seeding (LATAM, MENA, SEA) | I |  |  |  |  | R |  |  |  |  |
| Localization workflow (PT-BR, MX/AR/CO-ES) | A |  |  |  |  | R |  |  | C | C |
| Creator program brief (30 seed + 150 amb) | A |  |  |  |  | C | R |  |  |  |
| Paid media brief + channel allocation | A |  |  |  |  | C | R |  |  |  |
| Analytics & attribution setup (UTM/GA4) | A |  |  |  |  | R | C |  | C |  |
| Crisis & FUD playbook (5 scenarios) | A |  | C |  |  | R |  | C |  |  |
| PHASE 1B — LAUNCH MOMENT ¦ MAY 24 |  |  |  |  |  |  |  |  |  |  |
| FCB owned channel posts (IG/X/TikTok/YT) | C | A |  |  |  | R |  |  |  |  |
| Daily Player Drop asset go-live | C | A |  |  |  | R |  |  |  |  |
| Waitlist page + pre-order open | A |  |  | C |  | R |  |  | C |  |
| Country-Edition Card pre-orders (5K each) | A |  |  | R |  | C |  |  |  |  |
| Tier-1 press embargo lift (FT/Bloomberg) | C |  |  |  |  | C |  | R |  |  |
| Social seeding across communities | I |  |  |  |  | R |  |  |  |  |
| Sponsor play activation (Spotify/Stream) | A |  |  |  |  | R |  |  |  |  |
| PHASE 1C — WORLD CUP WINDOW ¦ JUNE 11 – JULY 19 |  |  |  |  |  |  |  |  |  |  |
| Country Boost Days (match-day triggers) | A |  |  |  |  | R | C |  |  |  |
| Win Bonus push notifications | A |  |  | R |  | C |  |  |  |  |
| MOTM Cashback mechanic | A |  |  | R |  | C |  |  |  |  |
| Bracket Prediction Game | A |  |  | R |  | C |  |  |  |  |
| Final Ticket VIP Draw (grand prize) | A | C | C |  |  | R |  |  |  |  |
| Paid social — World Cup creative wave | A |  |  |  |  | C | R |  |  |  |
| Creator program WC activations | A |  |  |  |  | C | R |  |  |  |
| Host-city IRL events (VIP hangouts) | A | C |  |  |  | R |  |  |  |  |
| FIFA broadcast slot (Mexico opener) | A | R |  |  |  | C |  |  |  |  |
| OOH / DOOH (remnant, 3 markets) | A |  |  |  |  | C | R |  |  |  |
| Korea Web2 activation | A |  |  |  |  | R |  |  |  |  |
| Customer support (PT/ES, KYC SLA) | A |  |  | R |  | C |  |  |  |  |
| Real-time funnel dashboard (daily) | R |  |  |  |  | C | C |  | C |  |
| Weekly performance review | R | I |  |  |  | C | C | C |  |  |
| PHASE 1D — POST-WORLD CUP ¦ JULY 20 – AUG 31 |  |  |  |  |  |  |  |  |  |  |
| Post-WC retention campaign (Aug+) | A |  |  |  |  | R | C |  |  |  |
| Win-back sequence (inactive users) | A |  |  |  |  | R | C |  |  |  |
| Loyalty program replace WC mechanics | A |  |  | R |  | C |  |  |  |  |
| Phase 1→2 vocabulary bridge (fiat→token) | R | C | C |  |  | C |  |  |  |  |
| User segmentation (high-LTV for TGE) | A |  |  |  | R | R |  |  |  |  |
| Pre-TGE handoff brief to Phase 2 team | R | C |  |  |  | C |  |  |  |  |
| BCB Resolution 561 architecture decision | A | C | R | R |  | C |  |  |  | R |
| Phase 1 marketing audit & retrospective | R | I |  |  |  | C | C | C |  |  |
| GOVERNANCE — ONGOING |  |  |  |  |  |  |  |  |  |  |
| Weekly CMO stand-up | R |  |  |  |  | C | C | C | C |  |
| Content approval queue (5-day SLA) | C | A |  |  |  | R |  |  |  |  |
| Legal review of ad copy per market | C |  | C |  |  | R |  |  |  | A |
| FCB channel access management | C | A |  | C |  | I |  |  |  |  |
| Surgence workstream reporting | A | I |  |  |  | R |  |  |  |  |
| Budget reconciliation (monthly) | R | I |  |  |  | C | C | C | C |  |
| KPI tracking vs targets | R | I |  |  |  | C | C |  |  |  |
| Crisis response activation | R | C | C |  |  | R |  | C |  |  |

# Surgence Labs

FC BARCELONA

× SURGENCE LABS

Proposal

Neobank Launch Phase and TGE Re-Engagement

| PREPARED FOR Andrew Lee, LFG.cat Maurits, FC Barcelona Web3 Team | PREPARED BY Julian Stafford and Vinh Nguyen Co-Founders, Surgence Labs |
| --- | --- |

May 2026. Confidential. NDA Protected.

SECTION 01

The Setup

Sequencing has changed. The neobank launches May 24 on the final La Liga match day. The token follows in August, anchored to the first match of the 2026 to 2027 season. That inversion changes what the immediate campaign needs to do.

The near-term window is a neobank launch campaign and pre-TGE build through the World Cup. Web3 KOL activation, CT FOMO mechanics, and presale support belong to a later phase. This document reflects that scope.

ANDREW, MARCH 26 80% of the focus should be on Web2. Web2 infiltration, that type of thing. Web3 is maybe 15-20% just shaping stuff, people will start talking. The DAT is more connections and intros rather than something more hands on.

Surgence has taken Andrew's framing further. Phase 1 is now 100% Web2. No token rumor seeding, no CT activity, no Web3-adjacent channel work of any kind. All token-related activation begins exclusively in Phase 2 once TGE timing is confirmed in writing. This eliminates any risk of premature token signal undermining the neobank launch and protects the locked-out narrative that the Phase 2 campaign relies on.

The two engagements are staged but connected. Phase 1 builds the neobank user base that becomes the most credible TGE audience available to any project launching in Q3 2026. Phase 2 converts that base. The team does not change between phases.

Surgence does not overlap with FCB's internal social team, Leo's design function, the LFG dev team, Carlos's PR network, or Open World's exchange and institutional work. The scope below is clean.

SECTION 02

Audience Strategy

Primary Audience: Existing FCB Fans

The primary campaign audience is not crypto-native. It is not even finance-native. It is football fans who have spent money supporting FC Barcelona for years and have received nothing back beyond the experience of watching the club. That fan psychology is the entry point.

FCB has 800 million global fans. The campaign does not need to convert all of them. The constraint is not reach. It is activation flow and onboarding friction. The product is already built. The job is to put it in front of people who have a pre-existing reason to care.

| SEGMENT | PROFILE | ACTIVATION ANGLE |
| --- | --- | --- |
| Core Fan Base (Global) | FCB social followers, merchandise buyers, match viewers. 18 to 45. LATAM, Europe, Africa, SEA. | Brand loyalty. The club they have supported their whole lives is now offering them something back. |
| Unbanked / Underbanked Fans | Young fans in LATAM, Africa, SEA with predatory local banks or no banking relationship. High mobile penetration. | Modern, clean digital banking with a brand they already trust. No need to explain crypto. |
| Korean Fan Market | Korea has an outsized FCB following relative to market size. High ARPU. Premium experience buyers. | Localised activation through Web2-first fan and football channels. Not crypto-native. |
| Web3 / Crypto-Adjacent Fans | CT users who follow football and crypto. Out of scope for Phase 1. | Activated entirely in Phase 2. No Phase 1 touchpoints. |

The 100% Web2 Frame

Phase 1 activity is 100% Web2. The pitch is the card, the cashback, and the FCB brand. No CT seeding, no rumor activity, no Web3 channel work of any kind. Token discourse waits for Phase 2.

This is not a compromise. It is the correct commercial decision given the timeline. The World Cup runs June 11 through July 19. Global attention is on football. The market for a football-branded financial product during that window is at its annual peak. That window should not be split. Every dollar and hour goes into converting football fans into neobank users.

SECTION 03

Featured Growth Mechanic

The FCB Loyalty Dividend.

Every successful pre-registration campaign is built on a single number that makes the user feel something. For ETHGas, the number was how much your Ethereum transactions cost in gas over the last year. For ORBT, it was your DeFi Score. 590,000 users shared the ETHGas report. 70,000 shared the ORBT score. Both spread because the number was personal, surprising, and slightly uncomfortable.

The FCB Loyalty Dividend applies the same mechanic to football fans. The number: how much the FCB card would have paid you back, based on your actual history as a supporter.

THE CORE MESSAGE You have spent EUR 4,200 supporting FC Barcelona over 8 years. If you had been using the FCB card, you would have earned EUR 336 back. Instead, your bank kept it.

That number is the campaign. Everything else is delivery infrastructure.

How It Works

Before May 24, fans connect their existing FCB account or enter their email and receive a personalised Loyalty Dividend card. The card shows: years as a fan, estimated lifetime FCB spend, Loyalty Dividend figure in large type, supporter tier badge, and a single line at the bottom.

- Shareable Output: Landscape card, same format as the Fan Spending Report already built in the Surgence Lovable toolkit. One-tap share to X and WhatsApp. Pre-written caption with the personal number embedded.

- Brand Line: FC Barcelona is finally paying its fans back.

- Token Signal: None. No forward reference to the token in the card, the email, the landing page, or any Phase 1 collateral. Phase 2 owns all token-related communication.

Why This Spreads in Web2

The card format is designed to circulate in group chats. The pre-written caption is short enough for WhatsApp. This is the same distribution mechanic that seeded the ORBT DeFi Score to 70,000 shares and the ETHGas Gas Report to 590,000 users. Adapted here for football fans who have never touched a crypto app.

People share personal financial data cards because they are sharing a fact about themselves, not a brand message. The FCB Loyalty Dividend combines two emotions simultaneously: pride at having supported the club for that long and mild grievance at having received nothing back. The card resolves both. That emotional structure is highly shareable.

CRM Data Tiers

The Loyalty Dividend figure is only as compelling as the data behind it. Surgence will confirm CRM access in the first 30 days of engagement. Three execution tiers:

| TIER | DATA AVAILABLE | DIVIDEND FIGURE | STRENGTH |
| --- | --- | --- | --- |
| Tier 1 | Full CRM transaction history per account | Real figure from actual spend history | Maximum personalisation and impact |
| Tier 2 | Account age + supporter tier only | Estimated from average spend per tier. Requires short disclaimer. | Still personalised. Slightly less precise. |
| Tier 3 | Email only, no CRM linkage | Based on self-reported fan quiz. Converts mechanic to quiz format. | Usable. Does not delay May 24 window. |

Surgence will confirm CRM access scope within the first 30 days of engagement and move to the appropriate execution tier. If full Tier 1 access is not available before May 24, Surgence launches on Tier 3 and upgrades on confirmation. The launch date does not move for data availability.

SECTION 04

Phase 1 GTM Sequence

Phase 1 runs from now through mid-July 2026, covering the neobank launch announcement on May 24, the World Cup window from June 11 to July 19, and the pre-TGE buildup. The campaign is structured in four sub-phases.

Pre-Launch: Now to May 24

Infrastructure and seeding before the public announcement. This is the highest-leverage window. Everything placed now compounds on announcement day.

- Strategy and Messaging Framework: Master GTM document delivered within week one. Covers positioning (Revolut-competitive, FCB brand trust), messaging hierarchy, spokesperson talking points, channel-by-channel tone guidance, and the no-token-signal protocol governing every Phase 1 communication.

- Loyalty Dividend Pre-Registration: Pre-registration flow built and live before May 24. Queue mechanic active. Fans who register before announcement day receive first-access status for the card.

- Reddit Sleeper Agent Seeding: Pre-positioned accounts active in r/Barca and r/FCBarcelona. Organic voice, not promotional. Accounts need weeks of posting history before the announcement to avoid appearing astroturfed.

- Facebook Admin Network: 30 regional supporter group admins briefed and activated. Admins post in their own voice. Surgence provides talking points and timing. Not branded.

- WhatsApp Regional Seeding: SEA, MENA, Africa, LATAM seeding begins immediately. Lead time on WhatsApp networks is three to four weeks minimum. Starting now is not optional.

- Korea Web2-First Activation: Local partner selection in progress. Activation covers fan community channels, football media, and K-adjacent cultural crossover. Partners confirmed within 30 days of engagement start.

- Community Advisory Layer: Moderation frameworks delivered to FCB's internal community team. New @FCBarcelona Web3 Telegram channel built and managed by Surgence. FUD response playbook prepared. Group-chat alignment with FCB community managers.

- Content Governance Setup: Content calendar built. X pre-post review process established. IG and FB brief templates delivered to FCB internal team. Spokesperson talking points drafted.

- Weekly Alignment Sessions: Standing weekly working session with Andrew and Maurits begins week one. Campaign review, upcoming activations, and content sign-off.

Announcement: May 24, Final Match Day

The neobank goes live. The Loyalty Dividend campaign activates publicly. Every channel fires simultaneously. The coordination advantage Surgence provides is that all channels are pre-warmed and briefed before this day. The Facebook admin network, WhatsApp seeders, Reddit accounts, and Korea activation are all ready. FCB's internal team handles official channels. Surgence operates the fan-community and organic layer.

- Match Day Activation Hook: The final La Liga match day is a high-emotion moment for every FCB fan globally. The announcement benefits from that context directly: fans who just watched a match are the target audience. The Loyalty Dividend number, shared by fans in real time, becomes organic match-day content.

World Cup Window: June 11 to July 19

This is the peak conversion window. Global football attention is at its annual maximum. Every brand on earth is competing for footballer association. The FCB neobank has a structural advantage: it already has player relationships through the LFG.cat roster. The Player Access programme (Section 06) runs at full throughput during this window.

- Football Forum and Podcast Outreach: Non-crypto sports media. This is where the Revolut-competitive narrative lands hardest. The pitch to football media is not a Web3 story. It is a better bank story with an FCB brand.

- World Cup Match Activation: Push notifications and in-app rewards tied to match results. If FCB players on national teams win, cardholder rewards multiply. Drives engagement and organic social.

- Referral Mechanic Activation: Cardholder referral programme active. Structure from the pre-registration queue mechanics: refer three fans, earn premium card tier upgrade or early access to limited Camp Nou experiences.

Pre-TGE Handoff: Late July to Phase 2 Activation

The final sub-phase of Phase 1 is building the handoff infrastructure for Phase 2. This means: neobank user segmentation by engagement tier, identification of highest-LTV users for presale prioritisation, documentation of what worked and what did not in the Web2 activation, and the TGE narrative framework ready for Phase 2 launch.

By the time Phase 2 activates in August, there should be a pre-warmed audience of neobank users who have already demonstrated financial commitment to the FCB ecosystem. That is the most valuable TGE audience available to any project launching in Q3 2026.

SECTION 05

Scope of Work

Phase 1 scope covers the neobank launch campaign from now through mid-July 2026. Web3 distribution workstreams are explicitly deferred to Phase 2 and documented at the end of this section. Each line below is assigned to one party.

Phase 1: Neobank Launch (Active Now)

| AREA | SURGENCE OWNS | FCB / PARTNERS OWN |
| --- | --- | --- |
| Web2 Infiltration (100%) | Reddit sleeper agents in r/Barca (high IQ) and r/FCBarcelona (volume). Accounts pre-positioned weeks before May 24. Facebook group admin activation across 30 named regional supporter groups. WhatsApp network seeding: SEA, Middle East, Africa, LATAM. Starts immediately. Lead time is four weeks minimum. Football forums, podcast outreach, planted threads. Korea Web2-first activation via Surgence Korea network and Web2 partner agency. Fan and football audience, not crypto-native. Local partner confirmed within 30 days. | Carlos: PR and player access. FCB official channels. |
| Viral Product Mechanic | Loyalty Dividend Pre-Registration: Personalised card showing how much the FCB card would have paid the fan back across their history as a supporter. Shareable format. Referral queue mechanic. Runs before and through May 24 launch. Three execution tiers based on CRM data access confirmed within 30 days: full transaction history, tier-estimated figures, or self-reported quiz. Launch date does not move for data availability. This is the campaign's primary organic distribution engine. Same mechanic architecture as the ORBT DeFi Score (70K shares) and ETH Gas Report (590K users). | LFG: dev integration for CRM linkage. FCB: CRM data access. |
| Community Advisory | Communication guidelines and moderation frameworks for FCB's internal team. Telegram channel build for new @FCBarcelona Web3 channel. Channel sits dormant until Phase 2 activation. Group chat alignment with FCB's existing community managers. FUD mitigation briefings and real-time response guidance. | FCB internal team: day-to-day community ops. FCB: WhatsApp broadcast (50M members). |
| Content Governance | Refine FCB's existing content calendar draft. Official X review before every post goes live. Instagram and Facebook briefs for FCB's social team. Talking points and approved language for all spokespeople. Zero token language from any FCB account in Phase 1. All token messaging activates exclusively at Phase 2. | FCB social team: owns and executes content. Leo + FCB team: all creative execution. |
| Strategy | Master GTM document: single source of truth for neobank launch campaign, updated weekly. Campaign sequencing and phase gate conditions through World Cup window. Messaging framework: Revolut-competitive positioning, FCB brand trust, unbanked fan audience. Weekly alignment sessions with Andrew and Maurits. | Andrew / Maurits: commercial and TGE structure. LFG: all development. |
| DAT / Institutional (Free) | Introductions to VCs, liquidity providers, and institutional contacts from Surgence network where relevant. Not a managed workstream. Value-add from network, activated when it makes sense. | Open World: owns all regulatory, exchange, market making, institutional IR. |

Deferred to Phase 2 TGE Re-Engagement

OUT OF SCOPE FOR PHASE 1 - All token-related messaging, rumor seeding, and forward references. Zero token signal of any kind in Phase 1 across any channel. - KOL Tier 2 amplification and Tier 1 TGE-day wave. - CT FOMO positioning and locked-out narrative for secondary-market intent building. - Presale support, holder communications, and sentiment monitoring. - Regional crypto-native channels: CIS, China, LATAM crypto channels are entirely off in Phase 1. Activated in Phase 2. - On-chain analytics dashboard and Dune deployment.

SECTION 06

Player Access (Schedule B)

New addition. LFG.cat has closed player endorsement relationships covering Messi, Lamine Yamal, Neymar, Ronaldinho, Alexia Putellas, Marcel Ruiz, and others. During the World Cup, every brand is seeking footballer association. This programme enables Surgence to broker deals from its Web3 client network against that roster.

Player Access runs in parallel to the monthly retainer and remains active across both Phase 1 and Phase 2. Each closed deal carries co-marketing conditions tied to the FCB neobank launch and, later, the $FCB token sale, which converts every brokered partnership into a distribution channel for both phases.

| Structure | 60/40 revenue share on commissions. LFG.cat closes the players. Surgence closes the sponsors. |
| --- | --- |
| Deal Conditions | Each sponsor deal is conditional on (1) active co-marketing of the FCB neobank launch, and (2) public commitment to support the $FCB token sale when it goes live. Conditions keep every brokered deal as an organic distribution channel for both phases. |
| Player SLA | LFG.cat confirms player availability within 5 business days of Surgence presenting a qualified sponsor opportunity. |
| Category Exclusivity | Right of first refusal by category. LFG.cat confirms no competing deal is active before Surgence opens any sponsor conversation. |
| Minimum Deal Size | USD 50,000 gross minimum per deal. To be confirmed. Ensures Surgence BD time is allocated to deals with material upside. |
| Independence | Player Access commissions are additive to the monthly retainer. Neither is offset against the other. Active across both Phase 1 and Phase 2. |

SECTION 07

Commercial Terms

Two engagements. Phase 1 is signed now. Phase 2 terms are pre-agreed in this document and activate on Andrew's written confirmation of TGE timing. When that confirmation comes, there is no renegotiation on the headline numbers.

Phase 1: Neobank Launch

| PHASE 1 NEOBANK LAUNCH Now to mid-July 2026 · ~2.5 months $20K / month | - Master GTM document and messaging framework - Loyalty Dividend pre-registration product (viral mechanic for neobank launch) - Reddit sleeper agent placement in r/Barca and r/FCBarcelona - Facebook group admin activation across 30 regional supporter groups - WhatsApp network seeding: SEA, Middle East, Africa, LATAM - Football forums and podcast outreach - Korea Web2-first activation via local partner (partner confirmed within 30 days) - Community advisory: moderation frameworks for FCB internal team; @FCBarcelona Telegram build - Content governance: calendar, X pre-post review, IG/FB briefs, spokesperson talking points - Weekly alignment sessions with Andrew and Maurits |
| --- | --- |

TOKEN ALLOCATION No token allocation for Phase 1. We can revisit 0.15% on the TGE re-engagement when scope, timing, and deliverables are locked.

Phase 2: TGE Campaign (Conditional)

Terms below are agreed as part of this document. Phase 2 activates on Andrew's written confirmation of TGE timing. No renegotiation required.

| PHASE 2 TGE CAMPAIGN · CONDITIONAL August 2026 onward · ~4 months minimum $25K / month | - KOL wave deployment: Tier 3 seeding, Tier 2 amplification, Tier 1 on TGE day - CT FOMO narrative: locked-out positioning and secondary-market intent building - All regional crypto-native channels live: Korea, CIS, China, SEA, MENA, LATAM - Independent creator drops timed to official X beats - Community ops and FUD mitigation through TGE day - Presale support, holder communications, and sentiment monitoring - 0.15% of total $FCB supply. Vesting schedule confirmed at Phase 2 sign-off. |
| --- | --- |

PHASE 2 ACTIVATION Trigger: Andrew's written confirmation of TGE timing. Capacity: reserved at these terms from the date of this document's execution. Expected window: June or July 2026 confirmation for ~August 2026 TGE.

Post-TGE Sustain

| POST-TGE SUSTAIN Monthly, reviewed $10K to $20K / month | - Holder retention and community sustain - Secondary market sentiment and FUD monitoring - Expansion market activation as needed |
| --- | --- |

KOL and Paid Media Budget

All KOL fees and paid media pass through at cost. No Surgence margin on distribution spend. Receipts on a 7-day cycle with full reporting. Phase 1 KOL budget is allocated to Web2 only: football creators, podcast placements, Facebook and WhatsApp amplification. Phase 2 KOL budget activates in Phase 2 and covers Web3 KOL waves and regional crypto channels. Specific budget envelopes for both phases are confirmed jointly with Andrew before activation.

TRANSPARENT SPEND COMMITMENT All KOL and paid media invoiced at cost with receipts. Zero Surgence margin. Phase 1 budget: TBD. Allocated to Web2 football creators, podcast placements, and regional amplification. Phase 2 budget: TBD. Allocated to Web3 KOL waves and regional crypto channels. Both envelopes confirmed jointly with Andrew before activation. Client-controlled, Surgence-managed.

Terms Summary

| Phase 1 retainer | $20,000/month. 3-month minimum. |
| --- | --- |
| Phase 1 total (minimum) | $60,000 across 2.5 to 3 months. |
| Phase 1 token allocation | None. |
| Phase 1 kill clause | 30 days notice after the 3-month minimum. No pro-ration on a zero token engagement. |
| Phase 2 retainer | $25,000/month. 4-month minimum. Activates on written TGE confirmation. |
| Phase 2 token allocation | 0.15% of total $FCB supply. Cliff and vesting confirmed at Phase 2 sign-off. |
| Phase 2 kill clause | 30 days notice after month 4. Token allocation pro-rated to milestones achieved. |
| Post-TGE sustain | $10,000 to $20,000/month. Reviewed monthly. |
| Player Access (Schedule B) | 60/40 revenue share on commissions. Additive to retainer. Active both phases. |
| KOL and paid media | Client-controlled. Managed at cost. Zero Surgence margin. |
| Payment terms | Monthly in advance. USDC preferred. |
| DAT / Institutional intros | Included free. Opportunistic value-add from Surgence network. Not a managed workstream. |

TOTAL RETAINER SUMMARY Phase 1: $60,000 across 3 months. Phase 2: $100,000 across 4 months (on activation). Phase 1 + Phase 2 combined: $160,000 cash across the full engagement. Against a $500M+ FDV TGE, the cash component is minimal. Surgence's Phase 2 upside is the 0.15% token allocation, which only pays out if the launch works.

SECTION 08

Next Steps

Eight steps from execution to Phase 2 activation. Sequence is critical. Steps 4 and 5 cannot be deferred without compromising the May 24 announcement.

| 01 | Sign this document. Phase 1 activates immediately on execution. Phase 2 terms are agreed and locked; no further commercial discussion required until TGE timing is confirmed. |
| --- | --- |

| 02 | Kick-off call: Surgence, Andrew, Maurits. CRM data access scope confirmed. Korea partner shortlist reviewed. Player Access categories discussed. |
| --- | --- |

| 03 | Surgence delivers Master GTM document and messaging framework within 5 days of kick-off. |
| --- | --- |

| 04 | WhatsApp and Reddit seeding begins immediately. Lead time on these networks is four weeks minimum. Starting now is not optional before May 24. |
| --- | --- |

| 05 | Loyalty Dividend pre-registration product brief delivered within 7 days. CRM data tier confirmed. Build begins. |
| --- | --- |

| 06 | Surgence begins Player Access outreach to Web3 partner network. First qualified opportunities presented to Andrew within two weeks. |
| --- | --- |

| 07 | Korea local partner confirmed within 30 days of kick-off. |
| --- | --- |

| 08 | Andrew confirms TGE timing in writing (expected June or July 2026). Phase 2 activates. No renegotiation on commercial terms. |
| --- | --- |