FC BARCELONA BANC Updated Phase 1 Marketing Plan — World Cup Edition Incorporating benchmarks: Nubank · Chime · Tuyo · May 10, 2026 · T-14 days to announcement · CONFIDENTIAL

| ✅ CONFIRMED | ⚠️ IN PROGRESS | ❌ MISSING | 🔗 DEPENDENCY |
| --- | --- | --- | --- |

This document is the operational marketing plan for Barça Banc Phase 1. It incorporates the competitive intelligence from Nubank, Chime, and Tuyo analyses and replaces the previous FCBarcelonaBanc_Marketing.docx as the working execution reference. Every section is status-coded. Every MISSING item includes what it is, what it should look like, and who needs to own it.

01  STRATEGIC FOUNDATION

POSITIONING

| Tagline | Your culer life, rewarded. | ✅ CONFIRMED |
| --- | --- | --- |
| Positioning | The only card that pays you back for being a Barça fan. Every swipe converts loyalty into cashback. No crypto required. | ✅ CONFIRMED |
| Frame | Celebration — not grievance. FCB gives back what the fan has always deserved. Grievance framing (e.g., 'the club has taken from you') is explicitly banned. | ✅ CONFIRMED |
| Phase 1 Rule | 100% Web2. No token language, no CT seeding, no Web3 channels. Token discourse (TGE) begins August 2026 and is a separate campaign. | ✅ CONFIRMED |

BRAND IDENTITY — STATUS: MISSING

| Brand Identity | Does not exist as of May 10. Required before: landing page, press kit, creator briefs, app store assets, Country-Edition card artwork, OOH creative, all 19 digital surfaces. Surgence is the delivery vehicle. Blocked by unsigned contract. Nubank benchmark: purple card as identity artifact — one color, zero ambiguity. Apply same discipline here: garnet + gold, no design drift across markets. | ❌ MISSING Owner needed Surgence — T+0 |
| --- | --- | --- |

AUDIENCE SEGMENTS

| Segment | Who They Are | Activation Angle | Benchmark Learning |  |
| --- | --- | --- | --- | --- |
| Core Culers | FCB social followers, merch buyers, match viewers. 18–45. LatAm primary. | Brand loyalty. The club they supported their whole lives now offers something back. | Nubank: NPS-led referral from existing advocates. Chime: member identity ('I bank with Chime'). | ✅ CONFIRMED |
| Unbanked / Underbanked | Young LatAm fans with predatory local banks or no banking. High mobile. | Modern clean digital banking with a brand they already trust. Zero crypto required. | Nubank: launched with waitlist + purple mailer to underbanked Brazil. Primary growth vector. | ✅ CONFIRMED |
| Korean Fan Market | Outsized FCB following relative to market size. High ARPU. Premium buyers. | Web2-first activation. Football channels, not crypto. Localised card variant. | Tuyo: X-only distribution for niche-but-passionate audience. Adapt for Korean football forums. | ✅ CONFIRMED |
| LatAm Football Adjacent | Non-Barça fans who watch La Liga + World Cup. New to FCB brand. | World Cup is the entry point. Country Boost Days turn national pride into Barça Banc trial. | Chime: Ball on a Budget NBA activation — 25M views from sports-adjacent audience. Apply same logic. | ⚠️ IN PROGRESS |
| Web3 / Crypto-Adjacent Fans | CT users who follow football and crypto. | OUT OF SCOPE — Phase 2 only. Zero Phase 1 touchpoints. | Tuyo Phase 1 → Phase 2 sequencing: build product users first, then layer token narrative. | ✅ CONFIRMED |

02  PRE-LAUNCH SPRINT  —  MAY 10–24

14 days. Every item below must complete before May 24. Items are ordered by dependency — nothing in Week 2 starts until Week 1 gates close. Red = must act today.

| Item | What It Is | What Good Looks Like | Benchmark | Status |
| --- | --- | --- | --- | --- |
| Sign Surgence contract | Legal agreement for Phase 1 scope ($60K retainer, 3 months). | Signed, countersigned, entity confirmed. WhatsApp seeding starts same day. | — | ❌ MISSING TODAY May 10 |
| Brand identity sprint | Logo, color system, type, card artwork brief, tone-of-voice guide. | 72-hour delivery from Surgence. One hero visual: garnet card, gold Barça crest, fan name. | Nubank: single purple card = entire brand. Zero ambiguity. | ❌ MISSING May 10–12 |
| Landing page + waitlist | banc.fcbarcelona.com — hero visual, tagline, waitlist CTA, referral queue-jump mechanic. | Mobile-first. Under 3s load. A/B test CTA copy. Queue-jump counter visible in real time. | Chime: landing page was their primary CAC surface. Nubank: waitlist exclusivity created FOMO. | ❌ MISSING May 10–17 |
| App Store submission | iOS + Android submissions in Brazil, Mexico, Argentina, Colombia. | All 4 market submissions filed by May 17. Apple review buffer = 7 days. | Financial apps face enhanced review. Nubank: separate submissions per market took 3 weeks. | ❌ MISSING May 17 HARD DEADLINE |
| Press kit assembly | Brand assets, embargo pitch, founder bio, product screenshots, key stats, B-roll. | PDF + Dropbox folder. Embargo pitch written. 10 journalists briefed by May 18. | Chime: Halftime Wedding generated 20 media pickups from one tight press kit. | ❌ MISSING May 10–20 |
| Paid media setup | Agency brief, account setup (Meta Ads, Google Ads, TikTok Ads), creative specs, budget approved. | Media plan submitted May 14. Campaigns loaded May 20. Live June 1 (pre-World Cup warm-up). | Chime: $1M Bet AKQA — 375M impressions from one bold paid activation. Model the single big bet. | ❌ MISSING May 14 |
| Legal framework — creator disclosures | FTC/CONAR/CNBV/SFC disclosure language per market. Creator brief template. NDA template. | One-page creator brief. Disclosure language appended. Legal sign-off before any creator contract. | Chime three-tier model: each tier had a different disclosure + exclusivity structure. | ❌ MISSING May 14 |
| Facebook group admin outreach | 30 admins across LatAm football Facebook groups. Relationship-building, not spam. | Personal outreach from Surgence team. No pitch in first contact. Build trust over 2 weeks. | Nubank: seeded early adoption through organic Facebook groups in Brazil in 2014–2015. | ⚠️ IN PROGRESS Starts May 11 |
| WhatsApp community seeding | Football fan WhatsApp groups in Brazil, Mexico, Argentina, Colombia, SEA, MENA. | Surgence team joins as members, provides value for 2 weeks before any product mention. | Needs 4 weeks minimum. May 10 is last possible start date to reach June 11 organically. | ❌ MISSING Starts TODAY |
| Country-Edition card artwork | 4 cards × 5,000 units: Brazil, Mexico, Argentina, Colombia. Design + to printer. | Artwork brief May 12. Design approved May 16. Printer file submitted May 16. | Physical artifact = earned media. Nubank's purple card got photographed by 200K users. | ❌ MISSING May 16 TO PRINTER |
| Loyalty Dividend CRM integration | FCB historical spend data → fan identity mapping → personalised card generation. | Sample data set tested with 1,000 fan profiles. Shareability tested. LGPD compliance confirmed. | Tuyo: BNPM slot machine was viral because it was personalised + surprising. Same logic here. | 🔗 DEPENDENCY FCB Data team |
| Korea activation brief | Localised strategy for Korean football channels, forums, and fan communities. | Brief written. One local partner identified. Korean-language content calendar mapped. | Tuyo: X-only for niche audience. Korea = niche-but-high-ARPU. Don't dilute with mass channels. | ❌ MISSING May 20 |

03  LAUNCH MOMENT — MAY 24

The final La Liga match day. Every activation fires simultaneously across owned, rented, and borrowed channels. This is not a social media post. It is a coordinated detonation across 8 surfaces in a 6-hour window.

| Time (CET) | Activation | What Happens | Benchmark |  |
| --- | --- | --- | --- | --- |
| 06:00 CET | Press embargo lifts | Bloomberg, FT, The Athletic, ESPN Brasil, Marca, GOAL publish simultaneously. | Chime: Halftime Wedding — 20 media pickups in 4 hours from one coordinated embargo. | ❌ MISSING |
| 10:00 CET | FCB official social post | Instagram + TikTok + X + YouTube Shorts. Product hero visual. Tagline. Waitlist link. | Nubank: launch post went to 5M followers at once. Engagement > reach. | ✅ CONFIRMED |
| 10:01 CET | Loyalty Dividend goes live | banc.fcbarcelona.com/your-rewards — fans enter FCB fan ID, get personalised card. | Tuyo: BNPM slot machine was live on launch day and drove immediate shares. Same mechanic. | 🔗 DEPENDENCY |
| 10:00 CET | WhatsApp broadcast (50M) | FCB WhatsApp broadcast list. One message. Link. No overexplaining. | 50M reach. Nubank used WhatsApp as primary Brazil activation channel 2014–2016. | ✅ CONFIRMED |
| 10:00 CET | Country-Edition card pre-order opens | 5K units per country. Countdown timer visible. Queue-jump for waitlist members. | Nubank: original purple mailer created physical FOMO. Scarcity drives urgency. | 🔗 DEPENDENCY |
| 12:00 CET | Daily Player Drop #1 | First player card live on Instagram Stories. Interactive poll: 'Which country edition?' | Cadence-first. Nubank's Carnaval drops were daily. Chime's NBA content was episodic. | ✅ CONFIRMED |
| Match Kickoff | In-match social activation | Live commentary + cashback mechanic preview. Story countdown: 'First win = first bonus.' | Chime: Ball on a Budget worked because it was live sports commentary. Time the content. | ⚠️ IN PROGRESS |
| Full Time | Founder post / CEO thread | FCB CEO or Barça Banc MD posts personal thread on X: why we built this, for who. | Nubank: Cristina Junqueira's personal posts outperformed all brand posts. Make it human. | ❌ MISSING |
| All Day | Reddit sleeper agents activate | Organic mentions across r/fcbarcelona, r/soccer, country-specific subs. | Tuyo: no paid Reddit. Surgence organic seeding model is correct. Execute as planned. | ⚠️ IN PROGRESS |
| All Day | Paid media day-1 campaigns live | Meta + Google + TikTok waitlist campaigns running in all 4 markets. | Chime: paid media was running before launch day. Don't cold-start on announcement day. | ❌ MISSING |

04  WORLD CUP WINDOW — JUNE 11 TO JULY 19

The six core mechanics. Each runs across the full window with market-specific peak moments. Nubank spent $40M+ on the 2022 World Cup. The advantage here is owned audience — FCB's 147M Instagram alone reaches more people than Nubank's entire customer base at that time.

| 01 | Country Boost Days When the national team of Brazil, Mexico, Argentina, or Colombia plays, cashback multiplier activates for all cardholders from that country. 3× cashback on match day. | EXECUTION REQUIREMENTS Design a match-day notification sequence: pre-match hype, kick-off cashback alert, final whistle summary. In-app banner + push + WhatsApp. | BENCHMARK Chime: Financial Progress Month — themed windows that activate the full member base. Apply same calendar architecture to football match schedule. ✅ CONFIRMED |
| --- | --- | --- | --- |

| 02 | Win Bonus When Barça wins, all cardholders get a win bonus deposited to their account. Automatic, instant, announced via push notification. | EXECUTION REQUIREMENTS Real-time trigger requires FIFA broadcast data integration. Backup: manual post-match activation with 15-minute delay. Design both flows. | BENCHMARK Nubank: real-time transaction notifications trained users to check the app after events. Win Bonus = same behavioral loop. 🔗 DEPENDENCY |
| --- | --- | --- | --- |

| 03 | MOTM Cashback The Man of the Match from each World Cup game triggers a cashback category boost. Messi MOTM = double cashback on food. Vinicius MOTM = double on transport. | EXECUTION REQUIREMENTS Category mapping needs product team sign-off. 32 MOTM categories to pre-map. Requires real-time match data. | BENCHMARK Nubank: partnered with streaming services (Netflix Wednesday) for co-branded moments. MOTM = the most co-brandable moment in football. 🔗 DEPENDENCY |
| --- | --- | --- | --- |

| 04 | Country-Edition Cards 5,000 physical cards per country (Brazil, Mexico, Argentina, Colombia). Pre-order opened May 24. Ship during World Cup window. | EXECUTION REQUIREMENTS Physical fulfillment partner needed. Shipping logistics to 4 countries. Unboxing video brief for creator program Wave 2. | BENCHMARK Nubank: original purple card was photographed by 200,000+ users. Physical artifact = free earned media at scale. Design the unboxing to be photographable. 🔗 DEPENDENCY |
| --- | --- | --- | --- |

| 05 | Bracket Prediction Game In-app game. Predict the bracket, earn points redeemable for cashback boosts. Daily engagement mechanic for the full 38-day window. | EXECUTION REQUIREMENTS Product feature must be built and QA'd before June 11. Leaderboard visible to all users. Social sharing of bracket = organic viral loop. | BENCHMARK Tuyo: BNPM slot machine drove shares because it was game-mechanic native. Bracket prediction = same logic, football context. ⚠️ IN PROGRESS |
| --- | --- | --- | --- |

| 06 | Final Ticket VIP Draw One cardholder per country wins tickets + hospitality to the World Cup Final (July 19). Entry = one transaction per week of the tournament. | EXECUTION REQUIREMENTS Legal sweepstakes compliance in all 4 markets. Prize logistics. Weekly winner announcement for sub-prizes (jerseys, signed merch) to maintain engagement. | BENCHMARK Chime: Final Ticket VIP Draw equivalent = their $1M Bet — one big prize creates disproportionate earned media relative to cost. ⚠️ IN PROGRESS |
| --- | --- | --- | --- |

05  CREATOR & INFLUENCER PROGRAM

180 creators across 4 markets over 3 waves. Chime's three-tier model is the template. Every creator brief requires legal sign-off before it goes out. Legal framework is the gate.

THREE-TIER CREATOR ARCHITECTURE (ADAPTED FROM CHIME)

| Tier | Profile | Count | Audience | Fee Range | Status |
| --- | --- | --- | --- | --- | --- |
| Tier 1 Macro | Football + finance macro influencers. Known faces in each market. | 10 | 1M–10M followers | $5K–$15K / post | ❌ MISSING Legal framework needed first |
| Tier 2 Mid | Football commentators, fan page operators, lifestyle creators with 100K–1M. | 50 | 100K–1M followers | $1K–$5K / post | ❌ MISSING Legal framework needed first |
| Tier 3 Micro | Super-fans, match-day vloggers, stadium regulars. Authentic voice. | 120 | 10K–100K followers | $200–$1K / post | ❌ MISSING Legal framework needed first |

CREATOR WAVE CALENDAR

| Wave | Dates | Creators | Brief Focus | Status |
| --- | --- | --- | --- | --- |
| Wave 1 | May 15–24 | 10 Tier 1 | Launch announcement. Loyalty Dividend reveal. 'Here's what my Barça years would have paid me back.' | ❌ MISSING Blocked: legal framework missing |
| Wave 2 | May 25–Jun 10 | 60 Tier 2 | Daily Player Drop amplification. Country-Edition card unboxing. Waitlist urgency. | ❌ MISSING Blocked: legal framework missing |
| Wave 3 | Jun 11–Jul 19 | 110 Tier 3 | World Cup mechanics live. Match-day content. Win Bonus reactions. Country Boost Days. | ❌ MISSING Blocked: legal framework missing |

MISSING: LEGAL COMPLIANCE FRAMEWORK

| ❌ MISSING Legal Framework | Required before first creator contract is signed. Includes: (1) FTC/CONAR/CNBV/SFC disclosure language per market, (2) Creator brief template with embedded disclosure, (3) NDA/exclusivity terms, (4) Content approval workflow — all posts require compliance sign-off before publishing. A single non-compliant post in a regulated financial market can trigger enforcement action and halt the campaign. Owner needed: FCB Legal + external financial advertising counsel in each market. |
| --- | --- |

06  PAID MEDIA

The waitlist math does not close without paid media. Organic alone from FCB's owned channels yields ~25K signups. The 750K target requires a paid media investment that has not been modeled. Chime's '$1 Million Bet' (375M impressions, AKQA) and Nubank's $40M+ World Cup spend are the benchmarks.

BUDGET MODEL — MISSING

| Market | Est. CAC | Budget Needed | Channel Mix | Status / Action |
| --- | --- | --- | --- | --- |
| Brazil 🇧🇷 | $8–15 | $600K–1.5M | Meta 50% · Google 25% · TikTok 25% | ❌ MISSING — Nubank dominates Brazil paid. Must outbid on FCB brand terms + football keywords. |
| Mexico 🇲🇽 | $12–20 | $400K–800K | Meta 40% · Google 30% · TikTok 30% | ❌ MISSING — Mercado Pago is the dominant incumbent. Differentiate on FCB loyalty angle. |
| Argentina 🇦🇷 | $6–10 | $200K–400K | Meta 60% · Google 20% · TikTok 20% | ❌ MISSING — Lower CAC due to economic conditions. High engagement market. Messi fandom is acute. |
| Colombia 🇨🇴 | $10–18 | $200K–400K | Meta 45% · Google 30% · TikTok 25% | ❌ MISSING — Fastest-growing neobank market in LatAm. Revolut and Nubank both entering. |
| Korea 🇰🇷 | $15–25 | $150K–300K | Instagram 50% · YouTube 30% · Naver 20% | ❌ MISSING — Web2-first, premium audience. Different channel mix. Requires localised creative. |

THE SINGLE BIG BET — CHIME BENCHMARK

| BARÇA BANC BIG BET CONCEPT | The Loyalty Dividend Reveal is the $1M Bet equivalent. Design one hero paid/earned campaign for May 24 built entirely around the Loyalty Dividend mechanic: 'We calculated what every BarçaFan would have earned if the card existed since 2000. Here's yours.' Full-page newspaper ad in Marca + Sport + Folha de S.Paulo. One OOH placement in Camp Nou. Paid social amplification of the personalised card generator. Chime's $1M Bet (AKQA) generated 375M impressions at a fraction of normal CPM because the concept was inherently newsworthy. Loyalty Dividend is equally newsworthy. Status: ❌ MISSING — concept validated, execution not started, budget not allocated. |
| --- | --- |

OOH — MISSING (DEADLINE PASSED FOR PREMIUM INVENTORY)

| ❌ MISSING OOH — 4 MARKETS | Premium OOH inventory in São Paulo, Mexico City, Buenos Aires, Bogotá locks 6–8 weeks in advance. That window has passed. Remaining strategy: (1) book remnant inventory NOW for June 11 (World Cup opener), (2) focus OOH spend on stadium adjacency — fan zones, transit routes to watch parties, (3) Nubank benchmark: Sphere Las Vegas ($10M+, 700 press mentions) — find the LatAm equivalent single-statement placement that earns media. Budget estimated $500K–1.5M for remnant + experiential OOH. Owner needed: media agency with LatAm OOH network. Brief required immediately. |
| --- | --- |

07  OWNED CHANNEL ACTIVATION

| Channel | Content Focus | Execution Standard | Status |
| --- | --- | --- | --- |
| Instagram (147M) | Daily Player Drop (Stories). Reel per match day. Country Boost Day countdown. Country-Edition card launch. | One story per day minimum. Player card = thumb-stop format. Poll mechanic on every post. | ✅ CONFIRMED |
| TikTok | Match-day reactions. Behind-the-scenes of card design. Loyalty Dividend demo. Duet with fans. | Post within 15 minutes of full time. Use trending audio. Fan-generated content repost strategy. | ⚠️ IN PROGRESS |
| X / Twitter | Announcement thread May 24. Real-time match commentary. Win Bonus announcements. CEO thread. | Founder/CMO account posts alongside brand account. Nubank CEO model: personal post > brand post. | ⚠️ IN PROGRESS |
| YouTube | Loyalty Dividend explainer. Country-Edition card unboxing. FCB Banc product tour. | 3–5 minute product story. Subtitle in PT-BR + ES. SEO-optimised title. Embed on landing page. | ❌ MISSING |
| WhatsApp Broadcast (50M) | Launch announcement May 24. World Cup match previews. Win Bonus notifications. | Max 2 messages per week. No marketing language — news only. Link to landing page always. | ✅ CONFIRMED |
| Email / CRM | Waitlist confirmation → onboarding sequence → activation nudge → first spend → referral ask. | 6-email sequence. Day 0, 1, 3, 7, 14, 30. Personalised with fan data where possible. | ❌ MISSING |
| banc.fcbarcelona.com | Waitlist page, Loyalty Dividend generator, product explainer, country card pre-order. | Mobile-first. Under 3s load. Waitlist CTA above fold. Queue-jump referral counter visible. | ❌ MISSING |

EMAIL ONBOARDING SEQUENCE — MISSING

| Send | Trigger | Content | Status |
| --- | --- | --- | --- |
| Day 0 | Waitlist signup | Welcome. Queue position. How to move up (referral). Your Loyalty Dividend preview: 'We're calculating yours now.' | ❌ MISSING Copywriter needed |
| Day 1 | +24 hours | Loyalty Dividend revealed: 'Here's what your Barça years were worth.' Shareable card image. CTA: Share to move up queue. | ❌ MISSING Copywriter needed |
| Day 3 | +3 days | How Barça Banc works. Product explainer. Country-Edition card preview. CTA: Pre-order your card. | ❌ MISSING Copywriter needed |
| Day 7 | App goes live | You're in. Download link. First 7 days: double cashback. Bracket Prediction Game is live. | ❌ MISSING Copywriter needed |
| Day 14 | +7 days post-download | First spend nudge. 'You have $X cashback waiting. Spend $1 to unlock it.' CTA: Make your first transaction. | ❌ MISSING Copywriter needed |
| Day 30 | +30 days | Monthly Culer Report — personalised spend summary, cashback earned, how you compare to other fans in your country. | ❌ MISSING Copywriter needed |

08  PR & EARNED MEDIA

Design one engineered earned moment per phase. Chime generated 20 media pickups from the Halftime Wedding and 375M impressions from the $1M Bet — both designed to be inherently newsworthy. Nubank's Sphere Las Vegas activation generated 700+ press mentions. The Loyalty Dividend is Barça Banc's equivalent.

| Phase / Date | Moment Name | Execution | Benchmark |  |
| --- | --- | --- | --- | --- |
| Phase 1 Earned Moment May 24 | Loyalty Dividend Launch | The story: 'We calculated what 50 million culers would have earned if this card existed since 2000.' Publish top-10 fan lifetime values (anonymised). FCB legend on record. Send to 10 journalists under embargo. | Chime: Manifest Money Candle (Apotheke collab) — designed to be photographed and shared. Loyalty Dividend card image = same photogenic hook. | ❌ MISSING |
| Phase 2 Earned Moment Jun 11 World Cup Opener | First Country Boost Day | Real-time coverage of first cashback multiplier activation. '50,000 Barça fans in Brazil earned 3× cashback at kick-off.' Press release with live transaction data (anonymised). | Nubank: released transaction data during World Cup 2022 in real time. Press loved the data story. | ❌ MISSING |
| Phase 3 Earned Moment Jul 19 Final | VIP Draw Winner Announcement | Announce the 4 Final ticket winners publicly. Video their reaction. Fly press to the Final. One human story = 10× the coverage of a product feature. | Chime: Halftime Wedding (Mavs game) — one human moment, 20 media pickups. Same model. | ❌ MISSING |
| Crisis Earned Moment On-demand | CEO Response Protocol | If app crashes, security incident, or regulatory inquiry: FCB Banc CEO posts personal statement within 60 minutes. No corporate communications language. Direct, human, specific. | Nubank: Cristina Junqueira's Instagram post during Brasil Paralelo crisis reversed sentiment in 48 hours. The CEO being visible IS the crisis response. | ❌ MISSING |

PRESS EMBARGO LIST — MISSING

Target 10 journalists briefed by May 18, embargo lifting simultaneously May 24 at 10:00 CET.

| Publication | Market | Journalist Target | Status |
| --- | --- | --- | --- |
| Bloomberg | Global | LatAm fintech / sports finance beat | ❌ MISSING |
| Financial Times | Global | European football / neobank correspondent | ❌ MISSING |
| The Athletic | Global | FCB beat writer — direct brand story angle | ❌ MISSING |
| ESPN Brasil | Brazil | Football + commerce intersection | ❌ MISSING |
| Folha de S.Paulo | Brazil | Business section — fintech coverage | ❌ MISSING |
| Marca | Spain/LatAm | FCB official media — will cover | ⚠️ IN PROGRESS |
| El País | Spain/LatAm | Business + football crossover | ❌ MISSING |
| El Financiero | Mexico | Fintech beat, neobank coverage | ❌ MISSING |
| Infobae | Argentina | Digital native, high LatAm reach | ❌ MISSING |
| Forbes Colombia | Colombia | Business + fintech coverage | ❌ MISSING |

09  COMMUNITY DISTRIBUTION ARCHITECTURE

| Channel | Who / Where | Execution | Benchmark |  |
| --- | --- | --- | --- | --- |
| Reddit Sleeper Agents | r/fcbarcelona, r/soccer, r/brasil, r/futbol, r/argentina + country subs. | Surgence team. Pre-existing accounts with history. Organic mentions, not promotion. | Tuyo: zero paid Reddit. Pure organic seeding through authentic community members. | ⚠️ IN PROGRESS |
| Facebook Group Admins (30) | 30 admins across LatAm and MENA football groups. | Surgence outreach. Two-week relationship build before any product mention. | Nubank: seeded adoption through Brazilian Facebook groups 2014–15. Primary early growth channel. | ⚠️ IN PROGRESS |
| WhatsApp Seeding | Football fan WhatsApp groups: Brazil, Mexico, Argentina, Colombia, SEA, MENA. | Surgence team joins as members. Minimum 2 weeks before product mention. Must start TODAY. | Requires 4 weeks from start to June 11. Last possible start date = May 10. | ❌ MISSING |
| Korea Web2-First | Korean football fan forums, Naver Cafe communities, Instagram football accounts. | Local partner brief. Korean-language content. No crypto language. Card + cashback only. | Tuyo: niche-but-high-ARPU audience. Concentrate rather than dilute. | ❌ MISSING |
| Loyalty Dividend Community | Community Advisory Board: 10–20 super-fans as early testers and advocates. | Recruited before May 24. Given early access. Brief to share Loyalty Dividend card. | Chime: early super-users (Wayne Brady, Tiffany Aliche) were community-native before they were paid. | ⚠️ IN PROGRESS |
| Discord / Fan Forum | NOT in Phase 1 plan. Recommendation: one owned community space. | Create a Barça Banc Discord or Telegram. Culer Lane concept (Chime Lane equivalent). Members-only perks, early access, exclusive content. | Chime Lane: member-exclusive lanes at events = owned community loyalty layer. Apply same logic. | ❌ MISSING |

10  POST-WORLD CUP RETENTION — AUGUST ONWARD

The World Cup ends July 19. The 2026-27 La Liga season opens early August. This gap is the biggest unaddressed risk in the plan. Chime's Financial Progress Month and monthly Culer Report concept solve this. Tuyo's seasonal points mechanic (4× → 3× → 2× → 1×) provides the reward architecture.

| Mechanic | What It Is | Execution + Benchmark |  |
| --- | --- | --- | --- |
| Monthly Culer Report | Personalised monthly spend summary, cashback earned, ranking vs. other fans in your country. | Data-as-content. Month 1 report publishes August 1. Shareable PDF card format. Chime: Financial Progress Report was their highest-earned-media piece of the year. | ❌ MISSING |
| La Liga Season Activation | Season opener in August = relaunch moment. New Daily Player Drop cadence for 2026-27 squad. | New country boost calendar for La Liga matches. Loyalty Dividend updated with World Cup cashback data. | ❌ MISSING |
| Culer Lane — Members Only | Exclusive community layer for activated cardholders. Early access. VIP perks. | Chime Lane (NBA member benefit). Barça Banc equivalent: early access to Phase 2 features, Camp Nou virtual events, signed squad card drops. | ❌ MISSING |
| Referral Engine — Ongoing | Post-activation referral program. Invite a fan, earn 500-position queue jump or cashback bonus. | Nubank NPS-as-acquisition-infrastructure: every happy customer was a growth channel. Referral must be a permanent product feature, not a launch tactic. | ⚠️ IN PROGRESS |
| TGE Bridge Narrative | August: Phase 2 narrative begins. 'You've earned cashback. Imagine if it were also equity.' | Zero token language in Phase 1. August narrative shifts: '300K+ fans are already earning. Phase 2 gives them ownership.' Tuyo model: build users first, then layer token. | ❌ MISSING |
| Win-Back Campaign | 30-day inactive users receive re-engagement sequence. World Cup winner celebration mechanic. | Email + push: 'You earned $X during the World Cup. Here's your summary. Your friends earned $Y.' Chime: win-back email sequence was their highest-ROI retention channel. | ❌ MISSING |

11  ANALYTICS & MEASUREMENT FRAMEWORK

The plan has targets (750K waitlist, 250-320K downloads, 90-115K activated cards, $1.0B Y1 tx volume) but no measurement framework. Without attribution, the CAC model can't be built and paid media can't be optimized.

| Metric | Cadence | How to Measure | Target | Status |
| --- | --- | --- | --- | --- |
| Waitlist Signups | Daily | Source-tagged link per channel. UTM parameters on all paid + organic links. | 750K by Jun 11 | ❌ MISSING Owner needed |
| Referral Rate | Daily | % of signups from referral link. Queue-jump conversion rate. | >30% referral-driven | ❌ MISSING Owner needed |
| Loyalty Dividend Shares | Daily | Share events from personalised card generator. Viral coefficient. | >100K shares week 1 | ❌ MISSING Owner needed |
| App Downloads | Daily | App Store Connect + Play Console. By country, by source. | 250–320K total | ❌ MISSING Owner needed |
| Card Activation Rate | Weekly | Downloads → KYC complete → card activated. Funnel drop-off by step. | 35–45% of downloads | ❌ MISSING Owner needed |
| First Transaction Rate | Weekly | Activated cards → first spend within 7 days. | >60% within 7 days | ❌ MISSING Owner needed |
| Cashback Engagement | Per mechanic | Win Bonus claim rate. Country Boost Day uplift in tx volume. MOTM cashback redemption. | Per mechanic baseline TBD | ❌ MISSING Owner needed |
| CAC by Market | Weekly | Paid media spend ÷ new activated cards per market. | $15–30 blended target | ❌ MISSING Owner needed |
| NPS / Referral Score | Monthly | In-app NPS survey at Day 30. Referral send rate by NPS score bucket. | NPS > 50 | ❌ MISSING Owner needed |
| Creator Attribution | Per wave | UTM-tagged creator links. CPA per creator. ROAS by tier. | Tier 3 highest ROAS (Chime benchmark) | ❌ MISSING Owner needed |

12  CRISIS & COMPETITIVE RESPONSE PLAYBOOK

A financial product launch at scale will have a crisis moment. The variable is response time, not occurrence. Nubank's Cristina Junqueira reversed negative sentiment in 48 hours with a personal Instagram post. The playbook needs to be written before May 24, not during the incident.

| Scenario | Trigger | Response Protocol | Benchmark |
| --- | --- | --- | --- |
| App Crash / Outage | App unavailable >15 min on launch day or World Cup. | T+15min: CEO posts to X + Instagram. 'We know. We're fixing it.' T+30min: In-app ETA. T+2hr: Resolution post. T+24hr: Affected users get cashback credit as goodwill. | Nubank CEO model. Personal, specific. No corporate language. |
| Security / Data Incident | User data breach or fraudulent transaction spike. | Immediate: legal engaged. T+1hr: CEO statement. T+24hr: audit announced. T+7 days: remediation report. Affected users individually notified. | Early transparency only path to trust recovery in fintech. |
| Competitor Response | Nubank/Mercado Pago counter-campaign or cashback price-match. | 'They can copy the cashback. They cannot copy the crest.' Lean FCB brand. Escalate Loyalty Dividend content. Announce next mechanic early. | Nubank: leaned into NPS community vs. price war when attacked. |
| Regulatory Inquiry | BACEN/CNBV/BCRA/SFC inquires about advertising or licensing. | Pause all paid ads in that market immediately. Legal responds within 24hr. No public statement until legal reviewed. No team social posts about inquiry. | One non-compliant creator post can trigger this. Pre-empt with legal framework. |
| Negative Viral Moment | Creator post wrong. Loyalty Dividend error. FUD on X or Reddit. | Identify within 1hr (social listening required). Correct factual errors fast. Don't engage bad-faith FUD. Community advocates respond first. CEO only if it escalates. | Tuyo: slot-machine criticism. Founder explainer thread resolved it. |

13  MASTER ACTION TABLE — EVERYTHING MISSING

Every MISSING item from this plan in one place. Ordered by deadline. Assign an owner to each line before the end of this week.

| Deadline | Action | Why It Matters / What It Blocks | Owner Needed |
| --- | --- | --- | --- |
| TODAY May 10 | Sign Surgence contract | Unlocks brand identity, WhatsApp seeding, 19 downstream deliverables | Walter / FCB Legal |
| TODAY May 10 | Start WhatsApp community seeding | Needs 4 weeks minimum. Today = last possible start for June 11 | Surgence (post-signature) |
| TODAY May 10 | Appoint paid media agency | No budget model, no CAC by market, waitlist math doesn't close | Walter / FCB Marketing |
| TODAY May 10 | Identify legal counsel — all 4 markets | Creator program blocked. Any creator post is a compliance risk | FCB Legal |
| May 12 | Brand identity v1 delivery | Blocks landing page, press kit, card artwork, creator briefs | Surgence |
| May 12 | Submit app to App Store + Google Play | 7-day review minimum. Miss this = no app on launch day | Product team |
| May 13 | Begin landing page build | No waitlist capture surface = zero signups before May 24 | Web team / Agency |
| May 13 | Begin press kit assembly | Media embargo cannot be placed without assets | PR team / Surgence |
| May 14 | Paid media plan + budget submitted | Campaigns cannot be built without plan and budget approval | Media agency |
| May 14 | Creator brief + legal disclosure drafted | Wave 1 creator outreach starts May 15 | Legal + Surgence |
| May 15 | Wave 1 creator outreach (10 Tier 1) | Must post on May 24 launch day | Surgence |
| May 16 | Country-Edition card artwork to printer | Physical cards for pre-order. 8–12 week production. Already late. | Surgence + Fulfillment |
| May 17 | App Store submission deadline (hard) | 7-day Apple review buffer. No submission = no app on launch. | Product team |
| May 17 | Landing page QA complete | Must be live and tested before May 24 | Web team |
| May 18 | Press embargo placed with 10 journalists | Journalists need 6 days to write. Embargo lifts May 24. | PR team |
| May 18 | Email nurture sequence written | Day 0 email sends automatically at waitlist signup | Copywriter / CRM team |
| May 19 | Loyalty Dividend CRM data test | Must work with real FCB fan data before May 24 | Product + FCB Data |
| May 20 | Press kit finalized + distributed | Journalists need assets to write the story | PR team |
| May 20 | Paid media campaigns loaded + approved | Must be ready to launch simultaneously with May 24 announcement | Media agency |
| May 20 | Korea activation brief written | Local partner needs brief to start outreach | Surgence |
| May 20 | Analytics + attribution setup | No measurement = no optimization = no CAC model | Analytics / Growth team |
| May 20 | Crisis response playbook written | Must exist before launch. Cannot write during a crisis. | CMO + Legal |
| May 21 | OOH remnant inventory booked (minimum) | São Paulo + Mexico City minimum. June 11 World Cup opener target. | Media agency |
| May 21 | Discord / Culer Lane community setup | Owned community space for activated users post-World Cup | Community team |
| May 22 | Full launch readiness review | Go/No-Go gate. All items above must be green. | Walter + FCB + Surgence |
| May 23 | Go / No-Go decision | If 3+ critical items are red, push announcement to June 11. | FCB Leadership |
| Jun 11 | World Cup mechanics all live + tested | Country Boost, Win Bonus, MOTM, Bracket Game all must work on day 1 | Product + Surgence |
| Jul 19 | Post-World Cup retention plan built | August plan must be ready before World Cup ends | CMO / Surgence |
| Aug 1 | Monthly Culer Report — Edition 1 live | First retention content post-World Cup | Content team |
| Aug 2026 | TGE bridge narrative drafted | Phase 2 narrative begins. 'You earned cashback. Now earn ownership.' | Surgence Phase 2 team |

BOTTOM LINE FOR EXECUTION

The strategy is sound. The World Cup window is right. The Loyalty Dividend is genuinely differentiated. The community architecture is more sophisticated than anything Nubank, Chime, or Tuyo deployed at Phase 1. None of that matters if the Surgence contract isn't signed today. Sign the contract. Brief the brand identity sprint. Everything else follows.

FC Barcelona Banc · Phase 1 Updated Marketing Plan · May 10, 2026 · Prepared by Surgence Labs · CONFIDENTIAL — Not for external distribution