FC BARCELONA BANC — PHASE 1 · RACI MATRIX R = Responsible (does the work) · A = Accountable (owns the outcome) · C = Consulted (input required before action) · I = Informed (kept updated) · May 10, 2026 · CONFIDENTIAL

| Workstream | Walter (CMO) | FCB Leadership | FCB Legal | FCB Product/Tech | FCB Data | Surgence Labs | Media Agency | PR Team | Web Agency | Legal Counsel (BR/MX/AR/CO) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PHASE 0 — GOVERNANCE & SETUP |  |  |  |  |  |  |  |  |  |  |
| Sign Surgence contract | A | C | R |  |  | C |  |  |  |  |
| Appoint paid media agency | A | C |  |  |  |  | R |  |  |  |
| Appoint PR agency / team | A | C |  |  |  |  |  | R |  |  |
| Appoint web / dev agency | A |  |  | C |  |  |  |  | R |  |
| Identify legal counsel — 4 markets | A | C | R |  |  |  |  |  |  | C |
| Define Phase gate go/no-go criteria | R | A | C | C |  | C |  |  |  |  |
| Surgence entity decision confirmed | C | A | R |  |  | R |  |  |  |  |
| PHASE 1 — PRE-LAUNCH SPRINT (May 10–24) |  |  |  |  |  |  |  |  |  |  |
| Brand identity system (logo, type, color, tone) | A | I |  |  |  | R |  |  |  |  |
| Country-Edition card artwork brief | A | I |  |  |  | R |  |  |  |  |
| Country-Edition card artwork to printer | A | I |  |  |  | R |  |  |  |  |
| Landing page / waitlist (design + build) | A | I |  | C |  | C |  |  | R |  |
| Landing page QA + mobile optimization | A |  |  | C |  | C |  |  | R |  |
| App Store + Google Play submission (4 markets) | C | I |  | A |  |  |  |  |  |  |
| App Store optimization (ASO) copy + assets | A |  |  | R |  | C |  |  |  |  |
| banc.fcbarcelona.com product pages | A | I |  | C |  | C |  |  | R |  |
| Analytics + attribution setup (UTM, funnels) | A |  |  | R |  | C | C |  | C |  |
| CRM data access + LGPD/privacy compliance | C | C | C | C | R |  |  |  |  | C |
| Loyalty Dividend integration + QA | A | I |  | R | C | C |  |  |  |  |
| Press kit assembly (assets, pitch, stats) | A | C |  |  |  | C |  | R |  |  |
| Press embargo placed — 10 journalists | C | I |  |  |  |  |  | R |  |  |
| Email onboarding sequence (6 emails written) | A |  |  |  |  | C |  |  |  | C |
| Email CRM platform configured | A |  |  | R |  | C |  |  |  |  |
| Creator legal framework — disclosure language | C |  | A |  |  | C |  |  |  | R |
| Creator brief template + NDA drafted | A |  | C |  |  | R |  |  |  | C |
| Sweepstakes legal compliance (VIP Draw) | C |  | A |  |  | C |  |  |  | R |
| Financial advertising compliance — 4 markets | C |  | A |  |  |  |  |  |  | R |
| WhatsApp community seeding — prep + launch | C |  |  |  |  | R |  |  |  |  |
| Facebook group admin outreach (30 admins) | C |  |  |  |  | R |  |  |  |  |
| Reddit sleeper agent accounts primed | C |  |  |  |  | R |  |  |  |  |
| Korea activation brief + local partner | A |  |  |  |  | R |  |  |  |  |
| Paid media plan + budget (by market) | A | C |  |  |  |  | R |  |  |  |
| Paid media creative brief + asset specs | A |  |  |  |  | C | R |  |  |  |
| Meta / Google / TikTok campaigns built | C |  |  |  |  |  | R |  |  |  |
| OOH remnant inventory booked — LatAm | A |  |  |  |  |  | R |  |  |  |
| Crisis response playbook written | R | C | C |  |  | C |  | C |  |  |
| Korea Web2-first content calendar | A |  |  |  |  | R |  |  |  |  |
| Full launch readiness review (all teams) | R | A | C | C |  | C | C | C | C | C |
| Go / No-Go decision — May 23 | C | A | C | C |  | C |  |  |  |  |
| PHASE 2 — LAUNCH DAY (May 24) |  |  |  |  |  |  |  |  |  |  |
| Press embargo lift — coordinated 10:00 CET | A | I |  |  |  |  |  | R |  |  |
| FCB owned social posts (IG/TikTok/X/YouTube) | A | I |  |  |  | R |  |  |  |  |
| WhatsApp broadcast (50M fans) | A | I |  |  |  | R |  |  |  |  |
| Loyalty Dividend live — banc.fcbarcelona.com | A | I |  | R | C | C |  |  |  |  |
| Country-Edition card pre-order opens | A | I |  | R |  | C |  |  |  |  |
| Daily Player Drop — Day 1 (Instagram Stories) | A | I |  |  |  | R |  |  |  |  |
| Paid media campaigns go live | A | I |  |  |  |  | R |  |  |  |
| Reddit / community organic seeding — Day 1 | C | I |  |  |  | R |  |  |  |  |
| Founder / CEO personal thread (X) | R | A |  |  |  | C |  |  |  |  |
| Creator Wave 1 posts — Day 1 | A | I |  |  |  | R |  |  |  |  |
| Real-time monitoring + response team on | R | A |  |  |  | C | C | C |  |  |
| PHASE 3 — WORLD CUP WINDOW (June 11 – July 19) |  |  |  |  |  |  |  |  |  |  |
| Country Boost Days — mechanic + push notifications | A | I |  | R |  | C |  |  |  |  |
| Country Boost Days — content calendar | A | I |  |  |  | R |  |  |  |  |
| Win Bonus — real-time FIFA data trigger | A | I |  | R | C |  |  |  |  |  |
| Win Bonus — notification design + copy | A | I |  | C |  | R |  |  |  |  |
| MOTM Cashback — category mapping (32 matches) | A | I |  | R |  | C |  |  |  |  |
| MOTM Cashback — content + announcement per match | A | I |  |  |  | R |  |  |  |  |
| Country-Edition card — fulfillment + shipping | A | I |  |  |  | R |  |  |  |  |
| Country-Edition card — unboxing creator brief | A |  |  |  |  | R |  |  |  |  |
| Bracket Prediction Game — product live | A | I |  | R |  | C |  |  |  |  |
| Bracket Prediction Game — content + leaderboard | A | I |  |  |  | R |  |  |  |  |
| Final Ticket VIP Draw — legal compliance | C | C | A |  |  | C |  |  |  | R |
| Final Ticket VIP Draw — weekly sub-prizes announced | A | I |  |  |  | R |  |  |  |  |
| Creator Wave 2 (60 Tier 2) — briefed + live | A | I |  |  |  | R |  |  |  | C |
| Creator Wave 3 (110 Tier 3) — briefed + live | A | I |  |  |  | R |  |  |  | C |
| Creator content compliance review — ongoing | C |  | A |  |  | C |  |  |  | R |
| Creator attribution + CPA tracking | A |  |  |  |  | C | R |  |  |  |
| Paid media optimization — weekly | A |  |  |  |  |  | R |  |  |  |
| OOH — World Cup opener placements live | A |  |  |  |  |  | R |  |  |  |
| Daily Player Drop — ongoing (daily) | A | I |  |  |  | R |  |  |  |  |
| WhatsApp seeding — ongoing match-by-match | C |  |  |  |  | R |  |  |  |  |
| Facebook group community management | C |  |  |  |  | R |  |  |  |  |
| Reddit organic amplification — ongoing | C |  |  |  |  | R |  |  |  |  |
| Phase 2 earned moment — World Cup opener PR | A | I |  |  |  | C |  | R |  |  |
| Real-time data press releases (Country Boost stats) | A | I |  |  | R | C |  | R |  |  |
| Weekly funnel report — all markets | R | C |  | C |  | C | C |  |  |  |
| CAC optimization — by market | A |  |  |  |  |  | R |  |  |  |
| PHASE 4 — POST-WORLD CUP RETENTION (August onward) |  |  |  |  |  |  |  |  |  |  |
| Monthly Culer Report — Edition 1 (Aug 1) | A | I |  | C | R | C |  |  |  |  |
| Monthly Culer Report — template + design | A |  |  |  |  | R |  |  |  |  |
| La Liga 2026-27 season activation brief | A | C |  |  |  | R |  |  |  |  |
| Daily Player Drop — new season cadence | A | I |  |  |  | R |  |  |  |  |
| Culer Lane — owned community setup (Discord/TG) | A |  |  |  |  | R |  |  |  |  |
| Culer Lane — member perks program design | A | C |  |  |  | R |  |  |  |  |
| Referral engine — permanent product feature | A | I |  | R |  | C |  |  |  |  |
| Win-back email sequence — inactive users at Day 30 | A |  |  |  |  | C |  |  |  |  |
| Post-WC analytics review — cohort analysis | R | C |  | C |  | C |  |  |  |  |
| TGE bridge narrative — Phase 2 story drafted | C | A |  |  |  | R |  |  |  |  |
| Phase 2 (TGE) team briefed and scoped | C | A | C | C |  | R |  |  |  |  |
| STANDING — CRISIS & COMPETITIVE RESPONSE |  |  |  |  |  |  |  |  |  |  |
| App crash / outage — response lead | R | A |  |  |  | C |  |  |  |  |
| App crash — customer comms (push + email) | A | I |  | R |  | C |  |  |  |  |
| Security / data incident — legal escalation | C | A | R |  |  |  |  |  |  | C |
| Security incident — public statement | R | A | C |  |  | C |  |  |  |  |
| Regulatory inquiry — market-specific response | C | A | R |  |  |  |  |  |  | R |
| Regulatory inquiry — advertising pause in market | A | C |  |  |  |  | R |  |  |  |
| Competitor counter-campaign — response brief | R | A |  |  |  | C |  |  |  |  |
| Negative viral moment — social listening alert | R | C |  |  |  | C |  |  |  |  |
| Negative viral moment — community response | C |  |  |  |  | R |  |  |  |  |
| Social listening tool — always on | A |  |  |  |  | R |  |  |  |  |

| LEGEND | R | A | C | I |
| --- | --- | --- | --- | --- |
| FC Barcelona Banc · Phase 1 RACI · May 10, 2026 · CONFIDENTIAL | Responsible — does the work | Accountable — owns the outcome, one per row | Consulted — input required before action | Informed — kept updated, no action required |